## Market Readiness Report Page 1
42863
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-05-08
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017. A Medium level of risk persists for the project overall due to aggressive timelines combined with a level of uncertainty around the operation of business processes under the new Rules and Procedures and dependency on new and immature market participants. Participants have highlighted risks associated with compressed timeframes for system build and testing, registration and accreditation activities, and transition and cutover activities. Uncertainty around faults and emergency processes and jurisdictional safety regulations have also been highlighted as risk areas. |  |  |  |  | High | Med | Low | #
[7 empty] | 4 | 2 | 3 | 1
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place | [7 empty] | #1 |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed | [7 empty] | #4 |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #5 |  | #5
4.2 |  | Successfully validated critical business processes during industry testing
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #6 |  | #6 |  | #6 |  | #6
5.3 |  | Performance of, and communication between, market systems validated during industry testing | [5 empty] | #7 |  | #7 |  | #7
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place | [5 empty] | #8 |  | #8 |  | #8
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals) | [7 empty] | #8 |  | #8
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Networks (ENM, ENO) |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-05-08
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Detailed implementation plan development at risk due to ongoing uncertainty in procedural operation (e.g. meter churn), jurisdictional safety regulations and DB's faults and emergency process. Some participants have also highlighted issues with vendor procurement. Implementation Plans may need to be re-assessed when the Victorian Government releases its OIC. |  |  | Participants are increasing internal resources and are awaiting the Victorian OIC
2 | Variance reported by Participants: Updating policies and procedures on schedule is at risk due to lack of clarity on safety regulation and the detailed implementation regarding the Victorian decision to defer metering competition (awaiting the Order in Council). |  |  | Participants are continuing to engage with the relevant departments and safety bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume of contracts that need to be entered into with industry parties and variable meter service provider maturity.
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due compressed timeframes for all registration and accreditation activities. |  |  | Participants are reviewing the new e-hub accreditation guide and are encouraged to submit their planned timeframes to AEMO asap so AEMO can resource accordingly.
5 | Variance reported by Participants: Progress on this is less than expected due to required rework from the final B2B Procedure changes, uncertainty in a number of areas including meter churn, faults and emergencies, jurisdictional requirements. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources and are awaiting the Victorian OIC
6 | Variance reported by Participants: System design and development are dependent on finalisation of procedures and technical specifications for completion. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources and are awaiting the Victorian OIC
7 | Variance reported by Participants: Testing timelines are contingent on system design and build and are becoming increasingly compressed and unrealistic.
8 | Variance reported by Participants: Increasing risk reported on transition and cutover planning and implications - timing of cutover, number of inflight transactions, scope of changes required. |  |  | Participants are engaging with the newly formed Industry Transition and Cutover Focus Group to develop the industry transition and cutover plans.
Notes
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-05-08 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail has completed a high level impact assessment of the changes required by PoC on its business operations and systems, requirements have been baselined, business processes drafted and detailed system design is in progress. A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL | Within schedule | Medium | Project is tracking to plan for Dec 2017 delivery. B2B process and system updates in progress. Validation of B2B process updates and key assumptions underway in parallel with various participants. Industry test planning for EN/MC also in progress. Industry test environment refresh scheduled to align with AEMO systems. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited build timeframes, impacts arising from the Victoria competition decision, updated schema timing dependencies, limited industry testing timeframes and significant commercial agreements that must be implemented.
| Alinta Energy | Within schedule | Medium | Project progressing to plan. Impact of Victorian Changes to be determined | [7 empty] | Operating in the Queensland market before the end of the year
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to meet POC timeframes.
| Energy Australia | At risk | Medium | The Program is making steady progress but has risks associated with the Vic Government decision to delay PoC, conversion of VicAMI type 5 to Type 4 and the lack of progress on jurisdictional safety matters. There are also concerns with the progress of industry coordinated activities, such as BCP and Emergency Planning. | [7 empty] | The Program is making steady progress but has risks associated with the Vic Government decision to delay PoC, conversion of VicAMI type 5 to Type 4 and the lack of progress on jurisdictional safety matters. There are also concerns with the progress of industry coordinated activities, such as BCP and Emergency Planning. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | Medium | The project risk rating has been increased to 'high' due to: - the number of changes required to our retail billing system - the level of complexity of some of these changes - the complexity and number of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting with no effective competition At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017. | [7 empty] | The project risk rating has been increased to 'high' due to: - the number of changes required to our retail billing system - the level of complexity of some of these changes - the complexity and number of contracts that need to be negotiated with Initial MC / competitive MC - additional complexities and costs associated with delivering PoC metering changes in a regional setting where no effective competition At this stage no changes have been made to jurisdictional safety requirements which will enable remote re-energisation. This remains a risk that retailers will not achieve the full benefits without these changes. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017.
| ERM Power Retail | At risk | Medium | ERM Retail overall POC system and business process development is progressing however, the aggressive POC implementation, testing, MC Registration and eHub Accreditation timeframes place ERM Retail POC development at a Medium risk. Further, lack of confirmed safety framework for remote services across Australia (excluding VIC) and the Victorian deferment from metering competition will affect POC development in the short term.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor is 90% complete. Vic related changes are a substantial risk. Business intention is to outsource MC role. Risk considered Medium as few vendors currently available for selection. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Mojo Power Pty Ltd | Within schedule | Medium | [8 empty] | [Risk in Victoria - Treatment of VIC AMI by market]
| Momentum Energy | Within schedule | Low
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. During April the program reported Red internally due to issues around Scope, Schedule and Cost. As of the 1st of May, these issues have been resolved and the program is now back to Amber. Project delivery progressing. High number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around VIC derogation extension is detracting from and delaying the delivery of the program (Submissions have been made proposing a deviation from the overall B2B procedures – which Origin Energy is against); • Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our planning and implemenation of activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. Cutover • Time frame for cutover is too tight: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. Is the aggregated risks fully understood? Comms • Comms plan to impacted parties (i.e. Electricians, Customers) is still not understood; AEMO needs to take the lead on this activity. | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. During April the program reported Red internally due to issues around Scope, Schedule and Cost. As of the 1st of May, these issues have been resolved and the program is now back to Amber. Project delivery progressing. High number of delivery risks continue to be monitored and mitigated for the duration of the project Delivery • Uncertainty around VIC derogation extension is detracting from and delaying the delivery of the program (Submissions have been made proposing a deviation from the overall B2B procedures – which Origin Energy is against); • Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our planning and implemenation of activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. Cutover • Time frame for cutover is too tight: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. Is the aggregated risks fully understood? Comms • Comms plan to impacted parties (i.e. Electricians, Customers) is still not understood; AEMO needs to take the lead on this activity. | [5 empty] | Areas of Concern: Delivery • Uncertainty around VIC derogation extension is detracting from and delaying the delivery of the program (Submissions have been made proposing a deviation from the overall B2B procedures – which Origin Energy is against); • Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our planning and implemenation of activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. Cutover • Time frame for cutover is too tight: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. Is the aggregated risks fully understood? Comms • Comms plan to impacted parties (i.e. Electricians, Customers) is still not understood; AEMO needs to take the lead on this activity.
| Pacific Hydro | At risk | Medium | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS WP3. 2. B2B - As Built Consultation - per IEC May Agenda item. 3. B2B - technical solution -still under review by AEMO and yet to be formally advised. 4. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 5. Vic Government decision not to proceed with PoC. 6. Jurisdictional safety review of the remote Re-en/De-en process. There is also an issue with other Market changes, e.g. Retail Transfer Errors to take effect 3 August 2017, being introduced within the PoC delivery timeframe.
| People Energy Pty Ltd | At risk | Medium | Due to the implecations of the Victorian Government decision and the impact it has surrounding the system and process changes, the overall project remains as a medium risk.
| Pooled Energy | Within schedule | Medium | Project remains on track. Continuing to work through procedural changes. | [7 empty] | Project remains on track. Continuing to work through procedural changes.
| Powershop | Within schedule | Medium | Powershop is currently undertaking a gap analysis of changed proceduress. This will form the scope of change required for Powershop developers.
| Red Energy & Lumo Energy | At risk | High
| Simply Energy | Within schedule | Medium | The program has identified three keys risks: 1. outcome of Meter Churn Procedures workshop held on the 24th Feb 2017 might not be suitable for the industry; 2. Faults and Emergencies Process not confirmed by Distribution Businesses. 3. VIC Govt decision of deferral of metering competition has opened a few questions that's impacting our design and build, e.g. new connections process in VIC; Plan of approach for VICAMI meters post go-live (type 5 vs type 4 issue), etc. | [13 empty] | Simply Energy has progressed as per it's internal plan of Power of Choice Program of Work and have prioritised B2M changes in order to commence testing for r35 schema, currently targetting July 2017.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Alinta Energy |  |  | Within schedule | Medium |  |  | Within schedule | Medium |  |  | Within schedule | Medium
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Mojo Power Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | At risk | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Powershop |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | High
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | 100% | 51% - 60% | 81% - 99% | 71% - 80% | Completed (100%) | 25% | 61% - 70% | 71% - 80% | 71% - 80% | Completed (100%) | 41% - 50% | 31% - 40% | 50% | 41% - 50% | 81% - 99% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | 1% - 10% | 75% | 31% - 40% | 71% - 80% | 51% - 60% | 31% - 40% | 25% | 11% - 20% | 51% - 60% | 61% - 70% | 51% - 60% | 21% - 30% | 11% - 20% | 50% | 1% - 10% | 71% - 80% | 51% - 60%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 21% - 30% | Completed (100%) | 25% | 41% - 50% | 71% - 80% | 71% - 80% | 21% - 30% | 25% | 61% - 70% | 31% - 40% | 21% - 30% | 51% - 60% | 21% - 30% | Not started (0%) | 75% | 81% - 99% | 21% - 30% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 1% - 10% | Not started (0%) | 0% | 21% - 30% | 51% - 60% | 21% - 30% | Not started (0%) | 0% | 61% - 70% | Not started (0%) | 21% - 30% | Not started (0%) | 1% - 10% | 1% - 10% | 0% | Not started (0%) | 1% - 10% | 1% - 10%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 11% - 20% | 21% - 30% | 25% | 21% - 30% | 41% - 50% | 1% - 10% | 11% - 20% | 0% | 61% - 70% | 1% - 10% | Not started (0%) | Not started (0%) | 1% - 10% | 1% - 10% | 25% |  | 31% - 40% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 11% - 20% | Completed (100%) | N/A | 11% - 20% | 51% - 60% | 1% - 10% | 51% - 60% | 0% | 61% - 70% | 31% - 40% | 61% - 70% | 31% - 40% | 1% - 10% | 1% - 10% | 25% |  | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Not started (0%) | N/A | N/A | 1% - 10% | 1% - 10% | Not started (0%) | Not started (0%) | N/A | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | N/A |  | N/A | Completed (100%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 41% - 50% | 11% - 20% | 25% | 31% - 40% | 71% - 80% | 1% - 10% | 21% - 30% | 0% | Completed (100%) | 31% - 40% | 51% - 60% | 41% - 50% | 1% - 10% | 21% - 30% | N/A |  | 31% - 40% | 41% - 50%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | Not started (0%) | 25% | 41% - 50% | 41% - 50% | Not started (0%) | 41% - 50% | N/A | Completed (100%) | Not started (0%) | 21% - 30% | 1% - 10% | Not started (0%) | 11% - 20% | N/A |  | Not started (0%) | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | Not started (0%) | 0% | 11% - 20% | 11% - 20% | Not started (0%) | 41% - 50% | 0% | 31% - 40% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% |  | Not started (0%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 0% | 61% - 70% | 71% - 80% | 51% - 60% | 11% - 20% | 25% | 21% - 30% | 1% - 10% | 71% - 80% | 21% - 30% | 11% - 20% | 21% - 30% | 50% | 21% - 30% | 41% - 50% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 61% - 70% | 31% - 40% | 0% | 31% - 40% | 51% - 60% | 1% - 10% | 11% - 20% | 0% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 1% - 10% | 1% - 10% | 50% | 1% - 10% | 21% - 30% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 25% | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 61% - 70% | 51% - 60% | 75% | 61% - 70% | 81% - 99% | 31% - 40% | 31% - 40% | 50% | Not started (0%) | 41% - 50% | 71% - 80% | 31% - 40% | 21% - 30% | 1% - 10% | 50% | 21% - 30% | 41% - 50% | 71% - 80%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Not started (0%) | 21% - 30% | 25% | 1% - 10% | 31% - 40% | 1% - 10% | 31% - 40% | 25% | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | 11% - 20% | Not started (0%) | 0% | Not started (0%) | 1% - 10% | 51% - 60%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 21% - 30% | 0% | 1% - 10% | 11% - 20% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | 11% - 20% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 1% - 10% | 0% | 1% - 10% | 1% - 10% | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 1% - 10% | Not started (0%) | 25% | Not started (0%) | Not started (0%) | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | 0% | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | N/A | N/A | N/A | N/A
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near completion. However, given the remaining uncertainty of rule and procedure operations, this is still considered 'at risk'. | Vic delay may require re-assessment. | [5 empty] | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. Procedure and meter type implication due to VIC derogation extension are not yet clear. Faults and Emergencies process not yet finalised |  |  |  | Powershop is currently undertaking a gap analysis of changed proceduress. This will form the scope of change required for Powershop developers.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established, Detailed plan in place and being tracked against. |  | .In Progress .Victorian impact to be included .RFI for metering services has been issued. | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | Progress has been impacted by the Victorian decision. | Significant changes required to internal systems and processes because of the mangitude of the changes to the final procudures has increased the scope and complexity of the project. Also reliant on contracted parties being ready from go-live date.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | The ACT Government is reviewing the ACT regulatory framework |  |  | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. | At risk as there are still unknowns in regards to jurisdictional safety requirements. | Queensland jurisdictional safety requirements are yet to be addressed. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions |  | scheduled and commenced. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  |  |  | Excludes Victoria and any potential changes required for Victoria | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [7 empty] | Commenced | Preliminary advice has been sought with regards to regulatory compliance. In addition to direct metering competition regulatory changes, a key challenge for Aurora Energy is to consider the wider (/indirect) regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). | Red due to the lack of clarity on safety regulations | Queensland jurisdictional safety requirements are yet to be addressed. There has also as yet been no resolution of the inconsistencies / issues with Meterology Procedure Part A - Queensland jurisdictional provisions. This has been raised with AEMO and with the Queensland Department of Energy and Water Supply and must be addressed prior to 1 December 2017. |  | not yet scheduled. |  |  | Policy changes/decisions still being derived through Blueprinting | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Contracts and commercial arrangements are being reviewed. | Flagging risk due to the number of commercial agreements required. | Commenced. RFI responses recieved | Activity has commenced for customers and vendors as part of POC implementation. |  | These processes have commenced. Significant complexity due to lack of precedent in negotiating agreements of this nature. |  | not yet scheduled. |  |  | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. |  |  |  |  | Internal management of this item | Meter Churn (Package 3) is causing some issues in finalising high level agreements.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Assessment and planning has commenced. |  | Contractual arrangements to support Accreditation requirements through a nominated MC. | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process has been passed onto the Business to enable the process to begin. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. |  |  |  | unclear testing registration requirements and impacts at this time. |  |  | Underway for new Market Roles |  |  |  | Powershop is about to commence a confirmation process with third-parties to acertain their position | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [8 empty] | Fulfillment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. | [6 empty] | Planning and preparation in progress |  |  |  |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment in progress |  | Operating model development commenced | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. |  |  |  | not yet scheduled. |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines |  |  |  |  | Internal management of this item
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Operating model development commenced | The recruitment of specialist human resources to cater for the rule change has commenced. | [6 empty] | Policy changes/decisions identified |  |  |  |  | Internal management of this item
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Training requirements are currently being assessed as part of the business process and system review and updates. | The magnitude of change and the number of staff required to be trained make this a high risk activity. |  |  | not yet scheduled. |  |  | Training requirements and resourcing determined and magnitude of change is understood |  |  |  |  | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Impact of Meter Churn clarification being assessed. |  | Commenced | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Victorian decision requires additional assessment | The significance of the changes to our billing system and the added complexity of developing a mechanism to address non-PoC areasnot subject to the provisions in Chapter 7 of the NER (isolated networks) is challenging in the timeframes. EEQ is also reliant on contracted parties being ready for go-live. Additional complexities and time constraints also as a result of negotiating ring fencing strategy / waivers with the AER which will impact contract negotiations. |  | commenced and in schedule |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; | [5 empty] | VIC decision has posed some risk in detailing internal processes; Faults and Emergencies process is not confirmed by the Distribution businesses, posing a bigger risk on retailers to implement end to end process.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Key processes have been drafted for CATS and B2B processes and are in review. |  | Commenced | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | As above | [5 empty] | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; Engagement with networks is planned to confirm smooth transition. | [5 empty] | VIC decision has posed some risk in detailing internal processes; Faults and Emergencies process is not confirmed by the Distribution businesses, posing a bigger risk on retailers to implement end to end process.
4.3 |  | The validation of business processes during industry testing | [8 empty] | Activity has not yet started. |  |  |  | not yet scheduled. |  |  | Not Commenced | [5 empty] | Due to commence in July 2017
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Detailed design in progress. |  | Vendor is looking for final arrangements out of the victorian derrogation and meter classification to finalise requirements and design documents | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging systems. The aggressive timeframe impacts on the ability of Aurora Energy's key vendors (including, but not limited to, prospective Metering Coordinators) to deliver the required system changes. | Progress has been impacted by the Victorian decision. | Blueprinting complete. Significant complexity and number of changes to systems is creating challenges in the timeframes. Internal scope review currently underway. |  | Vendor at 47% completion of overall project plan |  | System development is reliant on external vendor, delays in final market procedures will impact readiness activities | Detailed impact assessment of system changes has completed. Review of updated B2B procedures in progress. VIC derogation extension impact assessment ongoing. Schema version considered for B2B will be R36 and B2M will be R35. Transaction Acknowledgment to match the version of the request | A full assessment cannot be undertaken until the technical solution for B2B is known. This is further complicated by the Vic Government decision not to proceed with PoC. |  |  |  |  | Business requirements complete
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Commenced | Aurora Energy has engaged its key vendors to commence functional and technical design for system changes. However, systems changes will still be impacted by the any further changes to the B2B/B2M environment as part of Work Package 3. | There are risks associated with the compressed timeline. |  |  | vendor at 15% of retail sys build plan |  |  | Systems development in progress | As per the comment in 5.1. Also Business Requirements Specification documents are yet to be approved. |  |  |  |  | Solution workshops have commenced with vendors, functional specs underway
5.3 |  | The internal testing of market systems for your business | [8 empty] | Test Strategy development has commenced to support internal and industry testing. Aurora Energy will be engaging in the first round of industry testing in May 2017. | At risk, due to tight build and testing timelines to meet Dec 1st. | [5 empty] | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in July 2017
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Aurora Energy will be engaging in the first round of industry testing in May 2017. | Dependency on AEMO Industry Test Plans and schedules. | [5 empty] | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in August 2017
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Aurora Energy will be engaging in the first round of industry testing in May 2017. | AEMO Industry Test Strategy calls performance testing out of scope. It is unclear how this activity will be performed. | [5 empty] | Not Commenced | As per 5.2 |  |  |  |  | Scheduled to commence in August 2017
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | Risk around AEMO Industry & Cutover Plan progress. As per the AEMO Readiness Strategy draft was expected in April. | [5 empty] | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc). Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. | [6 empty] | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Bulk Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover;
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL | Alinta Energy | Aurora Energy | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Mojo Power Pty Ltd | Momentum Energy | Origin Energy | Pacific Hydro | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | [6 empty] | Progressing with working assumptions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. |  | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. Lack of jursidictional changes represents a risk to EEQ. | [10 empty] | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [10 empty] | Ongoing discussions with the Department of Energy and Water Supply and engagement with the Electrical Safety Office. Lack of jursidictional changes represents a risk to EEQ. | [5 empty] | Closely monitor Vic Government's progress on this matter.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | Escalated and added resource to commercial preparations. | [8 empty] | Origin has onboarded additional Business and Technology resources | [5 empty] | Package 3 scope should hopefully resolve the issues raised by the industry, however we're awaiting for the outcome.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy is proceeding on the assumption that accreditation will be received. |  | Awaiting AEMO publication of retailer e-hub requirements
2.5 |  | The fulfilment of accreditation and registration obligations | [15 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [8 empty] | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. |  | Increasing internal resources to undertake the analysis and development of new business processes to achieve compliance with obligations. | [10 empty] | Awaiting VIC Order of Council; Distribution businesses to provide their positions as soon as possible
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [21 empty] | Awaiting VIC Order of Council; Distribution businesses to provide their positions as soon as possible
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. |  | Increasing internal resources to undertake the analysis and development of new business processes is currently underway. | [5 empty] | Engaging with AEMO through the Systems WG and closely monitoring Vic Government's progress on the regulatory changes.
5.2 |  | The development and build of appropriate market systems for your business | [8 empty] | Aurora Energy is in the process of gathering detailed business and system requirements and engaging with key vendors. | [7 empty] | As per the comment in 5.1 and engaging with our vendor to finalise/agree known changes.
5.3 |  | The internal testing of market systems for your business | [16 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [16 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [9 empty] | EA to seek clarification to AEMO on this item. | [6 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [15 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
|  |  |  | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
|  |  |  | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
|  |  |  | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No
ActewAGL Retail | Yes | Yes | Yes
AGL | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No
Click Energy Pty Ltd | No | No | No
Covau Pty Limited | No | No | No
COzero Energy Retail Pty Ltd | No | No | No
Diamond Energy Pty Ltd | No | No | No
Energy Locals Pty Ltd | No | No | No
EnergyAustralia | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | No | No
Globird Energy Pty Ltd | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes | Yes
Macquarie Bank Limited | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes
Next Business Energy Pty Ltd | No | No | No
Online Power and Gas Pty Ltd | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No
Origin Energy | Yes | Yes | Yes
Pacific Hydro | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | No
Powerdirect Pty Ltd | No | No | No
Powershop Australia Pty Limited | Yes (using March report) | Yes | No
Progressive Green Pty Ltd | No | No | No
Qenergy Limited | No | No | No
Red Energy | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No
Simply Energy | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | No | No | No

## Distributor Reports
| 2017-05-08 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | AAD has received it's first set of code drops (2 of 17) and is currently testing these releases. Business process review continues with approximately 15% of all business process changes complete and an additional 20% underway. Total project progress is estimated at 17%. | [7 empty] | AAD has reviewed the registration process to become the initial MC and is currently preparing material for submission to AEMO. Further work is being undertaken to assess the B2B eHub accreditation requirements. | [5 empty] | Accreditation transfer and registration starting 2 March is a risk area and it is noted that AEMO will still be developing systems and processes at the time industry is requested to start this process. AAD received the registration information for initial MC requirements and is currently assessing these requirements. Moreover, the B2B eHub requirements have (at the time of writing) not been fully released and further revisions are being received from AEMO. The readiness of AAD to interface with the AEMO B2B eHub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD.
| Ausgrid | At risk | Medium | We have established a formal ICT project and assigned resources. A number of significant IT rebuilds are expected to be required in order to facilitate the new B2B requirements. | [7 empty] | Issues noted above (section B) impact on all these categories.
| AusNet Services | At risk | High | Project in progress. The overall risk rating is a consequence of; 1. Schedule and Scope risk is significant given the lack of maturity in strategies for Industry Testing, Industry Systems Implementation and Market Transition and an underestimating of the magnitude of these activities. 2. Uncertainty about the means to be used by the Victorian Government to implement the deferral of Metering Competition after the derogation expires, including lack of definition of whether Vic AMI Meters will be treated as Type 4, Type 5 or a mixture. 3. The scope of the changes are significant, requiring development resource/effort/cost beyond initial estimates. | [7 empty] | The scope of changes to be delivered are greater than anticipated and delivery timeframes are highly compressed. Unable to assess ability to align with Industry Testing and Market Transition phases as strategies for these activities have not been finalised.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Within schedule | Medium | CitiPower/Powercor is progressing its analysis and build phase in accordance with the program schedule. CitiPower/Powercor is preparing, and has registered, for Phase 1 industry testing. | [7 empty] | The Victorian Government has decided to defer the introduction of metering competition in Victoria for small customers until at least the end of 2020. In line with this decision, CitiPower and Powercor are to become a compliant Metering Coordinator/Metering Provider/Meter Data Provider, limited to small customer metering installations within it's network territory. CitiPower and Powercor has undertaken an initial assessment of additional requirements to provide new and replacement metering services from 1 December 2017. This assessment cannot be completed until the Victorian government orider in council is received
| Endeavour Energy | At risk | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures. The B2B procedures requires significant system and process changes, however there is only 6-7 months to design and develop and to test with the market to achieve accreditation. It is noted that registration as a B2B e-Hub Participants is required before the B2B e-Hub can be used. This registration process is also at risk as there is a dependency to demonstrate system compliance with the B2B procedures. AEMO facilitated a workshop on the meter churn process for participants to highlight issues and more efficient process options. AEMO later clarified that there will be no changes to the procedures for the meter churn process. However some participants have indicated that they intend to escalate this further. There is a risk that by the time this issue in resolved it could further shorten system design and build timeframes. The final determination for the "as built" consultation for AEMO procedures will not be published until 30 November 2017 which leaves no time to implement any changes for market start on 1 December 2017. To mitigate this we are actively participating in the various working groups including the PoC-WG, B2BWG, ITWG, RWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | Distributor: Status "at risk", Risk "medium", comment as per project Metering Coordinator, Meter Provider, Meter Data Provider: Status "within schedule", Risk "low" | [5 empty] | This report is for Endeavour Energy as at 30 April 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project is progressing slightly behind its planned schedule, however it is recoverable and will meet compliance requirements of 1 December 17. Key focus for the project currently is on key activities relating to confirmation of the assumptions made in interpretation of the B2B procedures with retailers and MC's. Joint coordination across multiple parties is a key consideration which requires mutual agreement to enable continual provision of services to customers. | [7 empty] | The magnitude of change in the final version of the B2B Procedures was larger than expected. The project is currently 'At risk'.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. Timing is very tight deliver required systems changes to enable Essential Energy to participate in B2B industry testing from August 2017, with no tolerance for delays. Essential Energy is working closely with vendors to ensure required systems are delivered on time with internal testing completed in readiness for industry testing. Additional resources have been assigned to assist in supporting program delivery. | [7 empty] | Distributor: Risk rating upgraded to high due risks associated with systems delivery in preparation for industry testing from August 2017. Program schedule is tight and does not provide tolerance for any delays. Meter Data Provider: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 7 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty of delivery scope associated with the Victorian Government Option 4 - Defer Competition decision; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to perform a Type 4 data conversion and cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas. | [7 empty] | With 7 months to go-live on 1 December 2017, the project is rated at MEDIUM risk this report due to 1. the uncertainty of delivery scope associated with the Victorian Government Option 4 - Defer Competition decision; 2. the adequacy of the proposed industry testing scope and timeframe; 3. the proposed go-live date of 1 December 2017 causing a need to perform a Type 4 data conversion and cutover mid week, at a Financial Month End period prior to the Financial & Regulatory Year End period, and during a period of high volumes for Customer new connections, adds and alts pre-Christmas.
| SA Power Networks | Within schedule | Medium | Currently within SAPN delivery schedule tolerance. Closely monitoring IT system development/build to ensure timely delivery of system changes.
| TasNetworks | At risk | Medium | TasNetworks' market systems build has commenced and current schedule will allow TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window. System build timelines will be challenging to meet. Business and change management activities within schedule.
| United Energy | At risk | Medium | Internal preparations continue to progress well. The amber status reflects the impact the Vic. Govt. deferral decision, which necessitated revisions to designs and continues to put pressure on the critical path. Risk rating reflects the remaining uncertainty over meter specifications and meter classification requirements for new meters (Type 5 vs Type 4). | [7 empty] | UE operates in Victoria only. Jurisdictional status refects overall position. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government decision to defer metering competition has created a number of uncertainties, including: a) whether the DB role as newly-appointed MC after 1 Dec remains regulated (UE is assuming that it will) b) whether new meters after 1 Dec 2017 will be classified as Type 5 or Type 4 and c) whether new meters 1 Dec 2017 will be required to meet the national specification as well as Victorian AMI. These uncertainties may result in additional scope and cost, and potentially an inability to be fully compliant by 1 Dec 2017. 2) Until 8 May 2017, lack of definitive direction on whether UE's existing VICAMI meters can remain as Type 5 MRIM was creating uncertainty around whether system changes, data changes and accreditation for Type 4 meters will be required in this area. On 8 May 2017, AEMO issued an information paper which has confirmed that existing meters can remain as MRIM in MSATS, and that existing meter reading substitution type codes can continue to be used for these meters, subject to bi-lateral agreements with retailers. UE is assessing what form these agreements will have to take, and whether achieving agreements with all affected retailers is feasible. 3) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although this is yet to be confirmed. If transition is required, it will be an activity over which UE does not have full control, particularly given there are currently no accredited Embedded Network Managers in the market. 4) UE is concerned that the lateness of procedures finalisation and the complexity and scale of testing with the increased number of market participants may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid |  |  | At risk | Medium
| AusNet Services | [10 empty] | At risk | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | Within schedule | Medium
| Endeavour Energy |  |  | At risk | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | Within schedule | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | At risk | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 51% - 60% | 81% - 99% | Completed (100%) | 81% - 99% | 61% - 70% | Completed (100%) | 71% - 80% | Completed (100%) | 81% - 99% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 51% - 60% | 31% - 40% | 31% - 40% | Completed (100%) | 61% - 70% | 81% - 99% | 51% - 60% | 61% - 70% | 81% - 99% | 51% - 60% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 51% - 60% | 31% - 40% | 51% - 60% | Completed (100%) | 51% - 60% | 41% - 50% | Completed (100%) | 51% - 60% | 81% - 99% | 31% - 40% | 61% - 70%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 41% - 50% | 21% - 30% | 31% - 40% | 31% - 40% | 41% - 50% | Not started (0%) | 1% - 10% | 31% - 40% | 31% - 40% | 21% - 30% | 21% - 30%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 31% - 40% | 1% - 10% | 11% - 20% | 51% - 60% | 31% - 40% | 11% - 20% | Not started (0%) | 41% - 50% | 21% - 30% | 1% - 10% | 21% - 30%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 51% - 60% | 1% - 10% | 31% - 40% | 41% - 50% | Completed (100%) | 71% - 80% | 21% - 30% | 21% - 30% | 21% - 30% | 41% - 50% | 11% - 20%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 41% - 50% | Not started (0%) | 1% - 10% | Not started (0%) | 21% - 30% | 11% - 20% | 21% - 30% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | 31% - 40% | 61% - 70% | Not started (0%) | 71% - 80% | 31% - 40% | 11% - 20% | 41% - 50% | 31% - 40% | 21% - 30% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 31% - 40% | 1% - 10% | Not started (0%) | 41% - 50% | 1% - 10% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 11% - 20% | 21% - 30% | Not started (0%) | Not started (0%) | 21% - 30% | 1% - 10% | Not started (0%) | 21% - 30% | 1% - 10% | Not started (0%) | 1% - 10%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 31% - 40% | 31% - 40% | 71% - 80% | 71% - 80% | 71% - 80% | 41% - 50% | 31% - 40% | 51% - 60% | Completed (100%) | 41% - 50% | 81% - 99%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 31% - 40% | 11% - 20% | 11% - 20% | 61% - 70% | 31% - 40% | 11% - 20% | Not started (0%) | 41% - 50% | 81% - 99% | 1% - 10% | 81% - 99%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | Completed (100%) | 51% - 60% | 51% - 60% | 61% - 70% | 31% - 40% | 11% - 20% | 71% - 80% | 41% - 50% | 81% - 99% | 81% - 99%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | 1% - 10% | 31% - 40% | 31% - 40% | 1% - 10% | 1% - 10% | 1% - 10% | 41% - 50% | 21% - 30% | 11% - 20% | 31% - 40%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | Not started (0%) | 11% - 20% | 31% - 40% | Not started (0%) | 1% - 10% | 1% - 10% | 1% - 10% | 21% - 30% | 1% - 10% | 11% - 20%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10% | Not started (0%) | 1% - 10% | 1% - 10% | 21% - 30% | 1% - 10% | 1% - 10% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%) | 1% - 10% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | At risk | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Not within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | At risk
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | At risk | Completed | At risk | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | At risk | At risk | Within schedule | At risk | At risk | At risk | At risk | Within schedule | At risk | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | N/A | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | N/A | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. |  |  |  |  | High-level scope and requirements documents have been signed off by the business. Currently performing the organisational impact assessment. |  | JEN was 100% complete based on option 1. Now that Vic Government has chosen option 4, we are undertaking a new assessment - still waiting for OIC scope clarification. |  | TasNetworks has updated impact assessment for Pack 2 and B2B. Further updates pending Pack 3.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is commencing testing on the first round of system changes which will be subject to further review depending on changes to requirements issued by AEMO in future. Business processes and procedures are also undergoing review with all work practices and supporting documentation for two major branches currently underway. |  | Implementation plans for internal systems established and in progress. Lack of certainty about treatment for AMI Meter Type creates significant scope risk. Development of Industry implementation and market transition plans required to validate internal scope/approach. |  |  | The magnitude of change in the final version of the B2B Procedures has impacted planning activities and the associated schedule. | Agile delivery methodology has recently been implemented for system changes required to support Power of Choice. This has delayed the finalisation of implementation planning, with amendments required to support the new delivery methodology. | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | Governance and Plans are in place. Resource recruitment is currently being finalised. | Further planning required for business process and change management.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | A high level assessment of the legal obligations will continue throughout the project as AEMO finalises the program requirements. |  | Possible delay in definition of the method to be used by the Victorian Government to implement the deferral of metering competition following the end of derogation. Uncertain framework for treatment of Vic AMI Meters (Type 4/5). |  |  | Ongoing activity - currently under review by organisational specialists. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | Monitor of changes from WP3 & B2B "As Built" procedures for impacts and changes | Still working through AEMO guidelines and jurisdictional safety requirements. | The Vic Govt. deferral decision has raised a number of uncertainties, including: 1: The nature of UE's role as MC role for new meters after 1 Dec 2: Whether new meters after 1 Dec will need to meet both Vic AMI and national specs or just Vic AMI. 3: Whether new meters after 1 Dec will be classified as Type 5 or Type 4. Note: Based on AEMO communications 8 May 2017, it is expected that existing meters will remain Type 5 MRIM.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | During the period February - April 2017 AAD has commenced work on legal agreements relating to customer contracts, initial MC agreements with retailers, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. |  | Possible delay in definition of the method to be used by the Victorian Government to implement the deferral of metering competition following the end of derogation. Uncertain framework for treatment of Vic AMI Meters (Type 4/5). | Note: In line with CitiPower/Powercor program delivery schedule. |  | Commencement will occur upon completion of activity 2.1. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule |  | This work is dependent on finalisation of the deferral details and resolution of the uncertainties listed above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. |  | Definition of B2B Procedures (e.g. New Connections) and finalisation of Market Roles required to complete establishment of commercial arrangements | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule | DNSP T&C's | Plans are in place to address the commercial implications, and resourcing is now in place. Initial assessments have commenced.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has reviewed the requirements to register as an initial MC and is preparing the required materials for submission to AEMO. B2B eHub requirements are now being assessed in line with material recently released by AEMO. |  |  | Note: Following the state government decision to defer the introduction of metering competion in Victoria, CitiPower and Powercor will need to further assess our accrediation and registrations requirements. |  | Received notification from AEMO representatives that state the existing LNSP, MPB and MDP accreditations will continue. MC will be a registration process given our current RP role, and eHub Accreditation will be required. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes |  | Accreditation requirements for UE are not clear, due to uncertainty on whether new VICAMI meters will be Type 5 or Type 4. Details of accreditation requirements (eg the subset of checklists that will be applied to the Vic DBs with existing Type 5 accreditation) are not yet clear. Note: Based on AEMO communications 8 May 2017, it is expected that existing meters will remain Type 5 MRIM.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | An Accreditation team has formed, commencing accreditation planning in preparation for the release of the Accreditation and Registration plan by AEMO. |  |  | In line with SAPN program delivery schedule |  | Plans and funding are in place to cover UE accreditation, but requirements are still not fully clear. Time and effort will be required to ensure that internal processes & policies meet the accreditation criteria. This is expected to take several months, leading to accreditation occurring in late Q3/Q4 2017.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | AAD is recruiting additional resources to back fill operational roles in anticipation of future testing requirements commencing late June 2017. In addition, a detailed assessment of ongoing operational resource requirements has commenced to ready the business for the transition and post PoC go-live activities. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently analysing the human resources impact due to POC implementation. This activity is due for completion by late June. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | AAD is currently recruiting additional people to fulfil the operational duties affected by project specific activities. Other recruitment requirements are being assessed as above. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | An Organisational Impact Assessment is in progress to determine POC recruitment and HR requirements to fulfil operational functions. |  | Not required - out of scope. | In line with SAPN program delivery schedule |  | Not required until late 2017
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Identification of training requriements has begun, however, development of this training is yet to commence as it is dependent on other changes (processes, systems, etc.) that are currently underway. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Training approach has commenced. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes | Training Strategy under development. | Development of training strategy and training needs analysis for all business units is nearing completion.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed reviews of AAD documentation has begun and resourcing for the changes has been completed. AAD is now in the process of carrying out the required reviews, consultation, workshops, etc. required to design and implement the required changes. |  | Uncertain of industry transition and cutover approach | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | Completed last month (April 2017) | Core business processes drafted and under review. | Assessment of business and process impacts, which was preivously completed, is being amended for changes arising from Vic deferral.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. |  |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - currently documenting current and future state processes through development of detailed requirements. Progress on this is less than expected due to required rework, due to the nature of the final B2B Procedure Changes. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In line with SAPN program delivery schedule |  | With the publication of SMP/B2B procedures on 6 Mar 2017, the remaining business process documents were completed and approved in mid March. Since then, the Victorian deferral decision has necessitated a full review of all process designs, with some being rendered irrelevant until 2021 or later, and many others requiring revisions. This work has impacted the critical path of solution design and build.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. |  | Subject to finalisation of market procedures Industry Testing approach. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is ongoing. The Scope of August industry testing remains unclear. Confirming the scope of industry testing as soon as possible would enable businesses to effectively meet the industry testing date. |  |  | In line with SAPN program delivery schedule |  | Plans are in place to execute industry testing. However the current draft of B2B procedures includes the movement of currently enforceable details into a non-binding "guidance" category. The industry considers some of these details to be necessary for uniform, reliable end-to-end processing in the market. UE is concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Final requirements have been received and are being incorporated into the design and development elements of system changes. | System impacts have been assessed in detail. The overall solution design is complete. | Schedule for delivery of market system changes may be impacted by extent of changes required, and uncertainty regarding market testing and transition. Subject to assessment of Vic Gov't approach to deferral of MC. | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Ongoing activity - currently developing market systems detailed requirements and design documents. The magnitude of change in the final version of the B2B Procedures particularly with regard to the Notified Party and OWN transactions in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Timelines are becoming increasingly unrealistic due to these changes. | Agile delivery approach now being applied to system changes, this will extend the timeframe for development of requirements and design for implementation. | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes |  | The Vic Govt. deferral decision has necessitated updates to numerous business process and functional designs that had previously been approved. This has impacted the critical path of solution design and build activities.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The first round of system changes entered test in March but will be subject review and possible change depending on further AEMO updates. Further code drops are scheduled from April through June. | The implementation phase is underway. Detailed designs continue to be prepared. Build activities have commenced. Final build estimates will be prepared as the designs complete. | Build process underway. Impact of changes required to support option selected by Vic' Gov't in progress. Updated EVM (B2B Validation Module) required to be available by end of May to meet industry testing timelines | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | The magnitude of change in the final version of the B2B Procedures particularly with regard to the NP and OWN's in the latest B2B Guidelines requires a revisit of requirements and reassessment of design. Development and build timelines are becoming increasingly compressed and unrealistic. | Agile delivery approach now being applied to system changes, with sprints being delivered over a 3 week period. | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes | Design activity almost complete and build activity underway. Systems build and testing timelines continue to be challenging. | The Vic Govt. deferral decision has necessitated updates to numerous business process and functional designs that had previously been approved. This has impacted the critical path of solution design and build activities.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Testing is underway on the first 2 of 17 code drops received in March 2017. | Not at the stage of testing market systems. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. Testing timelines are becoming increasingly compressed and therefore 'At risk'. | Agile delivery approach now being applied to system changes, with sprints being delivered every 3 weeks for internal testing. | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | In progress; no major changes | Test Strategy complete. Test planning activities underway. | System testing is progressing well in areas unaffected by the deferral decision. Testing in remaining areas is underway but commenced later than planned due to redesign work.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  |  | In line with SAPN delivery schedule | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Not at the stage of testing market systems. | Market Test Strategy and approach required. Final specifications of hub required. Role of non-functional testing as part of Industry Testing is required. | Note: In line with CitiPower/Powercor program delivery schedule. |  | Test approach is tracking to schedule. |  | Per the industry test plan - this is out of scope. | In line with SAPN delivery schedule | TasNetworks to participate in industry towards the latter part of AEMO's proposed testing window | Plans in place and resourcing agreed. Not yet due.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is awaiting further information from AEMO relating to focus groups related to this topic. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Discussions are continuing with impacted groups and information gathering to inform transition plans. |  | As above. Replanning is in progress for option 4. Waiting for OIC detail to finalise plans. | SAPN has registered and preparing for Phase 1 Industry testing. | Commenced planning to understand scope and magnitude of cutover. This activity is expected to require detailed planning and dedicated resources to manage. | Plans in place and resourcing agreed. Not yet due.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. |  | Industry approach has not been defined, therefore ability to meet schedule is unclear. | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | Transition planning has commenced. |  |  | In line with SAPN delivery schedule | Commenced data migration strategy and other preliminary planning activities. | Plans in place and resourcing agreed. Not yet due.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. | [6 empty] | TBC - subject to Vic Govt OIC detail.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is continuing final design and development activities based on information received to date. The degree to which re-work will be required due to changes in final AEMO documentation will be determined in the weeks immediately following release of said documentation. |  |  |  |  | Currently working through the B2B Procedure changes to understand impacts on detailed requirements, design and build. B2B configuration changes occurring in parallel to mitigate timeframe constraints. | Working closely with systems vendor to update plans aligned with Agile development approach. Additional resources assigned to assist with supporting program outcomes. | TBC - subject to Vic Govt OIC detail.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [7 empty] | Continued participation in Vic' Gov't Stakeholders Forum Active participation in assessment of options for Meter Type treatment. |  |  |  |  | TBC - subject to Vic Govt OIC detail. |  |  | UE has attended Vic Govt briefings and the AEMO-hosted PCF meeting 29 Mar, providing feedback about the implications of and uncertainty created by the deferral. UE continues to urge prompt drafting of the final decision (via Order-in-Council) in order to clarify the remaining items that are likely to impact scope and effort. UE has already indicated that it will not be in a position to provide meters that meet both Vic AMI and national specifications by 1 Dec.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | UE is assuming that DB-provided metering will remain a regulated service. It is also assumed that the current Victorian policy blocking customer opt-out will remain in place.
2.4 |  | An assessment of the required accreditation and registration activities | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | Seeking confirmation from Victorian Government on policy decision in relation to Type 5 or Type 4 meter classification for new meters. This is impacting the assessment of when UE will be ready to execute the accreditation process, and creates a risk of not being ready until just before the end-October deadline.
2.5 |  | The fulfilment of accreditation and registration obligations | [9 empty] | See above comment | [5 empty] | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [12 empty] | TBC - subject to Vic Govt OIC detail.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [12 empty] | TBC - subject to Vic Govt OIC detail.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery. | [6 empty] | TBC - subject to Vic Govt OIC detail.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [12 empty] | TBC - subject to Vic Govt OIC detail. |  |  | Business process designs have been amended based on deferral impacts. Internal approval of changes is nearing completion.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Requirement to provision additional resources to be assessed in order to deliver scope within timeframes. |  | See above comment | The Project is reviewing several mitigation strategies; significantly a phased implementation approach. | Prioritised development work associated with industry testing, to deliver early in the sprint releases. Working closely with vendor and business to ensure sprints are delivered on time. | TBC - subject to Vic Govt OIC detail. |  |  | Process designs have been revised for deferral impact and final approval is imminent. Solution designs are being progressively updated and should be finalised by mid-May.
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design tasks. | Communicated dependency on EVM via the SWG, awaiting confirmed delivery date from AEMO |  | See above comment | The Project has implemented a phased implementation approach. | Prioritised development work associated with industry testing, to deliver early in the sprint releases. Working closely with vendor and business to ensure sprints are delivered on time. | TBC - subject to Vic Govt OIC detail. |  |  | System development is progressing well based on revised designs, but remains behind original schedule due to deferral impacts. Schedule and resourcing have been revised to ensure readiness for market testing Aug 2017, but progress will need to be closely managed.
5.3 |  | The internal testing of market systems for your business | [11 empty] | Allocated additiona business resources to support Agile testing approach. SME's will work closely with vendor to begin testing as early in process as possible to minimise potential errors. | TBC - subject to Vic Govt OIC detail. |  |  | As above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [10 empty] | The handling of inflight transactions during cutover is a key risk. Our organisation continues to urge AEMO to provide a transform capability as usual to mitigate go live risk. |  | TBC - subject to Vic Govt OIC detail.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-05-08 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300 etc. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. | [13 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Amber status is maintained due to tight timeframes scope of change and project resourcing challenges. Key risk mitigation will be implemented for the duration of the project.
| Metering Dynamics | At risk | Medium | Project risk is due to the late release of procedures and the complexity of multiple Rule and role changes. Juridsdictional variations and lack of information on safety and technical rule changes is a major risk. Overall changes to organisation contributing to increased risk and resource contention. | [7 empty] | Meter Provider : Risk rating "low" Meter Data Provider: Risk rating "medium", Risk due to the complexity of changes needed.
| Select Solutions | Not within schedule | High | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs and procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is now well behind schedule. Contingency plans have been activated delaying procurement of a new system and focussing instead on ensuring availability and compliance of existing systems. | [7 empty] | Risk relates to the current status of new system implementation and existing systems modifications.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High | At risk | High
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 51% - 60% | 41% - 50% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 21% - 30% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 11% - 20% | 75% | 1% - 10%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 61% - 70% | 11% - 20% | 25% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 50% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 31% - 40% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 41% - 50% | 11% - 20% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 41% - 50% | 11% - 20% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 11% - 20% | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 41% - 50% | 31% - 40% | 75% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 41% - 50% | 21% - 30% | 50% | 1% - 10%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | 21% - 30% | 51% - 60% | 75% | 21% - 30%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 41% - 50% | 1% - 10% | 21% - 30% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 1% - 10% | 1% - 10% | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Not within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | At risk | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | At risk | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Risk is due to lack of time to prepare plans for compliance by testing and go live dates. | At risk due to system procurement program slippage so focus now on ensuring existing systems are compliant for 1 December 2017.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Continuing uncertainty and changes in jurisdictional rules is concerning at this late stage.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | Still waiting on jurisdictional regulators to review and update safety and technical requirements.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [8 empty] | Our internal commercial resources are not as well progressed as had been antcipated but are nonetheless progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Impacted by EQL merger and restructuring activity | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | Delays experienced due to change in key system component. | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [8 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Delays experienced due to change in key system component. | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Delays experienced due to change in key system component. | At risk due to system procurement program slippage.
5.3 |  | The internal testing of market systems for your business | [8 empty] | At risk due to system procurement program slippage.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | At risk due to system procurement program slippage.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | At risk due to system procurement program slippage.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | This action dependent upon finalisation of system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Additional resources requested | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Resource requests submitted. Awareness of blockers escalated to executive
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Update plan with required dates and allocate new resources.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Update plan with required dates and allocate resources.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Update plan with required dates and allocate resources. | Focus is now on making existing systems compliant for 1 December 2017.
5.3 |  | The internal testing of market systems for your business | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
| 2017-05-08 |  |  | Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | The element of risk is elevating with the delay and/or deferral of the following items: - Package 3 - as built : delayed with inclusive items which need urgent clarification rather than been incorporated in a 6mth consultation process. i.e. Meter Churn, CR6300 etc. - Clear communicated date of when the DB's treatment plan on how the Faults and Emergencies will be handled on site and subsequent Market communication of activities undertaken, will be available. | [13 empty] | Active Stream is currently accredited and operating as an Type 4 MDP and MPB/MPC. Systems and processes are currently in place, requiring AS to assess and deliver the delta to comply with the POC requirements. Our approach with the Progress and Traffic Light Status is related to POC specific amendments.
| Acumen Metering | At risk | Medium | Overall project delivery status at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Amber status is maintained due to tight timeframes scope of change and project resourcing challenges. Key risk mitigation will be implemented for the duration of the project.
| Metering Dynamics | At risk | Medium | Project risk is due to the late release of procedures and the complexity of multiple Rule and role changes. Juridsdictional variations and lack of information on safety and technical rule changes is a major risk. Overall changes to organisation contributing to increased risk and resource contention. | [7 empty] | New MC role integration into many market and business processes.
| Select Solutions | Not within schedule | High | The overall timeframes for these industry changes are tight. Select Solutions is working to a schedule set by relevant industry deadlines (ie industry testing, accreditation dates etc). Select Solutions overall strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs and procure a new system to form part of our accreditation for Type 4 small meters. Process impact and future process mapping is going well and we have a solid understanding of what is required to ring-fence from Ausnet services appropriately. IT system procurement is now well behind schedule. Contingency plans have been activated delaying procurement of a new system and focussing instead on ensuring availability and compliance of existing systems. | [7 empty] | Risk relates to the current status of new system implementation and existing systems modifications.
| VECTORAMS | Within schedule | Medium | Scope of change, tight timeframes, current uncertainty on outstanding matters such as lack of clarity on Emergency Procedures, Meter Churn rules, and transition at cutover leads to a Project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Metering Dynamics | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions | Not within schedule | High | Not within schedule | High | Not within schedule | High | Not within schedule | High | Not within schedule | High | Not within schedule | High
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 81% - 99% | 41% - 50% | 75% | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 51% - 60% | 41% - 50% | 75% | 61% - 70%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | 61% - 70% | 21% - 30% | 75% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 81% - 99% | 51% - 60% | 11% - 20% | 75% | 1% - 10%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 61% - 70% | 11% - 20% | 25% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 50% | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 1% - 10% | 31% - 40% | 25% | Not started (0%)
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 41% - 50% | 11% - 20% | 75% | 11% - 20%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 41% - 50% | 11% - 20% | 25% | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 11% - 20% | Not started (0%) | 50% | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 41% - 50% | 31% - 40% | 75% | 61% - 70%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 99% | 41% - 50% | 21% - 30% | 50% | 1% - 10%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | 21% - 30% | 51% - 60% | 75% | 21% - 30%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 41% - 50% | 1% - 10% | 21% - 30% | 25% | Not started (0%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | 1% - 10% | 1% - 10% | 0% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | At risk | Not within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Not within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | At risk | At risk | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | At risk | At risk | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | At risk | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Dependent on Faults/Meter Churn , timely resolution or provisioning of answers from AEMO. |  | Risk is due to lack of time to prepare plans for compliance by testing and go live dates. | At risk due to system procurement program slippage so focus now on ensuring existing systems are compliant for 1 December 2017.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Dependent on jurisdcitional determinations |  | Continuing uncertainty and changes in jurisdictional rules is concerning at this late stage.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Dependent on jurisdcitional determinations |  | Still waiting on jurisdictional regulators to review and update safety and technical requirements.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [8 empty] | Our internal commercial resources are not as well progressed as had been antcipated but are nonetheless progressing.
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Progressing through requirements for MC registration. Schedule challenged.
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | MC resource requirements have been determined |  |  | This has been done in 2 parts, the resource requirements to deliver the relevant projects and the ongoing resources required to deliver the services.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Resource assessment with respect to the MC role; MC org chart in draft. |  | Impacted by EQL merger and restructuring activity | Primary changes relate to resourcing around MC function. This work is being progressed but is currently behind schedule.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [8 empty] | Workshops are held internally to educate and prepare key staff for the required changes and impacts.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  |  | We've had 2 dedicated resources for over 6 months reviewing current processes and planning document changes for the process impacts relating to the PoC changes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Dependency Pkg 3 content and Faults/Emergencies. |  | Delays experienced due to change in key system component. | Still working with industry release dates to finalise these requirements as AEMO procedures are confirmed.
4.3 |  | The validation of business processes during industry testing | [8 empty] | At risk due to system procurement program slippage.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Delays experienced due to change in key system component. | A significant "blue print process" has been completed highlighting requirements. Still understanding B2B changes.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Delays experienced due to change in key system component. | At risk due to system procurement program slippage.
5.3 |  | The internal testing of market systems for your business | [8 empty] | At risk due to system procurement program slippage.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | At risk due to system procurement program slippage.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | At risk due to system procurement program slippage.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [8 empty] | This action dependent upon finalisation of system changes
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [8 empty] | This action dependent upon finalisation of system changes
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Metering Dynamics | Select Solutions | VECTORAMS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Additional resources requested | Dedicated resources and strong business focus on the systems delivery project.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [7 empty] | Resource requests submitted. Awareness of blockers escalated to executive
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Update plan with required dates and allocate new resources.
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [7 empty] | Update plan with required dates and allocate resources.
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | Update plan with required dates and allocate resources. | Focus is now on making existing systems compliant for 1 December 2017.
5.3 |  | The internal testing of market systems for your business | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Focus is now on making existing systems compliant for 1 December 2017.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
| 2017-05-08 |  |  | Embedded Networks Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Momentum Energy | Within schedule | Low
| Network Energy Services | Within schedule | Low | Preparing for Accreditation | [7 empty] | Getting prepared to implement all aspects
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 71% - 80% | 100%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 51% - 60% | 100%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 31% - 40% | 100%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Not started (0%) | 100%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 1% - 10% | 25%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 31% - 40% | 100%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 21% - 30% | 0%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 100%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Not started (0%) | 100%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 1% - 10% | 50%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 1% - 10% | 100%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Not started (0%) | 100%
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | 0%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 41% - 50% | 75%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 1% - 10% | 50%
5.3 |  | The internal testing of market systems for your business | [5 empty] | Not started (0%) | 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 0%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 0%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Not started (0%) | 75%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 25%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | System development is reliant on external vendor, delays in final market procedures will impact readiness activities
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Momentum Energy | Network Energy Services | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-05-08 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 99%
Completed (100%)
N/A
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-05-08 | [5 empty] | Within schedule | Medium | The Vic Got OIC, expected in Mid Ma,y will indicate if any Procedure Changes are required. The Vic Govt. has decided to classify Victorian smart meters as type 5, removing a level of uncertainty. Industry Testing and the Transition and Cut-Over planning is progressing, with the Industry Test Strategy nearing completion and the newly established Industry Transition and Focus Group commencing meeting. The B2B e-hub accreditation process has been published and AEMO held a Participant Information Session to walkthrough the process.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 21% - 30% | Within schedule | Final v1.0 of the POC Industry Accreditation and Registration Plan and the POC Industry Test Strategy released. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | Information paper on workpackage 3 consultation released 12 May. These procedures are expected to be finalised in November 2017. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 81% - 99% | Within schedule | For the B2B procedures, the IEC has decided only to amend the procedures for manifest errors, which does not require formal consultation |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 11% - 20% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | 81% - 99% | Within schedule | Participant information sesion on B2B e-hub accreditation held on 9 May. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | Within schedule | New Tarfiff change request underway. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 99% | Within schedule | New Tarfiff change request underway. |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 11% - 20% | Within schedule | EN/MC Testing on track to commence 23 May - detailed planning ongoing |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 1% - 10% | Within schedule | First Industry Transition and Cutover Focus Group meeting held on 10 May, project plan in place to deliver Industry plans |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 99% | Metering Coordinator
[12 empty] | Completed (100%) | Embedded Network Manager
[12 empty] | N/A | Embedded Network Operator
Third Party B2B Participant
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%