## Market Readiness Report Page 1
42989
AEMO Power of Choice Implementation Program
|  | Monthly Readiness Report | 2017-09-11
Overall Status |  | Commentary |  |  | Risk Rating |  | # Open Risks - Rating: |  |  | Issues:
|  | The overall project status remains amber - "at risk" of delivery by 1 December 2017 - primarily due to challenging program timeframes. Participants have highlighted challenging timeframes for system build and testing, registration and accreditation activities, and the number and complexity of commercial arrangements to be entered into. The overall project risk rating remains medium - with highlighted risk areas including the readiness of other participants, in particular Metering Coordinators. The POC Executive Forum voted in favour of industry adopting a staged transition approach to reduce overall risk, industry are currently scoping this approach. |  |  |  |  | High | Med | Low | #
[7 empty] | 6 | 5 | 2 | 0
AEMO and NEM Participants Readiness Criteria |  |  | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
# | Category | Criterion | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note | Status | Note
1. Assessment and preparation
1.1 | Assessment and preparation | Consequences of the POC reforms for your business considered, and appropriate implementation plans are in place |  |  |  | #1
1.2 |  | Key readiness planning documents delivered
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | Updated retail electricity market procedures and associated documents published
2.2 |  | Internal policies updated for consistency with regulatory changes including jurisdictional regulations and requirements (e.g. safety) |  |  |  | #2
2.3 |  | Operationally critical commercial contracts in place |  |  |  | #3 |  |  |  | #3 |  | #3
2.4 |  | Accreditation and registration activities completed |  |  |  | #4
3. People
3.1 | People | Operational roles specified, assigned to staff, and training delivered |  |  |  | #5
4. Business processes
4.1 | Business processes | Updated, validated and approved business processes in place |  |  |  | #6 | [7 empty] | #6
4.2 |  | Successfully validated critical business processes during industry testing |  |  |  | #8 | [7 empty] | #8
4.3 |  | Process work‑arounds in place for any issues identified during industry testing
5. Market systems
5.1 | Market systems | Delivery of the re-developed B2B e-hub for industry testing
5.2 |  | Successfully tested market systems capable of being moved into production |  |  |  | #7 |  | #7 | [5 empty] | #7
5.3 |  | Performance of, and communication between, market systems validated during industry testing |  |  |  | #8 |  | #8 | [5 empty] | #8
6. Transition planning
6.1 | Transition planning | Transition and cutover plan(s) in place |  |  |  | #9 |  | #9
6.2 |  | Prerequisite transition and cutover processes completed (e.g. trial data conversions and cutover dress rehearsals)
Jurisdictional Status
Jurisdiction |  | Comments | AEMO |  | Retailers |  | Distributors |  | MP and MDP |  | Metering Coordinator |  | Embedded Network Manager |  | Third party e-hub
|  |  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
ACT |  | Jurisdictional risk is a reflection of overall project risk.
NSW |  | Jurisdictional risk is a reflection of overall project risk.
QLD |  | Jurisdictional risk is a reflection of overall project risk.
SA |  | Jurisdictional risk is a reflection of overall project risk.
TAS |  | Jurisdictional risk is a reflection of overall project risk.
VIC |  | Jurisdictional risk is a reflection of overall project risk.

## HIDDEN 25% (hidden)
ü
| 100 | 75 | 50 | 25 | 0
| 0 | 25 | 50 | 75 | 100
WITHIN SCHEDULE | [5 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE

## Market Readiness Report Page 2
AEMO Power of Choice Implementation Program
Monthly Readiness Report
2017-09-11
Variances
Note # | Explanation of Variance |  |  | Mitigating Actions
1 | Variance reported by Participants: Development of detailed Implementation plans on schedule at risk as participants have identified a need to iterate plans for differing implementation approaches. The staged transition approach adds additional tasks. |  |  | Retailers and DNSPs are meeting to align processes.
2 | Variance reported by Participants: Updating internal policies on schedule at risk as participants are waiting for jurisdictional safety regulators to publish requirements (re-en and de-en) and for clarity on the ENM role in Victoria and Queensland. Participants are also waiting for the final Vic government OIC . |  |  | Participants are engaging with jurisdictional bodies.
3 | Variance reported by Participants: Updating commercial arrangements on schedule is at risk due to volume and complexity of contracts that need to be entered into with industry parties. The slow progress of MC registration has also been raised as a risk. |  |  | Participants are increasing internal resources and considering contingency options (such as the staged transition approach).
4 | Variance reported by Participants: Fulfilling registration and accreditation activities on schedule is at risk due compressed timeframes for all registration and accreditation activities. |  |  | Participants are increasing internal resources and progressing registration and accreditation activities.
5 | Variance reported by Participants: Availability of business subject matter experts and conflicts with project resources contributing to risks associated with resourcing and training. |  |  | Participants are re-allocating resources to cover training.
6 | Variance reported by Participants: Progress impacted by uncertainty in a number of areas including meter churn, faults and emergencies, jurisdictional requirements. Progress has been impacted by the Victorian Government deferral decision. |  |  | Participants are increasing internal resources, holding discussions with other participants, reviewing meter churn impacts under Package 3 and awaiting the final Victorian govt. OIC.
7 | Variance reported by Participants: System development at risk due to the complexity and number of changes required within tight timeframes for development and testing and delays from external market system vendors. |  |  | Participants are increasing internal resources and working closely with market system vendors.
8 | Variance reported by Participants: Testing timelines are contingent on system design and build and are compressed. Concerns with scope of testing and lack of readiness and/or participation by other participants also reported as risk areas. |  |  | [Market Trial cycle 1 completed on 8/9, with 21 companies and 49 participant IDs involved, 96.4% execution was achieved. 33 defects were raised, with 5 yet to be closed. 3 of these are AEMO defects - scheduled to fixed before cycle 2 commencement (18/9) ]
9 | Variance reported by Participants: Transition and Cutover planning dependent on new connection processes, readiness of competitive MCs. Cutover plan for existing embedded networks yet to be developed. The proposed transitional approach requires scoping and approval before planning can commence. |  |  | Participants are engaging with the ITCFG. [http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Power-of-Choice/Readiness-Work-Stream/Industry-Transition-Cutover-Focus-Group]
Notes
1. Please refer to the POC Industry Readiness Reporting Plan for more details on the Readiness Report process: http://www.aemo.com.au/-/media/Files/Electricity/NEM/Power-of-Choice/B2B/AEMO-POC-Industry-Readiness-Reporting-Plan-v20.pdf 2. The count of open Risk and Issues is based on the POC Industry Risk Register as at 17/08/2017. 3. Explanation of Variance and Mitigating Actions above are based on Participants comments, AEMO's comments are included within square brackets [ ].
Key - Progress and Status | [5 empty] | Key - Risk Rating
Progress |  |  | Status
Harvey balls represent progress towards achieving the criterion |  |  | Colour indicates the readiness status |  |  | Rating
~0% |  | ~50% | Criterion is within agreed schedule and deliverable requirements |  |  | High
~10% |  | ~60% | Criterion is at risk of not meeting requirements and corrective action may be required |  |  | Medium
~20% |  | ~70% | Criterion not meeting requirements. Immediate corrective action required |  |  | Low
~30% |  | ~80% |  |  |  | See POC Industry Risk Register for open risks and issues:
~40% |  | ~90% | Criterion has been achieved |  | ü | POC Industry Register

## Retailer Reports
| 2017-09-11 |  |  | Retailer Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Retail | Within schedule | Medium | ActewAGL Retail is currently focused on UAT/Regression Testing, Industry test and Operational readiness.A detailed project plan is in place and being tracked against in order to achieve compliance by the "go live" date.
| AGL Retailer Powerdirect | At risk | Medium | Phase 1 industry testing completed sucessfully. Commercial activities are still in progress. All core developments complete. Operational impact assessment complete. Training planning underway. Release plan developed. Performance test planning underway. Focus now on process lock down and issue resolution plus MC mobilisation. Project status remains yellow due to key risks relating to commercial agreements and now MC mobilisation activities in readiness for go-live. | [7 empty] | Risk rating remains at medium due to the number of parties involved, limited testing timeframes, significant commercial agreements that must be implemented and business transition and readiness activities.
| Alinta Energy | Within schedule | Medium | Over all the project is still progressing to plan. Metering Partner engagement behind schedule Still working to finalise PoC Business Processes, however dependency on engagement of metering partners. Working with Agility to develop the cutover plan | [7 empty] | Retailing in the Queensland Market
| Aurora Energy | At risk | Medium | Aurora Energy continues to manage a number of risks with regards to the implementation of the Power of Choice reforms by 1 December 2017. The most significant risk is the aggressive implementation timeline, reflected in Aurora Energy's 'at risk' project status. This risk is also impacting the ability of Aurora Energy's key vendors to meet POC timeframes. This includes, but is not limited to, a prospective Metering Coordinator, which will be required to establish advanced metering service capability in Tasmania where it currently does not exist.
| Energy Locals | At risk | High | [AEMO Note - Using 7 Aug 17 Report for Energy Locals]: The comments below and those in our PWC survey response and interview demonstrate the limited resource we can put into POC as a startup. This is made especially difficult when the customer benefits of POC are not apparent (beyond what we already do for customers). There is huge uncertainty across the industry - will it take place on 1 Dec or won't it. That uncertainty in itself is expensive and is losing us time. We need AEMO to either light the fuse or put the matches away by the end of August to stand a chance of hitting 1 December.
| Energy Australia | At risk | Medium | We see significant risks associated with: the lack of alignment on implementation approaches among participants; tightness of industry testing schedule; and the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. | [7 empty] | The Program is making steady progress but has risks associated with the progress of industry coordinated activities, such as industry-wide readiness, BCP and Emergency Planning. The Vic decision to delay competition in metering has had a significant impact on implementation of B2B processes, while these have been largely resolved, there are residual impacts to the schedule. | [5 empty] | Risks associated with industry coordinated activities still exist, such as BCP, Communications Planning and Emergency Planning.
| Ergon Energy Queensland (retail) | At risk | Medium | Ergon Energy continues to manage a number of system, process and people risks to deliver to the aggressive timeframe of the 1 December 2017. From a system perceptive, clarity is required on the overall readiness assessment of AEMO and the market. In particular where many participants are showing amber/red, recent industry testing defects and uncertainty around accreditation of participants throughout the market. Work is underway to mitigate EEQ's risks associated with vendor, key stakeholders and other important interfaces to ensure business continuity and customers are not impacted in a negative way. Transitions Planning and revised Business Continuity Plan (BCP) has added additional requirement to the Project to mitigate risk that may add additional resources and costs. Deployment Planning and associated in-flight transitions approach is being developed but could add additional risk to cut-over due to the tight timeframe. Change management is being reassessed and an increased focus to ensure business readiness. | [7 empty] | Ergon Energy continues to manage a number of system, process and people risks to deliver to the aggressive timeframe of the 1 December 2017. From a system perceptive, clarity is required on the overall readiness assessment of AEMO and the market. In particular where many participants are showing amber/red, recent industry testing defects and uncertainty around accreditation of participants throughout the market. Work is underway to mitigate EEQ's risks associated with vendor, key stakeholders and other important interfaces to ensure business continuity and customers are not impacted in a negative way. Transitions Planning and revised Business Continuity Plan (BCP) has added additional requirement to the Project to mitigate risk that may add additional resources and costs. Deployment Planning and associated in-flight transitions approach is being developed but could add additional risk to cut-over due to the tight timeframe. Change management is being reassessed and an increased focus to ensure business readiness.
| ERM Power Retail | At risk | Medium | ERM continues to report at risk for the PoC project, primarily due to remaining uncertainty in areas including 1) Meter Churn processes 2) Impact of these on commercial agreements Many previous uncertainties have been resolved, reducing (but not eliminating) risk.
| M2 Energy Pty Ltd | Within schedule | Medium | Project Scoping by Vendor is complete, and coding has commenced.. Vic related changes are a substantial risk. Business intention is to fully outsource MC role. Risk considered Medium as few vendors currently available for selection and none are accredited. M2 Energy is maintaining dialogue with potential vendors. | [7 empty] | Vic withdrawl from POC has introduced risk into System Scoping, and increased training and change management requirements.
| Macquarie Bank Limited | Within schedule | Low
| Mojo Power | Within schedule | Medium | [8 empty] | [VIC comment]: Mojo in application for licence to enter Victoria.
| Momentum Energy | At risk | Medium | Material risks are related to probable issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes and merge codes for B2B and B2M market transactions. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Next Business Energy | Within schedule | Low | NBE is tracking well with internal processes almost complete for post POC implementation. NBE also intends to adopt the staged approach to POC implementation to mitigate risk associated with delays in receiving, reviewing and implementing MC contracts.
| Origin Energy | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If safety regulations in each state (incl. ACT) does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity. | [7 empty] | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. | [5 empty] | Areas of concern include: Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines. Program is currently reporting Amber however remains highly dependant on the readiness of other participants to be successful and 9 out of 11 Distributors reporting at risk. A high number of delivery risks continue to be monitored and mitigated for the duration of the project. Areas of concern include: Delivery • Uncertainty around the details of the VIC derogation extension may delay the delivery of the program (Origin has expressed concerns over proposed deviation from the overall B2B procedures); • Industry Faults and Emergencies process is still not defined (i.e.: R&R for Networks x Retailers x MPs and the comms method and hours of operations); • Meter type 4A E2E process not defined in the Industry - risk of inconsistent processes across participants is high; • Bulk Data conversion for Standing Data (MC/ENM role, Meter Type, NMI/Meter Register Status) across industry participants is still unclear and therefore impacting our planning and implementation of activities; participants updating own data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover; • Awaiting delivery from AEMO of a completed Testing Plan inc. Test Data requirements for Market Trial Testing . If a Production Test Data cut is not agreed and published in the next few weeks, the Testing activities of the program will be impacted. Additionally, Origin believes that Phase 3 Market Testing should be seen as a mandatory PoC milestone for all participants to ensure industry readiness is tested / verified. • If QLD safety regulation does not allow MPs to energise a site, then New Connections timeframes will prolong by several days with risk of additional cost to customers. • Industry focus on compliance with the new obligations and lack of progress at jurisdictional level for supporting regulation changes, such as safety cases, right to entry etc. may result in poor customer experience. Cutover • Time frame for cutover is not practicable: Thursday night (30th Nov) / Friday morning (1st Dec) - I.e. significant disruption to BAU batch processes and Call centres operations is expected (i.e. we require approx. 20 hours for Cutover and Only 12 hours are available (assuming we shut down systems at 6pm and return to BAU at 6am) • Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, storm season, etc.). Transition & Cutover planning must take this into account; • In-flight Transactions approach are still being developed and may lead to customer impacts & additional costs. The schema change may necessitate a cancel re-raise for open service orders; • There is no Back-out scenario for this implementation given this is an integrated delivery backed by change in legislation. The risk profile is extremely high given statuses of various participants; • AEMO needs to report on the overall readiness assessment. AEMO overall status shows Amber when virtually all participants are showing Amber / Red. This seems to suggest the aggregated risks may not be fully understood. Comms • Communications plan to affected parties (i.e. Electricians, Customers) is still not finalised; expectation that AEMO will lead on this activity.
| Pacific Hydro / Tango | At risk | High | The timing and outcomes of the following outstanding PoC activities have the potential to impact the build, test and implementation phases: 1. MSATS - As Built Consultation 2. B2B - Translation tool delivery and client side implementation & testing; potential new B2B schema changes prior to 1 Dec, and any Errata requiring process workarounds 3. Meter Churn Issues - recently raised and despite a paper being issued by AEMO, there are still concerns being raised. 4. Vic Government decision not to proceed with PoC. 5. Jurisdictional safety review of the remote Re-en/De-en process. 6. Internal Project delay for replacing current systems.
| People Energy Pty Ltd | At risk | Medium | Overall project delivery deadline at risk, due to constrained timelines for delivery against overall AEMO Delivery Timelines.
| Pooled Energy | Within schedule | Medium | Project status remains within schedule. Continuing to work through procedural and process changes. Project risk rating remains at medium. Pooled Energy is reviewing a number of related commercial agreemnets and progress is dependent on external providers meeting timelines. | [7 empty] | As above - Pooled Energy operates in NSW only currently.
| Powershop | Within schedule | Medium | Powershop's development team is currently building the functionality to support POC
| Red Energy & Lumo Energy | At risk | High | Business and customer activity is very high at the targeted cut-over time. Inconsistent approaches across industry creates increased activity and raises risk (eg. new connections, meter churn, faults and emergencies, expected approaches to in-flight transactions). Victorian approach is understood but the detail and specifics is not yet finalised (Order in Council drafted but final version not released) Other jurisdictional consequential legislative amendments are not yet understood (and unseen) which is adding further risks to the overall project. Continued discussion at the industry forums regarding participants not being ready in various forms is reducing our confidence in a positive customer experience in the move to metering competition. This is also highlighted in AEMO's assessment of the overall project having a high risk rating. The lack of clarity regarding what will be done to change the risk rating at the industry level is amplifying the risk. | [7 empty] | [VIC comment]: Lack of clarity regarding final OIC and nuances between approaches for each DNSP in Vic to standard processes has changed our Risk rating for Victoria. Draft OIC has initial MC contracts being available on 15 October rather than 1 September, further adding to uncertainty and risk
| Simply Energy | Within schedule | Low | [14 empty] | Simply Energy has commenced Market Trial and is on track as per the schedule with no major defects identified in cycle 1 of Phase 3.
| Stanwell Corporation Limited | Within schedule | Low | Project progressing as planned.
| Sumo Power | Within schedule | Medium | [8 empty] | Readiness of market participants
| WINConnect Pty LTD | At risk | Medium
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Retail | Within schedule | Medium | Within schedule | Medium
| AGL Retailer Powerdirect | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Alinta Energy |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Aurora Energy | [8 empty] | At risk | Medium
| Energy Locals |  |  | At risk | Medium | At risk | Medium
| Energy Australia | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ergon Energy Queensland (retail) |  |  |  |  | At risk | Medium
| ERM Power Retail | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| M2 Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Macquarie Bank Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Mojo Power |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Momentum Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Next Business Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Origin Energy | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Pacific Hydro / Tango |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| People Energy Pty Ltd |  |  | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Pooled Energy |  |  | Within schedule | Medium
| Powershop |  |  | Within schedule | Medium | Within schedule | Medium |  |  |  |  | Within schedule | Medium
| Red Energy & Lumo Energy |  |  | At risk | High | At risk | High | At risk | High |  |  | At risk | High
| Simply Energy | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Stanwell Corporation Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  |  |  | Within schedule | Low
| Sumo Power | [10 empty] | Within schedule | Medium
| WINConnect Pty LTD |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Locals | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINConnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 51% - 60% | 81% - 99% | Completed (100%) | Completed (100%) | 75% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%) | 81% - 99% | Completed (100%) | 61% - 70% | 71% - 80% | 100% | 61% - 70% | 81% - 99% | Completed (100%) | 71% - 80% | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed (100%) | Completed (100%) | Completed (100%) | 61% - 70% | 11% - 20% | 81% - 99% | 71% - 80% | 51% - 60% | 50% | 91% - 99% | 51% - 60% | 71% - 80% | 61% - 70% | 61% - 70% | 51% - 60% | 51% - 60% | 41% - 50% | 0% | 31% - 40% | 81% - 99% | 81% - 99% | 61% - 70% | 71% - 80%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | Completed (100%) | 91% - 99% | 71% - 80% | 1% - 10% | 71% - 80% | 71% - 80% | 51% - 60% | 25% | 81% - 90% | 71% - 80% | 71% - 80% | 51% - 60% | 61% - 70% | 51% - 60% | 41% - 50% | 41% - 50% | 75% | 81% - 99% | 41% - 50% | 71% - 80% | 21% - 30% | 41% - 50%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | 61% - 70% | 81% - 90% | 31% - 40% | Not started (0%) | 51% - 60% | 61% - 70% | 41% - 50% | 0% | 81% - 90% | 61% - 70% | 41% - 50% | 61% - 70% | 41% - 50% | 31% - 40% | 21% - 30% | 21% - 30% | 0% | Not started (0%) | 31% - 40% | 21% - 30% | Not started (0%) | 11% - 20%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 21% - 30% | 61% - 70% | 61% - 70% | 41% - 50% | 31% - 40% | 61% - 70% | 71% - 80% | 41% - 50% | 0% | 21% - 30% | 71% - 80% | 41% - 50% | 11% - 20% | 21% - 30% | 51% - 60% | 21% - 30% | 11% - 20% | 25% |  | 51% - 60% | 11% - 20% | 11% - 20% | 41% - 50%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 81% - 99% | Completed (100%) | Completed (100%) | 31% - 40% | 51% - 60% | 71% - 80% | 51% - 60% | 71% - 80% | 25% | 91% - 99% | 81% - 99% | 71% - 80% | 41% - 50% | 61% - 70% | 51% - 60% | 41% - 50% | 61% - 70% | 50% |  | Completed (100%) | Completed (100%) | Not started (0%) | 71% - 80%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 81% - 99% | 61% - 70% | 11% - 20% | 1% - 10% | 51% - 60% | 21% - 30% | 71% - 80% | 11% - 20% | N/A | 91% - 99% | 11% - 20% | 61% - 70% | Not started (0%) | Not started (0%) | 1% - 10% | 11% - 20% | 11% - 20% | 0% |  | N/A | 41% - 50% | Not started (0%) | 71% - 80%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 99% | 71% - 80% | 51% - 60% | 61% - 70% | 31% - 40% | 71% - 80% | 81% - 99% | 61% - 70% | 50% | N/A | Completed (100%) | 61% - 70% | Completed (100%) | 51% - 60% | 51% - 60% | 31% - 40% | 61% - 70% | 25% |  | 51% - 60% | 41% - 50% | Completed (100%) | 71% - 80%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 11% - 20% | 31% - 40% | 61% - 70% | 61% - 70% | N/A | 41% - 50% | 51% - 60% | 51% - 60% | N/A | N/A | Completed (100%) | 61% - 70% | 81% - 90% | 31% - 40% | 51% - 60% | Not started (0%) | 61% - 70% | N/A |  | Not started (0%) | 41% - 50% | N/A | Completed (100%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Not started (0%) | 1% - 10% | Not started (0%) | 11% - 20% | Not started (0%) | 21% - 30% | 41% - 50% | 51% - 60% | 25% | Not started (0%) | 41% - 50% | 41% - 50% | 31% - 40% | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% |  | 31% - 40% | 11% - 20% | Not started (0%) | Completed (100%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | 71% - 80% | 71% - 80% | 21% - 30% | 71% - 80% | 81% - 99% | 41% - 50% | 25% | 81% - 90% | 61% - 70% | 41% - 50% | Completed (100%) | 71% - 80% | 71% - 80% | 41% - 50% | 51% - 60% | 75% | 71% - 80% | 71% - 80% | 61% - 70% | 61% - 70% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed (100%) | 61% - 70% | 41% - 50% | 31% - 40% | Not started (0%) | 71% - 80% | 71% - 80% | 41% - 50% | 25% | 81% - 90% | 41% - 50% | 41% - 50% | 71% - 80% | 41% - 50% | 21% - 30% | 21% - 30% | 21% - 30% | 25% | 61% - 70% | 41% - 50% | 1% - 10% | 31% - 40% | 51% - 60%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 21% - 30% | 31% - 40% | 11% - 20% | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | Not started (0%) | 0% | N/A | 1% - 10% | 31% - 40% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | 41% - 50% | Not started (0%) |  | Completed (100%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 81% - 90% | 91% - 99% | 71% - 80% | 11% - 20% | 81% - 99% | 81% - 99% | 51% - 60% | 75% | 81% - 90% | 41% - 50% | 61% - 70% | Completed (100%) | 71% - 80% | 81% - 90% | 61% - 70% | 71% - 80% | 75% | 71% - 80% | 71% - 80% | 81% - 99% | 71% - 80% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 61% - 70% | 81% - 90% | 91% - 99% | 71% - 80% | 11% - 20% | 61% - 70% | 81% - 99% | 41% - 50% | 75% | 61% - 70% | 41% - 50% | 51% - 60% | 71% - 80% | 51% - 60% | 41% - 50% | 41% - 50% | 61% - 70% | 50% | 51% - 60% | 61% - 70% | 71% - 80% | 61% - 70% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 61% - 70% | 71% - 80% | 51% - 60% | 41% - 50% | 1% - 10% | 31% - 40% | 51% - 60% | 31% - 40% | 0% | 61% - 70% | 1% - 10% | 61% - 70% | Not started (0%) | 21% - 30% | 1% - 10% | Not started (0%) | 51% - 60% | 0% | 21% - 30% | 71% - 80% | 61% - 70% | 51% - 60% | Not started (0%)
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed (100%) | 51% - 60% | 51% - 60% | 11% - 20% | 1% - 10% | 21% - 30% | 31% - 40% | 21% - 30% | 0% | Not started (0%) | 1% - 10% | 61% - 70% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | Not started (0%) | 31% - 40% | 81% - 99% | 11% - 20% | Not started (0%)
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 51% - 60% | 11% - 20% | 11% - 20% | 1% - 10% | 1% - 10% | 11% - 20% | 31% - 40% | Not started (0%) | 0% | Not started (0%) | 1% - 10% | 51% - 60% | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | Not started (0%) | 41% - 50% | Not started (0%) | 11% - 20% | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 31% - 40% | 61% - 70% | 21% - 30% | 31% - 40% | 1% - 10% | 31% - 40% | 11% - 20% | 31% - 40% | 25% | 71% - 80% | Not started (0%) | 31% - 40% | 41% - 50% | 21% - 30% | 31% - 40% | 1% - 10% | 41% - 50% | 0% | 21% - 30% | 21% - 30% | Not started (0%) | 61% - 70% | Not started (0%)
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 31% - 40% | 11% - 20% | Not started (0%) | 1% - 10% | 21% - 30% | Not started (0%) | Not started (0%) | 11% - 20% | 0% | Not started (0%) | Not started (0%) | 1% - 10% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | 0% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Locals | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINConnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Completed | Completed | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Completed | Completed | Completed | At risk | Not within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Completed | Within schedule | At risk | Not within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | At risk | Not within schedule | At risk | At risk | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | At risk | Within schedule | Within schedule | N/A | At risk | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | N/A | N/A | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | N/A | N/A | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule | N/A | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | At risk | Within schedule | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | At risk | Within schedule | At risk | At risk | Not within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Completed | Within schedule | At risk | At risk | Not within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Not within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Not within schedule | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | Not within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule |  | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk | Within schedule | Within schedule | Within schedule | At risk
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | At risk | At risk | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | N/A | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Locals | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINConnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | High level impact assessment has been conducted. |  |  | A high-level assessment of necessary business operational process and systems changes is near 100% completion noting the detailed assessment supporting the high-level view is still incomplete. | As a startup we need to terminate some of our staff to pay for POC. We're unwilling to do this until AEMO commits 100% to the December go live date. | Due to differing implementation approaches of participants, Reassessment of customer impacts is required at a DNSP level. | [6 empty] | n/a | Impact Assessment completed, but will need to be iterated pending consultation outcomes and changes. Procedure and meter type implication due to VIC derogation extension are not yet clear. Faults and Emergencies process not yet finalised | [7 empty] | Less of an impact given geographic location being operated in is currently limited to Victoria
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Program established, detailed plan in place and being tracked against. |  |  | Detailed requirements have been gathered and vendors engaged to deliver the changes to market messaging. Additional changes to enable all other core operations post 1 December 2017 are being assessed. The aggressive timelines for systems build and testing, combined with contracting and establishment of an MC and the required implementation and testing combined systems is the basis of the 'at risk' status. | As above | Re-development of DB specific implementation plans is required, due to variations in participant implementation approaches. | As a retailer, EEQ is heavily reliant on contracted parties being ready from go-live date. | [5 empty] | n/a |  | At risk due to process and system delays. | [6 empty] | Clarification received on handling in flight transactions across the cutover weekend.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [8 empty] | A detailed assessment of the revised legal and regulatory is significantly developed. In its current form the detailed assessment has provided the basis of Aurora Energy preparedness to date. The assessment continues to be informed by on-going AEMO market procedure consultation although remaining uncertainty over rule and procedure operations ensures this is still considered 'at risk'. Onboarding steps with Aurora Energy's prospective Metering Coordinator are further informing the detailed assessment. | As above |  | Queensland jurisdictional safety requirements in relation to remote re-energiation are yet to be addressed. |  | scheduled and commenced. |  |  | Retailer timeframes to assess and agree to the T&Cs of the LNSPs are extremely tight and require the same pool of resources needed for establishing contractual agreements with Metering Coordinators and Embedded Network Owners | n/a | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines | Jurisdictional requirements for safety in relation to remote re-en/de-en in non-Vic jurisdictions unconfirmed. |  |  |  | Await final Victoria Order in Council and jurisdictional amendments to safety regulations and assessment of any potential changes required | Awaiting jurisdictional safety regulators to publish requirements
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [8 empty] | Aurora Energy has considered the wider and indirect regulatory implications of metering competition on business-as-usual activities (particularly given the existing regulatory framework was developed in the context of type 6 metering). | Requires items above to be completed first | Schedule risks associated with the magnitude & complexity of the change | Jurisdictional changes to Meterology Part A are underway but not yet complete |  | not yet scheduled. |  |  | Severe challenges with the level of effort required to translate system and process changes into business operational readiness | n/a | Policy changes/decisions still being derived | Vic Government decision on PoC and timing of regulatory changes to reflect the decision not to proceed with PoC. Potential variance of process by QLD DNSP not accepting Service Orders from an MC. |  |  |  | Awaiting jurisdictional regulatory confirmation and update
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Awaiting executable MC contracts to be issued by the relevant parties. | Contract dlivery is now behind revised schedule. | . Negotiating with MCs . Retail and C&I Contracts reviewed and updated . Customer collateral drafted | Activity has commenced for customers and vendors as part of POC implementation. The major challenge is to develop and execute contractual arrangements with a Metering Coordinator, which will have to establish metering service capability in Tasmania where it currently does not exist. | We've signed one contract with a MP/MDP and that provider has also added the MC role at our request. 3 others are at contract stage. | Scheduled activities at risk due to complexities of numerous participants | Substantial agreement on terms achieved, work ongoing to resolve outstanding items - forecast to be complete 15/9/17 | The number of contracts and counter-parties put this item at risk. | in progress |  |  | Dependency on partnering with registered MC(s) | As at September 2017, NBE is still waiting to receive and review contractual arrangements with MCs (one one contrac thas been recieved, other than intital MCs, being relevant LNSPs). This places signifiant risk to the business with short timeframes to review and negotiate contracts before 1 December 2017. | Overall strategy has been developed and endorsed. Generic Meter provider contract drafted for new providers and contracts in play for current providers. | Requirements/services for various Service Providers yet to be finalised. Discussions with various Service Providers are in progress. MCs shortlisted and offerings currenlty under review. |  | Dependent on external provisers commercial agreements | Negotiations have commenced | Internal management of this item | Most of the potential Metering Coordinators default MC Ts and Cs are still not available to the market.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Accreditation results have been submitted to AEMO. |  | Contracts to reflect Accreditiation requirements Retail accreditiation via testing | Aurora Energy will be required to receive accreditation for using the B2B e-hub. The newly published B2B E-Hub Accreditation and Revocation process is currently being considered. The timeline and uncertainty for accreditation and registration activities of other participants (specifically, the Metering Coordinator role) also impacts on Aurora Energy's planning. Dialogue with the jurisdictional safety regulator has commenced. | Confirmed that accreditation is only require for MC, MP, MDP and no other retailer requirements. Application has been submitted to AEMO |  | Industry testing now underway |  |  |  |  | Submission has been followed by initial response from AEMO and Momentum is working consistently towards resolving the highlighted gaps. | n/a | Underway for new Market Roles | Despite 5.2, B2B accreditation is still required and for that purpose we still believe we will be in a position to complete in the required timeframe. |  |  |  | Internal management of this item
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Accreditation results have been submitted to AEMO. |  | Accreditiation via testing | Fulfilment of the accreditation obligations is now being considered following AEMO publishing final version of the 'B2B Accreditation and Revocation Process'. | As above | eHub application submitted, industry testing commenced | Minimal requirements for a retailer. |  |  |  |  | Volume of information required following initial assessment is higher than expected | Scheduled for later in 2017. | Planning and preparation in progress | Per 5.2 and the limited timeframes for internal testing and commencement of Market Trial. |  |  |  | Internal management of this item
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Detailed assessment completed. |  |  | This has commenced and will be finalised following with the detailed assessment of operational and systems changes. | Assessments to date show no additional ongoing resource, which is good because we'd need to busk outside Richmond station to pay for them. | Re-confirming resourcing for operational functions | FTE impact analysis complete |  | No resource changes at this time |  |  |  | Procurement of additional resources underway. | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. Forecasted workload planning completed for key business areas and socialised to inform recruitment decisions. | Internal replanning drafted with resourcing requirements identified. |  |  |  | Internal management of this item |  |  | No additional staff operational required
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | The recruitment of specialist human resources to cater for the rule change is progressing as the need to fill key project roles arises. A key challenge is the availability of internal business subject matter experts to assist in change management. Further, total program resources represent a significant portion of Aurora Energy's total staff resource pool, which instensifies resourcing risk. | N/A depending on 3.1 | Recruitment activity dependent upon FTE revalidation | Transition Support Team requirement analysis complete, pending approval to recruit. | [5 empty] | Procurement of additional resources underway. | Policy changes/decisions identified. Recruitment for long lead time positions commenced. |  |  |  |  | Internal management of this item
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Scheduled to commence in the next period. |  |  | Training requirements are currently being assessed as part of the business process, change management and system planning. | Depends on section 1 | Training development at risk due to delay in delivery of key processes | Curriculum completed, preparation of training material underway with delays. Staff training scheduled for Oct-Nov |  | Waiting on testing environment to be released, staff have been briefed and aware of industry change |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing | Subject to completion of procurement activity. | Training requirements and resourcing determined and magnitude of change is understood, change planning started. Learning curriculum being finalised and training material development commenced. Confirmation of some market transactions and treatments still pending which may impact training timelines given constraints in place. | At risk due to 5.2/4.1. |  |  |  | Internal management of this item
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Awaiting advice on Remote Re-Energisation/De-Energisation. Lack of information or engagement from jurisdictional safety regulators. |  |  | All impacted service order, B2B & B2M and business processes have been identified. Assessment of current and future processes is underway to enable gap analysis and identify process and system changes. Possible future changes puts the delivery scope and timeline at risk. | Undertaken high level assessment. Full assessment required of existing and future business processes, plan and actions to close and resource allocation and responsibility. | Detailed process validation with individual Participants resulted in the requirement to redesign some solutions, with likely manual effort and customer impacts. | There remains a small number of outstanding business processes between market participants to be finalised. Assumptions workshops nearling completion and E2E EQL process workshop scheduled. | The scope of change puts this item at risk. | commenced and in schedule |  |  |  |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; | Business process impact analysis almost complete. | [6 empty] | Back office service provider has assessed PoC impacts on BAU activity | Subject to confirmation on options in Victoria.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Business Processes completed and Process Owners allocated. Validation continues to be done with MC's (depending on their maturity). Now under formal change control. |  |  | Future business processes are currently being developed using the details from Work Package 1 and 2, as well as the B2B procedures. The timeline for implementation and on-going procedural uncertainty is the basis for Aurora Energy reporting 'at risk'. | Need to do 4.1 as pre requirement. | As above | On track for completing documentation of work instructions for end of September | The scope of change puts this item at risk. | commenced and in schedule |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  | Detailed implementation schedule and program resourcing drafted and aligned to AEMO delivery milestones and timelines. VIC derogation extension not yet clear. Faults and Emergencies process not yet finalised; Engagement with networks is planned to confirm smooth transition. | No longer within schedule due to system delay per 5.2 and 4.1. Development of PoC processes in progress.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Participated in Cycle 1 of Industry Test. |  |  | Activity has not yet started. | Can't do that until accreditation received and system being ready for test. |  | EQL end to end processes walk throughs scheduled to commence week of 11/9/17 |  |  |  |  | Delays from third parties are impacting our ability to participate in industry testing |  | Test planning commenced, detail on industry testing as yet unclear | At risk due to 5.2/4.1.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [8 empty] | Detailed requirements have been gathered and vendors have deliver the changes to market messaging systems. | System delivery being managed by Agility. Back up plan to use Translation tool has now been changed so that we will pursue the full solution in our billing system (Engage from Agility). Development is in progress by Agility for release in September. |  | System designs complete. System build complete. AT complete. SIT Cycle 2 underway. UAT cycle 1 underway. Indstry Testing Cycle 1 underway |  | Vendor at 77% completion of overall project plan |  |  |  |  | Mass Market Design activities complete and Large Customers design in progress. Change requests being assessed and planned. | In addition to 4.1, identification of any interim system changes required to be compliant on 1 Dec drafted.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Drop 4 of 6 has been delivered. |  |  | Aurora Energy has engaged its key market system vendors. System build has completed for essential market connectivity and system functionality for 1 December 2017 apart from future defect releases. | As per 5.1 | Changes required to align with revised LNSP processes has delayed build & test | Build now complete Serveral Change Request under analysis |  |  |  |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities. | Being managed by external vendors. | Build progressing on track | Reverted from 'Not within Schedule' given we are no longer looking at implementing PoC with new system for 1 Dec. Dependent on completed development and implementation of B2B Translation Tool, and any changes per 5.1. Uncertainty regarding B2B Errata process and timelines for potential schema updates.
5.3 |  | The internal testing of market systems for your business | [5 empty] | 3 cycles of SIT has been completed, UAT and Regression testing has commenced. |  |  | Aurora Energy is progressing through System Test in the lead up to UAT and Market Trial test activities. | As per 5.1 | As above | Assembly Testing Complete, SIT has commenced, System Performance testing has commenced |  |  |  |  | The late delivery of our B2B code by the external provider doesn't allow enough time for internal testing | Schedule to occur later in 2017. | Testing is progressing on track. Risks remain around open changes eg Vic derogation. | As per 5.2 |  |  |  |  | Commenced for B2M and B2B
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Completed accreditation scenarios with e-hub and participated in Cycle 1 of Industry Test. |  |  | Aurora Energy was unable to participate in AEMO's first round of testing due to no other participants being available. eHub connectivity has been tested and established and B2B accreditation testing has commenced. Aurora Energy is ready to commence cycle 2 of Market Trial as planned but is still reliant on other participants to perform testing and therefore continues to consider this to be 'at risk'. | As per 5.1 | Lack of participation by other industry participants is increasing readiness risk. | Intermittant issues with AEMO ehub functionality is impeeding the EEQ's ability to execute and complete industry test scenarios within cycle 1 Ongoing defects pertainng to NEM12 file delivery and format also impacting ability to successfull execute industry testing scenarios. This is having a downstream impact on entry criteria to UAT. | [5 empty] | Schedule to occur later in 2017. | Small cohort available for cycle 1 industry testing due to industry participant readiness. A slow start is therefore expected. | As per 5.2 Agreement with test partners (particularly MCs) yet to be confirmed. No longer joining Market Trial Cycle 2. Plan to join in Cycle 3. |  |  |  |  | Testing with market participants in Cycle 1 of Phase 3
5.5 |  | The validation of performance of market systems during industry testing | [8 empty] | Aurora Energy is planning to separately initiate performance testing, as distinct from market interface testing, scheduled for October 2017. Aurora Energy is reliant on key system vendors to perform performance testing and therefore continues to consider this to be 'at risk' | As per 5.1 | As above | EEQ Systems are functioning as expected however the above, AEMO ehub and NEM12 file format issues speak to the validation of performance of MSATS and eHub. | [5 empty] | Schedule to occur later in 2017. | Batch performance and sizing in progress | As per 5.2 |  |  |  | Target Rounds 2 and 3 of industry testing.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Detailed planning in progress. |  |  | A Transition Plan will be completed once AEMO packages and commercial agreements with Metering Coordinator(s) are finalised. Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. We are now looking to include our Metering Co Ordinator in these meetings. | Will start when 5.4 & 5.5 are complete | Concerned about slow progress of the AEMO contingency planning. | Draft Deployment Aproach prepared. |  |  |  |  | Transition plans are dependent on timely delivery of earlier program stages | Schedule to occur later in 2017. | Time frame for cutover coincides with: 1) peak period for numerous BAU teams (New Connections, C&I re-contracting); and 2) Natural Disaster season (bushfire, cyclone, etc.). Transition & Cutover planning will take this into account. | Internal cutover planning commenced, based on output from ITCFG. |  |  |  | Transition and cut over working group outcomes are not yet finalised (in draft), as such, this is impacting the preparation of our business processes. Of particular concern are: - New connections process - initial MC contracts are in draft and being assessed - readiness of competitive MCs |  |  | Clarification regarding handling of inflight transactions across the cutover weekend becomomg clear at industry level. | Initial feedback from AEMO indicates a transitional approach to dealing with lagacy data in MSATS.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Transition planning is progressing to schedule. |  |  | Aurora Energy has started discussions with TasNetworks regarding transition and cutover planning. This has been communicated to the relevant AEMO working group. | Will start when 5.4 & 5.5 are complete | [6 empty] | Draft version of internal Momentum Transition and Cut Over Plan in progress | Schedule to occur later in 2017. | Transition planning and scheduling cannot be accurately determined until Design & Build is completed. Bulk Data conversion for Meter Standing Data (MC/ENM role, NMI/Meter Register Status) across industry participants is still unknown and therefore impacting our Build / Test activities; AEMO's position to leave to participants to update data may lead to substantial issues with integrity of information and risk of performance if all participants have to update MSATS at the same time during cutover;
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Retail | AGL Retailer Powerdirect | Alinta Energy | Aurora Energy | Energy Locals | Energy Australia | Ergon Energy Queensland (retail) | ERM Power Retail | M2 Energy Pty Ltd | Macquarie Bank Limited | Mojo Power | Momentum Energy | Next Business Energy | Origin Energy | Pacific Hydro / Tango | People Energy Pty Ltd | Pooled Energy | Powershop | Red Energy & Lumo Energy | Simply Energy | Stanwell Corporation Limited | Sumo Power | WINConnect Pty LTD | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [8 empty] | Aurora Energy has implemented a program of work to interpret and implement the POC reforms, within the context of the timeframe and procedural uncertainty. | Request commitment from AEMO to 1 Dec date by 31 Aug. If not received, take a decision on 1 Sep over participation or otherwise. | Ongoing meetings with DNSP's to align processes. | [6 empty] | n/a | Progressing with working assumptions.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [8 empty] | Aurora Energy has implemented a program of work to effectively and efficiently work towards market compliance. | As above | Implementing manual processes for December 1st which will be progressively implemented over the following quarter. | EEQ continues to work with delivery partners in go-live preparations | [5 empty] | n/a
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Meeting with ACT Government conducted - no expected barriers at this point. NSW Govt is proving to be a challenge to engage. |  |  | Aurora Energy has implemented a program of work to interpret and implement the POC reforms that factors in the challenging timeframe and procedural uncertainty. Aurora Energy continues to engage with AEMO and other market participants to inform its assessment. | As above |  | Ongoing discussions with the Department of Energy and Water Supply and participation in development of a national framework for remote re-energisation. At this stage it is unlikely that remote re-energisation will be available to retailers on 1 December 2017. | [5 empty] | n/a |  | Monitor jurisdictional saftey discussion. |  |  |  |  | Internal assessments have commenced
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Internal documents related to Cth legislation are listed by branch and business unit. Dates for update and review have been set. Codes of Practice being written for key areas. |  |  | Aurora Energy continues to liaise with the Tasmania Government and WorkSafe Tasmanian to identify jurisdictional requirements that require amendment to facilitate metering competition. |  | Actively participating in industry working group for developing industry re-en/de-en guideline. | AEMO and Department of Energy and Water Supply are currently addressing jurisdictional changes to Metrology Part A. - will need to be endorsed by COAG Energy Council by ~Nov | [5 empty] | n/a |  | Closely review and monitor Vic Government's progress of the OIC. Discussions with DBs ongoing.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [6 empty] | MC contract submitted and now in review. Further contract development underway. |  | Aurora Energy's procurement process for securing a Metering Coordinator for small customers is at a progressed state with a preferred MC selected but not yet contracted. | Get list of accredited MCs from AEMO. Get crystal clear clarity from AEMO on role of MC (it currently differs according to who we talk to in the industry). |  | Ensure contingencies are in place to enable interim arrangements if required for commercial arrangements. | [5 empty] | Adopting of staged approach for new connections and adds and alts - awaiting confirmation that staged approach includes adds and alts. | Origin has onboarded additional Business and Technology resources | [5 empty] | We've escalated this to the senior management of metering service providers and awaiting their response by mid September and failure to receive any concrete plans will resilt in escalation from AEMO (via PCF).
2.4 |  | An assessment of the required accreditation and registration activities | [8 empty] | Aurora Energy has submitted its accreditation application and is proceeding on the assumption that accreditation will be received. | Chase AEMO re our application |  | Daily EQL Industry testing working group established | [5 empty] | n/a |  | Dependent on AEMO delivery of B2B Translation Tool, and our implementation and testing. Draft B2B Accreditation Guide under review.
2.5 |  | The fulfilment of accreditation and registration obligations | [18 empty] | Origin has onboarded additional Business and Technology resources
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [10 empty] | FTE revalidation in process | [6 empty] | n/a
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [8 empty] | Aurora Energy has established the core group of its Testing team and will continue to expand its testing resources over the coming months. |  |  | Approval to recruit TST being sought. | [5 empty] | n/a
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [10 empty] | Developing ‘return to green’ plan | Additional training resourced recruited, training requirements being reviewed and alternate training delivery plan drafted to addres delays in preparation of training materials. | [5 empty] | Acess to additional, resources thorugh external business consultants. |  | Reallocation of resources to cover this activity.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [7 empty] | Dependent on engagement of Metering partners | Aurora Energy continues to invest considerable effort in participating in AEMO procedural consultation. Aurora Energy is proceeding on the basis of the currently available information and must continue to manage the risk of final procedures changing. |  | Ongoing DNSP and MC meetings. | Contingency planning for market participant readiness progressing.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [7 empty] | Additional resourcing on board |  |  | Additional DNSP specific processes under development | [8 empty] | Reallocation of resources to cover this activity.
4.3 |  | The validation of business processes during industry testing | [6 empty] | Via cycle 1. Cycle 3 will concentrate on full e2e process testing | Moved some test cases to later cycles. Planned for additional bilateral testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | Use Translation tool approved for build by AEMO. Supplement with documentation for manual use of MSATS to perform market transactions and service orders. Partner with a another Agility supported T2 / T3 retailer to leverage work. | [9 empty] | Assisting AEMO with testing of B2B Translation Tool. Reviewed draft Vic OIC.
5.2 |  | The development and build of appropriate market systems for your business | [19 empty] | Closely monitoring IEC/B2BWG/ASWG discussions and potential for additional B2B Errata/schema changes prior to 1 Dec.
5.3 |  | The internal testing of market systems for your business | [19 empty] | As per 5.2
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | C&I instance testing to commence later. Using same PoC code line. |  |  | Test cases have been rescheduled to cycles 2 & 3 | Attendance to daily AEMO Industry Testing Working Group Attending Daily EQL testing working group to discuss current issues Amending current testing approach to conduct both UAT and Industry testing from the same connected enviornment. | [7 empty] | As per 5.2
5.5 |  | The validation of performance of market systems during industry testing | [10 empty] | as above | Attendance to daily AEMO Industry Testing Working Group Attending Daily EQL testing working group to discuss current issues Amending current testing approach to conduct both UAT and Industry testing from the same connected enviornment. | [7 empty] | As per 5.2
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [6 empty] | Draft transition plan ready / draft implementation plan prepared |  | Aurora Energy transition and cutover preparations are being supported by its attendance at AEMO cutover and planning workshops. | [9 empty] | Transition & Cutover planning will take this into account.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Retailer Participation
References:
[8 empty] | AEMO | http://www.aemo.com.au/Electricity/National-Electricity-Market-NEM/Participant-information/Current-participants/Current-registration-and-exemption-lists
[8 empty] | AER | https://www.aer.gov.au/retail-markets/authorisations/public-register-of-authorised-retailers-and-authorisation-applications
[8 empty] | ESC | http://www.esc.vic.gov.au/project/energy/2075-licensing/
Retailer | On Sep 2017 Report? | On Aug 2017 Report? | On Jul 2017 Report? | On Jun 2017 Report? | On May 2017 Report? | On April 2017 Report? | On March 2017 Report?
1st Energy Pty Ltd | No | No | No | No | No | No | No
ActewAGL Retail | Yes | Yes | Yes | Yes | Yes | Yes | Yes
AGL | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Alinta Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Aurora Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Blue NRG Pty Ltd | No | No | No | No | No | No | No
Click Energy Pty Ltd | No | No | No | No | No | No | No
Covau Pty Limited | No | No | No | No | No | No | No
COzero Energy Retail Pty Ltd | No | No | No | No | No | No | No
Diamond Energy Pty Ltd | No | No | No | No | No | No | No
Energy Locals Pty Ltd | Yes (using August report) | Yes | No | No | No | No | No
EnergyAustralia | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Enova Energy Pty Ltd | No | No | No | No | No | No | No
Ergon Energy Queensland (retail) | Yes | Yes | Yes | Yes | Yes | Yes (using March report) | Yes
ERM Power Retail Pty Ltd | Yes | Yes | Yes | Yes | Yes | No | No
Globird Energy Pty Ltd | No | No | No | No | No | No | No
Lumo Energy (reporting with Red Energy) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
M2 Energy Pty Ltd | Yes | Yes | Yes | Yes (using May report) | Yes | Yes | Yes
Macquarie Bank Limited | Yes | Yes | Yes | Yes | No | No | No
Mojo Power Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Momentum Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Next Business Energy Pty Ltd | Yes | Yes | Yes | No | No | No | No
Online Power and Gas Pty Ltd | No | No | No | No | No | No | No
Onsite Energy Solutions Pty Ltd | No | No | No | No | No | No | No
Origin Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pacific Hydro / Tango | Yes | Yes | Yes | Yes | Yes | Yes | Yes
People Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Pooled Energy Pty Ltd | Yes | Yes | Yes | Yes | Yes | Yes | No
Powerdirect Pty Ltd (reporting with AGL) | Yes | Yes | Yes | Yes | No | No | No
Powershop Australia Pty Limited | Yes | Yes (using July report) | Yes | No | Yes (using April report) | Yes | No
Progressive Green Pty Ltd | No | No | No | No | No | No | No
Qenergy Limited | No | No | No | No | No | No | No
Red Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Sanctuary Energy Pty Ltd | No | No | No | No | No | No | No
Simply Energy | Yes | Yes | Yes | Yes | Yes | Yes | Yes
SparQ Pty Ltd (Sumo Power) | Yes | Yes | Yes (using June report) | Yes | No | No | No
Stanwell Corporation Limited (Stanwell Energy) | Yes | Yes | Yes | Yes | Yes | Yes | No
WINenergy Pty Ltd (WINenergy) | Yes | Yes | Yes | No | No | No | No

## Distributor Reports
| 2017-09-11 |  |  | Distributor Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| ActewAGL Distribution (AAD) | Within schedule | Medium | [AEMO Note - Using 7 Aug 17 Report for AAD]: For this reporting period the project remains heavily focussed on development and testing activities. AAD has commenced the test cycle 3 of 6. AAD is currently conducting workshops with retailers to establish detailed processes. AAD is now shifting its attention from procedural documents and commencing a detailed revision of all online materials and other supporting documentation. Total project progress is estimated at 49%. | [13 empty] | AAD has submitted the required information for accreditation as the initial MC for type 5, 6 and 7 metering installations and are responding to AEMO queries. Type 3-4 metering accreditation has now been received and AAD is continuing work on systems development to maintain compliance with the PoC reforms. The readiness of AAD to interface with the AEMO B2B eHub is a significant risk. In the absence of information, the system changes required to facilitate this new data flow is undefined. It is noted AEMO have 12 mths to develop this and Industry only have 3.5 mths to implement. There is a disparate timeframe for Industry to modify, test, put into production and this is noted as a major area of concern for AAD. AAD has noted that AEMO is making a "planning assumption" of go live on 4 December allowing for cutover activities to occur on the weekend of 2/3 December. AAD welcomes clarification on this point and is working to 1 December 2017 in the absence of formal notification of a delay.
| Ausgrid - Distribution Business | At risk | Medium | The lack of resolution of the proposed transitional process is negatively impacting business planning, process development and communnications to external parties. Cycle 1 of industry testing has compelted successfully, however, Internal system testing is still underway. | [7 empty] | [Refer to overall comment]
| AusNet Services | Within schedule | Medium | On track for 1st December cutover and go-live. Other participant readiness across the NEM remains a risk, the majority of contributing concerns are not relevant within Victoria given metering exclusivity. | [7 empty] | Refer to overall comment.
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | At risk | Medium | CitiPower/Powercor is continuing to progress its build/test phase. Program timing remains challenging with no tolerance for delays or further requirement changes. CitiPower/Powercor has participated in industry planning for market trials and 1 December 2017 industry transition and cutover. We have hosted an information forum for retailers. We are available to meet one-one with any industry participant at their request. | [7 empty] | The Victorian Government has decided that distributors will be required to continue to install remotely read interval metering after 1 December 2017 compliant with the Victorian AMI functionality and service levels specifications and that existing and new/replacement AMI metering will be continue to be classified as Type 5 metering. In line with this decision and the draft Orders in Council published by the Victorian Government, CitiPower and Powercor will not be making any changes to how we classify either existing or new/replacement AMI meters in MSATS, nor any changes to our forward estimates, meter data validation and/or substitution methodologies. The Government Orders are yet to be finalised and a discussion paper on embedded networks yet to be published.
| Endeavour Energy | Within schedule | Medium | A project risk is the implementation of system and procedural changes to comply with the B2B procedures, which requires significant system and process changes over a period of only 6-7 months to design, develop and test. This short timeframe increases the risk on quality vendor delivery, however to date our vendors have made good progress against our schedule having provided periodic system functionality drops enabling us to commence testing. A key dependency for our PoC project, which is technical currency of our core system, has been successfully implemented. Another project risk is that different interpretations from each market participant of the Rules, procedures and jurisdictional obligations may result in an ineffective or unworkable processes between businesses. To mitigate this we are actively engaging with retailers and metering service providers to foster an open dialog on managing key processes. These engagements are proving beneficial as they are highlighting differences in our assumptions and approaches to some of the processes at an early point of the project. To help industry and to provide us better confidence that our solution will work effectively with other market participants we are participating in the industry testing and additional bi-lateral testing with other participants. We are also actively participating in the various working groups including the PoC-WG, B2BWG, PCF, ITCFWG, RWG and SWG to ensure that AEMO procedures and B2B procedures supports the metering contestability and embedded networks rule changes in the most effective and cost efficient manner, and to only include transactions and obligations required for go live as a priority. | [7 empty] | [Refer to overall comment] | [5 empty] | This report is for Endeavour Energy as at 31 August 2017. Endeavour Energy will be operating as a LNSP, and as the initial MC, MP and MDP for type 5, 6 & 7 metering installations from 1 December 2017. Endeavour Energy have implemented a project team to manage the impacts of Power of Choice. The activities for the Market Systems testing and cutover are dependent on the development and build of the appropriate market system which is currently at risk.
| Energex Ltd. & Ergon Energy Corporation Ltd. | At risk | Medium | The Distribution project is tracking slightly behind its intended schedule however is confident that it will meet 1 December 17 compliance requirements. The project is undertaking its System Integration Testing and Industry Testing release in priority order. The changed transitional approach is adding additional work to a tight timeline at a critical point in the project. Similar to last month, the project's key focus is on testing its Market systems and new processes. Industry testing and ehub Accrediation testing is also a key focus. | [7 empty] | The Distribution project is tracking slightly behind its intended schedule however is confident that it will meet 1 December 17 compliance requirements. The project is undertaking its System Integration Testing and Industry Testing release in priority order. The changed transitional approach is adding additional work to a tight timeline at a critical point in the project. Similar to last month, the project's key focus is on testing its Market systems and new processes. Industry testing and ehub Accrediation testing is also a key focus.
| Essential Energy | At risk | High | Essential Energy's PoC program is progressing, with system changes on the critical path to deliver compliance by 1 December 2017. The program has delivered all systems changes required for industry testing, with positive results for cycle 1 testing. A number of business efficiency system changes have been deferred for delivery post 1 December. A significant issue exists with Essential Energy's Initial MC registration, this is being worked through with AEMO. | [7 empty] | [Distributor, Risk Rating = High]: Risk rating remains at high Program schedule is tight and does not provide tolerance for any delays. Some business efficiency items deferred for delivery post 1 December. [Meter Provider, Risk Rating = Low] [Meter Data Provider, Risk Rating = Medium]: Risk rating is classified as moderate for systems changes to support amended B2B framework, including to receive and process meter exchange information to enable timely publishing of final readings for Type 5 & 6 meters. | [5 empty] | Essential Energy will be an Initial MC, MDP and MP for Type 5 and 6 meter installations connected as at 1 December 2017. Essential Energy is actively participating in AEMO industry groups and NSW jurisdictional workshops associated with Power of Choice.
| Jemena Electricity Networks | Within schedule | Medium | With 12 weeks to go-live on 3 December 2017, JEN's build is complete, User Acceptance Testing, Industry Testing and Bilateral Testing is in progress as is end-user training. Draft deemed MC T&Cs and Retailer Operations Handbook have been issued to all Retailers who have customers on the Jemena Electricity Network. Partner readiness risks to the JEN Program remain as AMBER. | [7 empty] | With 12 weeks to go-live on 3 December 2017, JEN's build is complete, User Acceptance Testing, Industry Testing and Retailer Bilateral Testing is in progress as is end-user training. Draft deemed MC T&Cs and Retailer Operations Handbook have been issued to all Retailers who have customers on the Jemena Electricity Network. Partner readiness risks to the JEN Program remain as AMBER.
| SA Power Networks | At risk | Medium | SAPN continue to face significant project challenges, particularly with regards to the development of the market system. At this point we still believe that we will be in a positon to achieve minimum market compliance. SAPN are working with Industry regarding the Opt-in Staged Transition for Connection related work, however, resolution regarding all the key inputs (particularly Regulatory support and DNSP's costs) is needed urgently if this option is to remain viable. | [7 empty] | See overall project status comment
| TasNetworks | At risk | Medium | TasNetworks intends to be ready for the 1st December 2017. TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality which may have a flow on effect to market processes, training activities and potentially other market participants. Some program activities may need to be completed post 1st December. Whilst there are some challenges with the Market Systems other program activities have progressed and are now on schedule.
| United Energy | Within schedule | Medium | Preparations continue to progress well. UE has been participating in both market trials and bi-lateral testing with a number of key retailers. No major concerns have arisen from this testing, although UE notes that only a subset of the industry is participating. The amber risk rating reflects general concerns about industry readiness, and the possible operational impact of market disruption after go-live. | [7 empty] | UE operates in Victoria only. Jurisdictional status reflects overall position. | [5 empty] | Key concerns regarding UE (and industry) readiness are as follows: 1) The Victorian Government draft orders confirm the assumptions that 1: UE's role as MC for new meters after 1 Dec will be on the basis of existing regulated services, 2: New meters after 1 Dec will need to meet only the Vic AMI specifications and 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. Until the amended Orders are finalised, the possibility of unexpected requirements or obligations remains. UE accepts that the likelihood of unexpected change at this late stage is low, but will remain concerned until the Orders are finalised and gazetted. 2) UE compliance with the ENM rules and ring-fencing is dependent on Embedded Network Managers being accredited, assigned and ready to operate by 1 Dec 2017. UE's compliance in this area may also be dependent on existing child metering services being transitioned to meter providers on or by 1 Dec 2017, although the draft Vic Govt amended Orders indicate that this deadline may not apply. If transition is required, it will be an activity over which UE does not have full control, particularly given UE's understanding that there are currently no accredited Embedded Network Managers in the market as at early September 2017. 3) UE is concerned that the complexity and scale of changes may ultimately lead to negative impacts on consumers. Strong focus will be required to ensure that connections and supply processes are clear, and industry has a uniform, efficient and reliable approach so the reform is seamless to customers. It is important that higher participation in readiness reporting and in the remaining testing phases is achieved for a positive 1 Dec 17 start. 4) UE remains concerned that lack of readiness of some industry participants and/or poor results during industry testing may lead to the go-live being delayed from 1 Dec 2017. Whilst the likelihood of this occurring appears to be reducing, if it occurs the cost incurred by UE to retain the appropriate project personnel during the delay will be significant. There will also be a negative impact on operational teams, with readiness preparations having to be interrupted and/or repeated, and recruitment of additional operational personnel being impacted.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| ActewAGL Distribution (AAD) | Within schedule | Medium
| Ausgrid - Distribution Business |  |  | At risk | Medium
| AusNet Services | [10 empty] | Within schedule | Medium
| CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | [10 empty] | At risk | Medium
| Endeavour Energy |  |  | Within schedule | Medium
| Energex Ltd. & Ergon Energy Corporation Ltd. |  |  |  |  | At risk | Medium
| Essential Energy |  |  | At risk | High
| Jemena Electricity Networks | [10 empty] | Within schedule | Medium
| SA Power Networks | [6 empty] | At risk | Medium
| TasNetworks | [8 empty] | At risk | Medium
| United Energy | [10 empty] | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid - Distribution Business | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%)
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 61% - 70% | 81% - 99% | Completed (100%) | Completed (100%) | 91% - 99% | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 99% | Completed (100%)
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 61% - 70% | 81% - 99% | 81% - 99% | Completed (100%) | 81% - 90% | 81% - 90% | Completed (100%) | Completed (100%) | Completed (100%) | 81% - 99% | 91% - 99%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 61% - 70% | 41% - 50% | 71% - 80% | 81% - 99% | 41% - 50% | 51% - 60% | 61% - 70% | Completed (100%) | 61% - 70% | 71% - 80% | 91% - 99%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 41% - 50% | 71% - 80% | 71% - 80% | 61% - 70% | 81% - 90% | 51% - 60% | 61% - 70% | Completed (100%) | 41% - 50% | 81% - 99% | Completed (100%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 71% - 80% | 81% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99% | Completed (100%) | Completed (100%) | Completed (100%) | Completed (100%) | 91% - 99%
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 61% - 70% | 11% - 20% | 51% - 60% | 41% - 50% | 61% - 70% | 81% - 90% | 41% - 50% | Completed (100%) | 31% - 40% | 61% - 70% | 61% - 70%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 61% - 70% | 81% - 99% | Not started (0%) | 71% - 80% | 71% - 80% | 81% - 99% | Completed (100%) | 61% - 70% | 51% - 60% | Completed (100%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 51% - 60% | 31% - 40% | 71% - 80% | Not started (0%) | 81% - 90% | 31% - 40% | 21% - 30% | N/A | N/A | 11% - 20% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 31% - 40% | 21% - 30% | 71% - 80% | 31% - 40% | 21% - 30% | 31% - 40% | 11% - 20% | 61% - 70% | 21% - 30% | 31% - 40% | 71% - 80%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 51% - 60% | 61% - 70% | Completed (100%) | 81% - 99% | 91% - 99% | 91% - 99% | 81% - 99% | Completed (100%) | Completed (100%) | 71% - 80% | Completed (100%)
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 51% - 60% | 21% - 30% | Completed (100%) | 81% - 99% | 91% - 99% | 71% - 80% | 41% - 50% | Completed (100%) | 91% - 99% | 51% - 60% | Completed (100%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not started (0%) | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | 41% - 50% | 21% - 30% | Completed (100%) | 1% - 10% | Not started (0%) | 21% - 30%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%) | 71% - 80% | 81% - 90% | Completed (100%) | Completed (100%) | 81% - 90% | Completed (100%) | Completed (100%)
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 51% - 60% | 81% - 99% | 71% - 80% | 81% - 99% | 31% - 40% | 81% - 90% | 71% - 80% | Completed (100%) | 81% - 90% | 61% - 70% | Completed (100%)
5.3 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | 31% - 40% | 61% - 70% | 61% - 70% | Completed (100%) | 51% - 60% | 61% - 70% | Completed (100%) | 51% - 60% | 21% - 30% | 81% - 90%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not started (0%) | 21% - 30% | 41% - 50% | 11% - 20% | Completed (100%) | 71% - 80% | 21% - 30% | 31% - 40% | 21% - 30% | Not started (0%) | 21% - 30%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not started (0%) | 21% - 30% | 21% - 30% | Not started (0%) | 1% - 10% | 31% - 40% | 21% - 30% | N/A | 41% - 50% | Not started (0%) | 21% - 30%
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 21% - 30% | 21% - 30% | 41% - 50% | 41% - 50% | 21% - 30% | 21% - 30% | 11% - 20% | 71% - 80% | 61% - 70% | 21% - 30% | 81% - 90%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | Not started (0%) | Not started (0%) | 21% - 30% | Not started (0%) | 41% - 50% | Not started (0%) | 31% - 40% | 31% - 40% | 31% - 40% | 21% - 30%
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid - Distribution Business | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed | Completed | Completed | Within schedule | At risk
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | At risk
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Completed
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Completed | Within schedule | Completed | Completed | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed | Within schedule | Within schedule | At risk
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Completed
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | N/A | N/A | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Completed | At risk | Completed
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Completed
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | Completed | Completed | Within schedule | At risk | At risk | Completed | Completed | Within schedule | Within schedule | Completed
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | Within schedule | At risk | At risk | At risk | At risk | Completed | At risk | Not within schedule | Completed
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | At risk | Within schedule | At risk | Completed | At risk | Within schedule | Completed | At risk | Not within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | At risk | Within schedule | At risk | Within schedule | Completed | Within schedule | Within schedule | Within schedule | At risk | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | N/A | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid - Distribution Business | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | The high level impact assessment is complete. Some gaps may be identified as part of the more detailed program of works to be carried out in the period through to December 2017. | Finalisation is awaiting resolution of proposed transitional process |  |  |  | Business review of the Organisational Impact assessment is almost completed. |  |  | Completed | AEMO Pack 3 assessed and no material impact on TasNetworks program.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | AAD is approximately half way through the third of six test cycles. Progress is ahead of schedule AAD is currently conducting workshops with market participants to continue progress on retailer specific items. | Finalisation is awaiting resolution of proposed transitional process |  |  |  | The Business Readiness Framework has been finalised and has received formal approval. |  |  | Completed ( July 2017) | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | AAD is currently working through initial MC contract drafting, legal aspects of market processes and ring fencing implications. | No jurisdictional safety requirements in place yet. |  |  |  | Ongoing activity - currently in progress by organisational specialists. |  |  | Completed | Initial MC (Type 6) T&C's finalised and provided to Retailers. | Given the deferral of competition in Victoria, United Energy has been proceeding on the basis of the following assumptions: 1: UE's role as MC for new meters after 1st of Dec will be on the basis of existing regulated services 2: New meters after 1 Dec will need to meet only the Vic AMI specifications. 3: New meters after 1 Dec will be classified as Type 5 MRIM, per current practice, and existing meters will remain Type 5 MRIM. These have been confirmed through the draft Order-in-Council issued in July 2017, but some risk will remain until the OIC details formally confirmed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | AAD has commenced work on legal agreements relating to customer contracts, initial MC agreements with retailers, terms and conditions for provision of data/information to customers, etc. This work will continue until approximately September. | In progress. No jurisdictional safety requirements in place yet. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - the project is working with the internal regulatory team to ensure all regulatory requirements are met. |  |  | Within schedule; MC Terms and Conditions Published ;Work in progress with the business |  | This work is complete, but is based on the draft outcomes in the Vic Govt Order-in-Council. If the final orders differ from the positions presented to date, rework will be required which may impact readiness.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | As above. | Initial MC T&Cs now issued. Ring-fenced service agreements in progress. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - amendments under consideration by each contract owner, updates will be made using existing procurement and contractual processes. Assessment of new agreements/contracts also ongoing. |  | Deemed T&C's have been issued to Retailers who have Customers on the JEN as draft until OIC is final. | Within schedule; Work in progress with the business | Initial MC (Type 6) T&C's finalised and provided to Retailers. | UE issued its Initial MC Contract in accordance with the relevant rules. It was necessarily based on the draft Order-in-Council documentation issued by the Vic Govt on 20 July. If the final Orders differ from the draft, this may have an impact on the Initial MC Contract. No other major commercial preparations are required.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | AAD has now submitted the required documentation to AEMO for B2B eHub accreditation. Application for accreditation as the initial MC has now been submitted to AEMO. AAD is now responding to clarification questions relating to the MC registration application. Type 4 accreditation has been received and AAD is working towards systems compliance with PoC requirements. | In progress. |  |  |  | All of the required accreditation and registration documentation and associated activities have been completed. The project is currently progressing its self-accreditation with the E-Hub which is almost finalised. |  | Still waiting for AEMO written confirmation. | Completed |  | Based on Vic Govt draft orders, UE continues to assume that accreditation as a Type 4 MDP is not required. Registration as MC and accreditation for use of e-Hub are required.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | As above. | In progress. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The project is clear on the accreditation activities required for compliance and has almost finalised all of its associated obligations as planned. The project is in the process of collating Retailer feedback on the draft T&C's submitted to AEMO, which is one of the final steps required to fulfil all obligations. | Signficant issue with Essential Energy's Intial MC registration |  | Within schedule; Work in progress with the business |  | Accreditation for use of e-Hub and registration as MC for Type 5, 6 and 7 meters will be completed in accordance with AEMO requirements, and preparations are nearing completion. The "at risk" flag reflects the remaining uncertainty about accreditation as a Type 4 MDP (which UE is assuming is not required).
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | A detailed assessment of ongoing operational resource requirements has commenced (approximately 50 per cent complete) to ready the business for the transition and post PoC go-live activities. | Finalisation awaiting resolution of proposed transitional process |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Ongoing activity - Impact assessment is approved and recruit and training of new staff is underway. |  |  | Within schedule; Work in progress with the business | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality | Change impact assessment and personnel budgets complete. Team-by-team impacts covered by 3.2 and 3.3 below.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Recruitment processes have now begun to fill these roles. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The engagement of additional resources has commenced. With the first tranche of new staff undergoing training. The proposed Transitional Approach will have a yet to be calculated impact on resources. |  | Not required for Jemena - out of scope. | Not Applicable | TasNetworks is preparing to understand the role for operational functions but not yet confirmed FTEs as a result of the Market Systems readiness for 1 December. | Operational backfill resources in place to allow subject matter experts to carry out testing. Planning continues for securing post-go-live operational resources, based on a Change Impact Assessment for all impacted teams.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Development of detailed training packages for industry and internal staff relating to network requirements has begun. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | The training approach is progressing as planned, with training collateral in development. |  | End user training is in progress. | Within schedule; Development of training packages are in progress | TasNetworks has commenced implementing the Training Plan for internal staff. Engagement with other market participants has allowed end-to-end processes to progress. | Training materials and work instructions are nearing completion. Training delivery will commence in late October 2017.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Detailed workshops with retailers to develop systems and processes that are compatible with other external requirements are underway. | Finalisation awaiting resolution of proposed transitional process |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority ‘to be’ business processes are complete. Lower priority ‘to be’ business are currently under review, with the intention of moving them to the Release 2 Schedule. |  |  | Completed (April 2017) | Business Process impacts well understood, challenges around final Market Systems solution may impact processes for 1 December.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | As above. | Relies on the above. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | High priority ‘to be’ business processes are completed and currently in circulation for business approval. Lower priority ‘to be’ business are currently under review, with the intention of moving them to the Release 2 Schedule. |  |  | Within schedule; Procedures are being updated to reflect changes from WP3 | To-be business processes well understood, intend to document the processes toward the backend of the project for approval.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Not yet begun. | Expected to start following Cycle 2 insutry testing | Industry testing only covers small subset of transactions. | Note: In line with CitiPower/Powercor program delivery schedule. |  | The first cycle of industry test has not revealed any signifcant assumption misalignment between participants. However, there has been limited participation by MC's so far. Concerned by the level of industry testing that appears to be being undertaken through the msats browser rather than in participant's market systems. Creates the risk that data, assumption and validation issues are not found in cycle 1 of Industry testing. Intermittent AEMO Ehub issues is impacting industry testing. |  |  | In line with SAPN delivery schedule | TasNetworks intends to participate in Cycle 2 of Industry Testing. | UE is participating in both the AEMO-led Market Trials and bi-lateral testing with multiple participants, including the major retailers in UE's distribution area. UE remains concerned that varying interpretations and inconsistencies between industry participants will become apparent during industry testing and may threaten its progress. However the early signs from industry testing completed to date are positive.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | AAD has a change request process underway for several minor amendments to system design. Changes are at various stages ranging from conceptual design through to development. | All solution designs are complete. |  | Note: In line with CitiPower/Powercor program delivery schedule. | See above comment | Requirement specifications and high priority designs are complete. The project's phased implementation approach ensures the achievement of compliance in release 1 and further efficiencies in release 2 of which will occur post 1 December 2017. The Proposed Transitional Approach brings additional risk due to the significant re-work and potential of additional scope. The risk of misalignment of assumptions between participants, continues with assumptions being realised throughout participation in Industry Testing. |  |  | Within schedule; Work in progress with the business |  | Based on Vic Govt advice that existing and new meters are to remain Type 5 MRIM, all solution impacts have been assessed.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All initial code has been received by AAD. System updates relating to change requests (see above) are resulting in ongoing development efforts. | The implementation phase is nearing completion with final build tasks being completed in line with the project schedule. |  | Critical path has little remaining contingency | See above comment | The build and test phase is progressing well however is slightly behind schedule. There is very little contingency remaining in the build schedule. Key Risk: changes in retailer / MC assumptions of the interpretation of the B2B procedures may impact the build schedule. | Agile delivery approach applied to system changes. Sprints required for market testing will be delivered just prior to commencement of market testing. |  | Business will go live as per plan however with lot of work arounds which is not ideal | TasNetworks is facing some challenges in completing all Market Systems changes and testing before 1 December. TasNetworks is taking a risk based approach on the delivery of the Market Systems functionality | Development and component testing of the core "market" solution that will support the MC changes on 1 December 2017 is complete.
5.3 |  | The internal testing of market systems for your business | [5 empty] | Internal testing is approximately 50% complete. AAD still holds concern for time constraints around retesting of blocked and failed tests already run. | Testing is underway. 15 testers are working across all solution components. Cycle 1 of Industry testing has completed successfully. |  | Note: Refer above. |  | Testing is currently tracking to schedule. However, testing timelines are compressed and therefore are 'At risk'. |  |  | Refer to Section 5.2 comment | Testing progress has been impacted by the level of defects identified to-date. | End-to-end integration testing of the core "market" solution that will support the MC changes is complete. User acceptance testing commences 11 Sept and will be executed in parallel with industry testing.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Not yet begun. | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. One issue related to SSL Certificate validation with AEMO remains. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  | The reporting of industry test results are unnecesarily complicated and in some instances not accurate. It is not possible to assess the level of regression risk from the industry testing reports. AEMO needs to improve the accuracy and relevance of reporting. | Refer to Section 5.2 comment; testing of market system interfaces will depend on the built solution and appropriate participation | TasNetworks intends to participate in industry testing during Cycle 2. | Market Trials and bi-lateral testing with the major retailers in UE's distribution area is underway and progressing well.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Not yet begun. | Testing with market systems is underway. | Timeframe for Industry Testing is very short given complexity, scope and number of participants | Note: In line with CitiPower/Powercor program delivery schedule. |  |  |  | The industry test plan performance testing is out of scope. We are unsure as to why this line item is in the report as there is no scheduled structured industry performance testing in AEMO's Industry Program Plan. | Within schedule; Phase 1 and Phase 2 Industry Testing complete | TasNetworks intends to participate in industry testing during Cycle 2. | Market Trials and bi-lateral testing with the major retailers in UE's distribution area is underway and progressing well.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | AAD is currently preparing transition and cutover plans. This includes actively participating in the ITCFG with AEMO and engaging with market participants to plan for jurisdictional specific measures. AAD is working with retailers to ensure readiness to go live on 1 December 2017. | System transition planning being undertaken in ITCFG, however awaiting resolution of proposed transitional process for new connections. |  | Note: In line with AEMO schedule of released documentation and CitiPower/Powercor program delivery schedule. |  | New proposed transitional approach requires industry wide acceptance before planning can commence. The Distribution Project supports the New Connection transitional approach, which requires a considerable re-work to our solution. Interest in the Adds & Alts Transitional Approach is being canvassed with key retailers due to the significant risk it will add to meeting compliance requirements of 1 December 2017. |  | Transition and resumption planning is in progress. Industry contingency planning has commenced. | Within schedule; Business Transition Tasks Identified & Planning in Progress | This activity is under pressure due to the competing priorities and compressed timelines. This activity is also dependant on other market participants. | Detailed cutover plan is at final draft, and has been informed by a Dress Rehearsal exercise in August 2017. Transitional preparations and documentation are well progressed.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | As above. | Not due yet. |  | Note: In line with CitiPower/Powercor program delivery schedule. |  | Due to the proposed Transitional Approach the project cutover and transition plan is in a state of flux. |  |  | Within schedule; Data Analysis and Data Cleaning started | Data migration strategy complete. Cutover Planning activities underway. | Preparation work is progressing well. The first of two full dress rehearsals was successfully completed in mid-August 2017 and learning points have been addressed. A second dress rehearsal is planned for mid October. No major data migrations or conversions are required.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | ActewAGL Distribution (AAD) | Ausgrid - Distribution Business | AusNet Services | CitiPower Pty Ltd and Powercor Australia Ltd (CitiPower/Powercor) | Endeavour Energy | Energex Ltd. & Ergon Energy Corporation Ltd. | Essential Energy | Jemena Electricity Networks | SA Power Networks | TasNetworks | United Energy
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | AAD has established risk, issue and decision registers to track and mitigate gaps that are identified as progress is made. |  |  |  |  | Further review is in progress to asses the impacts of the proposed transitional approach.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Weekend work and additional test resources have been approved to mitigate the risks associated with slower than expected progress. |  |  |  |  | Further review is in progress to asses the impacts of the proposed transitional approach.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [15 empty] | In July, the Vic Govt issued two draft orders that will be used to implement the deferral, and associated explanatory notes. UE assessed this documentation and provided feedback to the Vic Govt on 4 Aug. This was followed by the DELWP position paper on embedded network child metering arrangements. In both cases, no major concerns were raised. However UE continues to urge prompt finalisation of the changed Vic Govt Orders to ensure that no unexpected requirements or obligations are introduced.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [15 empty] | As above.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [15 empty] | UE continues to proceed on the basis of the draft orders issued on 20 July. Any changes to the draft materials may require change to the UE MC contract.
2.4 |  | An assessment of the required accreditation and registration activities | [15 empty] | As noted above, UE continues to urge prompt finalisation of the draft Vic Govt Orders so that accreditation requirements can be confirmed.
2.5 |  | The fulfilment of accreditation and registration obligations | [11 empty] | This is being worked through with AEMO |  |  |  | As above.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Requirements for additional testers and a business analyst has begun to mitigate risks associated with testing and delivery.
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing | [14 empty] | Validation of business processes may be done outside of industry testing and during UAT | To address concerns about varying interpretations of B2B procedures between industry participants, UE has issued both a retailer handbook and a more detailed transaction guide to assist other participants with testing their interactions for customers in UE's distribution area.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [9 empty] | See above comment
5.2 |  | The development and build of appropriate market systems for your business | [6 empty] | All available resources have been assigned to the design & development tasks. |  |  | See above comment | The Project has implemented a phased implementation approach. | Working closely with vendor and business to ensure sprints are delivered on time and of high quality. Some non-market facing items deferred for delivery after 1 December 207. |  |  |  | Development and testing of flexible "management information" reports to support operational teams is nearing completion. This work is not a dependency for 1 Dec go-live.
5.3 |  | The internal testing of market systems for your business | [15 empty] | Refer note above.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [14 empty] | TasNetworks expects to begin this activity during the next reporting period.
5.5 |  | The validation of performance of market systems during industry testing | [14 empty] | TasNetworks expects to begin this activity during the next reporting period.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [10 empty] | Support of Transitional Approach through participation of industry working groups and other industry bodies.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [10 empty] | Once a decision is made on the proposed Transitional Approach, the project will be able to commence planning of cutover and transition activities taking into consideration the new approach.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## MP and MDP Reports
| 2017-09-11 |  |  | Metering Provider (MP) and Metering Data Provider (MDP) Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | 1. AEMO Package 3 received 4/9/2017 - Assessment of the final package 3 is underway to ensure any amendments to systems and processes are undertaken prior to PoC 2. Ensuring any changes driven by the DNSP Transition Approach to Cut-Over (AEMO Exec Forum - 28 August) is incorporated into the Active Stream transition and cut-over plans. 3.DNSP Meter lock issues still to be resolved to allow contestible metering providers access to metering installations. 4. Confirmation still required from AEMO that all DNSPs, when called out for faults/emergencies will bypass meters that are identified as faulty, to allow retailers the opportunity to raise service orders for meter exchanges with their contestible metering provider.
| Acumen Metering | At risk | Medium | Current period - Amber status remains within a tight schedule. Work progresses with development of changes and testing whilst concurrently aligning with AEMO and participants as we move towards Cycle 2 and defining the business, people and cutover impacts. Coordinating time and input across multiple parties for bilateral and commercial agreements remains challenging for all and resolution of development and system issues arising following testing and increasing understanding of cutover and transition adds to thecomplexity. All three applications submitted (MP/MDP/MC). Currently providing clarification for MDP queries. Ongoing monitoring and mitigation of challenges is being sustained and confidence of readiness for go-live remains.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in test. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts are being executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development.
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Within schedule | Medium | Revised project delivery plan progressing well. Jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. Transitional plan option being considered introduces uncertainty and additional workload. AEMO delays in setting up new participant IDs has impacted testing.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017.
| Spotless Advanced Metering | Within schedule | Low | [8 empty] | Accrediation Audit completed early August, all outstanding minor actions completed. Awaiting confirmation of MPB Accrediation from AEMO Accrediation Audit completed early August, all outstanding minor actions completed. Awaiting confirmation of MDP Accrediation from AEMO
| VECTORAMS | Within schedule | Medium | Scope of change and tight timeframes to deliver IT changes and establsih commercial arrangements result in a project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium |  |  | Within schedule | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 90% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | 51% - 60% | Completed (100%) | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 90% | 71% - 80% | 81% - 99% | Completed (100%) | 81% - 90% | 51% - 60% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | 11% - 20% | Completed (100%) | 81% - 90% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 91% - 99% | 71% - 80% | 41% - 50% | 81% - 99% | 41% - 50% | 71% - 80% | 11% - 20% | Completed (100%) | 81% - 90% | 71% - 80%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 71% - 80% | 31% - 40% | 61% - 70% | 81% - 99% | 31% - 40% | 51% - 60% | 11% - 20% | 51% - 60% | 81% - 90% | 51% - 60%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 91% - 99% | 81% - 99% | Completed (100%) | 81% - 99% | 81% - 90% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 91% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 71% - 80% | 51% - 60% | 11% - 20% | 81% - 90% | 91% - 99% | 61% - 70%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 90% | 61% - 70% | 61% - 70% | Completed (100%) | 71% - 80% | 71% - 80% | 41% - 50% | Completed (100%) | 71% - 80% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | 61% - 70% | 31% - 40% | Completed (100%) | 51% - 60% | 71% - 80% | 21% - 30% | 71% - 80% | 71% - 80% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 41% - 50% | 11% - 20% | 21% - 30% | Completed (100%) | 21% - 30% | 41% - 50% | Not started (0%) | 31% - 40% | 81% - 90% | 21% - 30%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 91% - 99% | 71% - 80% | 81% - 99% | 81% - 99% | 71% - 80% | 51% - 60% | 41% - 50% | Completed (100%) | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 90% | 61% - 70% | 41% - 50% | 81% - 99% | 41% - 50% | 51% - 60% | 21% - 30% | 81% - 90% | 81% - 99% | 61% - 70%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 11% - 20% | 31% - 40% | 21% - 30% | 71% - 80% | 11% - 20% | 21% - 30% | Not started (0%) | 21% - 30% | Not started (0%) | 11% - 20%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | 61% - 70% | Completed (100%) | 81% - 99% | 61% - 70% | 61% - 70% | 21% - 30% | Completed (100%) | 81% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 90% | 41% - 50% | 81% - 99% | 71% - 80% | 51% - 60% | 51% - 60% | 1% - 10% | 81% - 90% | 81% - 90% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 90% | 21% - 30% | 31% - 40% | 81% - 99% | 31% - 40% | 11% - 20% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 51% - 60% | 11% - 20% | 21% - 30% | 51% - 60% | 21% - 30% | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 11% - 20%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 11% - 20% | 1% - 10% | 21% - 30% | 51% - 60% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 51% - 60% | 11% - 20% | 51% - 60% | 51% - 60% | 31% - 40% | 61% - 70% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 1% - 10% | Not started (0%) | Not started (0%) | 51% - 60% | Not started (0%) | 61% - 70% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Assessment being undertaken against the Final AEMO package 3 outcomes |  | MC supporting documents arising from MC Application submission complete.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Optionality plans to accommodate 1 step (CR6800) or 2 step (CR6300/CR6800) approaches undertaken to ensure compliance |  | Working with ITCFG to understand impacts before completing planning |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Working with legal and regulatory to ensure contracts, process and systems comply across jurisdictions |  | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Active Stream internal policies updated to reflect any variations in PoC and jurisdictional requirements |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules and interpretation of ring-fencing guideline requirements.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Continuing to engage with key stakeholders and counterparties for PoC contract development with Deemed contracts being developed as a safety net |  | Reviews in progress. This is a significant logistical effort to negotiate agrements with each prospective party. |  | Complexity of contractual and commercial arrangements is challenging. Transitional plan option being considered introduces uncertainty and additional workload. | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Select Solutions is continuing to work through the review and update to a large volume of indivdual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negiotiation timeframes will impact arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Already achieved MC registration for 1/12. Currently finalising MP and MDP reaccreditation - on track. eHub accreditation testing, planned for execution in Market Trials, cycle 2 |  | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | MC Accreditation obtained. MDP and MP accreditation on track |  | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. |  |  | Metering Coordinator registration application submitted to AEMO. |  | MC Registration (and all supporting documentation) has been submitted to AEMO and is currently under review.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Active Stream resourcing requirements for project deployment and ongoing BAU have been determined - monitor and update for remainder of project |  | Awaiting final updates to policies and work instructions. |  | Corporate restructuring and ring fencing requirements continue to impact HR plan.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Active Stream resourcing requirements for project deployment and ongoing BAU have been determined - monitor and update for remainder of project |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Work now commenced to review and amend operational Work Instructions and QRGs, prior to undertaking training execution closer to PoC go-live |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Now that the Final Package 3 has been received this is currently under review |  | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  | Jurisdictional differences and variation in Retailer expectations of MC are resulting in more complex processes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Any changes that come from the review will determine the need for any further changes or documentation |  | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  | The volume of documents requiring approval and system integrator changes have delayed this work. |  |  | We are on track to complete documentation updates as part of project activities.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 1 completed and partial scope executed. Currently on track within available schedule, but this item does depend on external parties (generally retailers) to drive the progress and completion |  | Cycle 1 Industry Testing successful. |  |  | Industry testing not completed. |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Detailed assessment undertaken and incorporated into system requirements and design. This will be assessed and monitored through testing, trial conversions and dress rehearsals |  | All solution designs are complete.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Finalising systems before systems freeze and code lock-downs |  | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Change in systems approach has delayed progress in build activities. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [5 empty] | PoC system/SIT/UAT testing underway |  | Testing is underway. 15 testers are working across all solution components. Cycle 1 of Industry testing has completed successfully. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Bilateral testing undertaken, Market trials underway eHub accreditation testing, planned for execution in Market Trials, cycle 2 |  | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. One issue related to SSL Certificate validation with AEMO remains. | intelliHUB has significant problems getting web service API connected to AEMO. Aemo have identified the issue and rectifying the issue at ther end. | Delayed waiting for new participant IDs to be set up by AEMO in pre-prod. |  |  | Select Solutions has successfully completed BPT Cycle 1 (internal test activity) and we are on track to participate in Industry Testing Cycle 2 activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | End to end transaction testing undertaken, volume testing planned |  | Testing with market systems is underway. |  |  |  |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Integrated Cutover Runsheet development. Workaround processes being identified. B2M and B2B treatments being documented |  | Working with ITCFG. Cutover planning is due to commence. |  | Dependent on internal and market planning activities and decisions. Transitional plan option being considered introduces uncertainty and additional complexity. |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | First trial conversion successfully completed. Further trial conversions planned. DRs planned and Data cleaning activity scheduled. Draft CutOver Runsheet developed. |  | Not yet due. |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional and ring-fencing requirements. Discussions and clarification with regulators.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. Transition plan needs to be finalised quickly and clearly for all parties. |  |  | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified and decisions made to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Working through differences and Retailer assumptions of MC services.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for enhancing current systems and processes.
4.3 |  | The validation of business processes during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned in cycle 2 and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule.
5.5 |  | The validation of performance of market systems during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned in cycle 2 and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG & CPWG member. |  |  | Select Solutions is on track to complete our project transition, deployment and business readiness detailed planning by end of September, enabling implementation throughout Oct-Dec.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [12 empty] | Select Solutions is on track to complete detailed cutover planning by end of September, in readiness for dress rehersals and cutover in Nov-Dec.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Metering Coordinator Reports
Metering Coordinator (MC) Readiness Assessment Reports - see Distributors Report tab for initial MC
| 2017-09-11 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending MCs. This is not a reflection of their registration status or a complete list of all intending Metering Coordinators. The list of Registered Metering Coordinators can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Participant_Information/NEM-Registration-and-Exemption-List.xls
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Active Stream | Within schedule | Low | 1. AEMO Package 3 received 4/9/2017 - Assessment of the final package 3 is underway to ensure any amendments to systems and processes are undertaken prior to PoC 2. Ensuring any changes driven by the DNSP Transition Approach to Cut-Over (AEMO Exec Forum - 28 August) is incorporated into the Active Stream transition and cut-over plans. 3.DNSP Meter lock issues still to be resolved to allow contestible metering providers access to metering installations. 4. Confirmation still required from AEMO that all DNSPs, when called out for faults/emergencies will bypass meters that are identified as faulty, to allow retailers the opportunity to raise service orders for meter exchanges with their contestible metering provider.
| Acumen Metering | At risk | Medium | Current period - Amber status remains within a tight schedule. Work progresses with development of changes and testing whilst concurrently aligning with AEMO and participants as we move towards Cycle 2 and defining the business, people and cutover impacts. Coordinating time and input across multiple parties for bilateral and commercial agreements remains challenging for all and resolution of development and system issues arising following testing and increasing understanding of cutover and transition adds to thecomplexity. All three applications submitted (MP/MDP/MC). Currently providing clarification for MDP queries. Ongoing monitoring and mitigation of challenges is being sustained and confidence of readiness for go-live remains.
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in test. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts are being executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development.
| intelliHUB Pty Ltd | Within schedule | Medium
| Metering Dynamics | Within schedule | Medium | Revised project delivery plan progressing well. Jurisdictional differences continue to contribute to slow progress on MC commercial arrangements. Transitional plan option being considered introduces uncertainty and additional workload. AEMO delays in setting up new participant IDs has impacted testing. | [7 empty] | Complex commercial arrangements.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Powermetric Metering Pty Ltd | At risk | Medium | Powermetric MDP, MPB & MC overall POC system and business process development is on schedule however, the aggressive POC implementation, industry testing and MC Registration timeframes place Powermetric POC development at a Medium risk.
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | The summary project status and risk rating relate to the activities as Metering Coordinator. Select Solutions overall PoC strategy is to continue to run its existing systems for our Type 1-4 large meters and MP/MDP participant IDs with supporting enhancements to existing systems to form part of our accreditation for MC Services. There are currently no substantial risks or issues impacting our existing Type 1-4 Large MP and MDP accreditations. Select Solutions system development, testing and business readiness activities are progressing to plan in readiness for 1 December 2017 Go Live. Project risks predominantly relate to the substantial volume of commercial updates to be undertaken (scoped, negotiated and executed) prior to 1 December 2017. | [7 empty] | Risk relates to the remaining timeframe to complete updated commercial arrangements by 1 Dec 2017.
| Spotless Advanced Metering | Within schedule | Low | [8 empty] | Application for Registration as a MC submitted to AEMO
| VECTORAMS | Within schedule | Medium | Scope of change and tight timeframes to deliver IT changes and establsih commercial arrangements result in a project risk rating of Medium.
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Active Stream | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Acumen Metering | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| intelliHUB Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Metering Dynamics | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| Powermetric Metering Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
| Spotless Advanced Metering | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
| VECTORAMS | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low
0
0
0
0
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | 81% - 90% | 81% - 99% | Completed (100%) | Completed (100%) | 81% - 90% | 71% - 80% | 51% - 60% | Completed (100%) | Completed (100%) | 81% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 90% | 71% - 80% | 81% - 99% | Completed (100%) | 81% - 90% | 51% - 60% | 61% - 70% | Completed (100%) | Completed (100%) | 81% - 99%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | 61% - 70% | Completed (100%) | Completed (100%) | 71% - 80% | 71% - 80% | 11% - 20% | Completed (100%) | 81% - 90% | 71% - 80%
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 91% - 99% | 71% - 80% | 41% - 50% | 81% - 99% | 41% - 50% | 71% - 80% | 11% - 20% | Completed (100%) | 81% - 90% | 71% - 80%
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 71% - 80% | 31% - 40% | 61% - 70% | 81% - 99% | 31% - 40% | 51% - 60% | 11% - 20% | 51% - 60% | 81% - 90% | 51% - 60%
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | 91% - 99% | 81% - 99% | Completed (100%) | 81% - 99% | 81% - 90% | 71% - 80% | 71% - 80% | Completed (100%) | Completed (100%) | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 91% - 99% | 71% - 80% | 51% - 60% | 81% - 99% | 71% - 80% | 51% - 60% | 11% - 20% | 81% - 90% | 91% - 99% | 61% - 70%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 81% - 90% | 61% - 70% | 61% - 70% | Completed (100%) | 71% - 80% | 71% - 80% | 41% - 50% | Completed (100%) | 71% - 80% | 61% - 70%
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | 61% - 70% | 31% - 40% | Completed (100%) | 51% - 60% | 71% - 80% | 21% - 30% | 71% - 80% | 71% - 80% | 41% - 50%
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 41% - 50% | 11% - 20% | 21% - 30% | Completed (100%) | 21% - 30% | 41% - 50% | Not started (0%) | 31% - 40% | 81% - 90% | 21% - 30%
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 91% - 99% | 71% - 80% | 81% - 99% | 81% - 99% | 71% - 80% | 51% - 60% | 41% - 50% | Completed (100%) | 81% - 99% | 71% - 80%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 81% - 90% | 61% - 70% | 41% - 50% | 81% - 99% | 41% - 50% | 51% - 60% | 21% - 30% | 81% - 90% | 81% - 99% | 61% - 70%
4.3 |  | The validation of business processes during industry testing | [5 empty] | 11% - 20% | 31% - 40% | 21% - 30% | 71% - 80% | 11% - 20% | 21% - 30% | Not started (0%) | 21% - 30% | Not started (0%) | 11% - 20%
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 81% - 90% | 61% - 70% | Completed (100%) | 81% - 99% | 61% - 70% | 61% - 70% | 21% - 30% | Completed (100%) | 81% - 99% | 61% - 70%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 90% | 41% - 50% | 81% - 99% | 71% - 80% | 51% - 60% | 51% - 60% | 1% - 10% | 81% - 90% | 81% - 90% | 61% - 70%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 81% - 90% | 21% - 30% | 31% - 40% | 81% - 99% | 31% - 40% | 11% - 20% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 51% - 60% | 11% - 20% | 21% - 30% | 51% - 60% | 21% - 30% | 11% - 20% | Not started (0%) | 1% - 10% | Not started (0%) | 11% - 20%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 11% - 20% | 1% - 10% | 21% - 30% | 51% - 60% | Not started (0%) | 11% - 20% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 51% - 60% | 11% - 20% | 51% - 60% | 51% - 60% | 31% - 40% | 61% - 70% | Not started (0%) | 21% - 30% | 51% - 60% | 21% - 30%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 1% - 10% | Not started (0%) | Not started (0%) | 51% - 60% | Not started (0%) | 61% - 70% | Not started (0%) | Not started (0%) | Not started (0%) | Not started (0%)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Within schedule | Within schedule | Completed | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | At risk | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Completed | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | At risk | Within schedule | Completed | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Completed | Within schedule | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Within schedule | At risk | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Completed | Within schedule | Within schedule
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Within schedule | At risk | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.3 |  | The internal testing of market systems for your business | [5 empty] | Within schedule | Within schedule | At risk | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Assessment being undertaken against the Final AEMO package 3 outcomes |  | MC supporting documents arising from MC Application submission complete.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Optionality plans to accommodate 1 step (CR6800) or 2 step (CR6300/CR6800) approaches undertaken to ensure compliance |  | Working with ITCFG to understand impacts before completing planning |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Working with legal and regulatory to ensure contracts, process and systems comply across jurisdictions |  | Final reviews completed.
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Active Stream internal policies updated to reflect any variations in PoC and jurisdictional requirements |  | In progress. Will not be finalised until design and early prototypes of user systems are available. |  | Continuing uncertainty and changes in jurisdictional rules and interpretation of ring-fencing guideline requirements.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Continuing to engage with key stakeholders and counterparties for PoC contract development with Deemed contracts being developed as a safety net |  | Reviews in progress. This is a significant logistical effort to negotiate agrements with each prospective party. |  | Complexity of contractual and commercial arrangements is challenging. Transitional plan option being considered introduces uncertainty and additional workload. | Metering Coordinator contractual arrangements being finalised with several major retailers. |  | Select Solutions is continuing to work through the review and update to a large volume of indivdual I&C customer contracts in readiness for 1 December commencement of MC services and PoC changes. Commercial activities include the addition of new services, transactions, fees and charges, each to be individually negotiated and agreed. There is a risk that protracted negiotiation timeframes will impact arranagements for POC Go Live on 1 December 2017. This has been registered as part of our Risk Management framework and a risk treatment plan is currently being worked through to ensure readiness for 01/12.
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Already achieved MC registration for 1/12. Currently finalising MP and MDP reaccreditation - on track. eHub accreditation testing, planned for execution in Market Trials, cycle 2 |  | In hand.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | MC Accreditation obtained. MDP and MP accreditation on track |  | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. |  |  | Metering Coordinator registration application submitted to AEMO. |  | MC Registration (and all supporting documentation) has been submitted to AEMO and is currently under review.
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Active Stream resourcing requirements for project deployment and ongoing BAU have been determined - monitor and update for remainder of project |  | Awaiting final updates to policies and work instructions. |  | Corporate restructuring and ring fencing requirements continue to impact HR plan.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Active Stream resourcing requirements for project deployment and ongoing BAU have been determined - monitor and update for remainder of project |  | Relies on the above. |  | Impacted by recent merger and restructuring activity. |  |  | On Track to recruit additional MC resources as required to support Industry Transition and Go Live activities.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Work now commenced to review and amend operational Work Instructions and QRGs, prior to undertaking training execution closer to PoC go-live |  | Relies on the above. |  | Due to change in key system components, flow on effect to training development and delivery timing. | Training to be developed inline with industry testing. |  | Change Management and Training Activities in progress.
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Now that the Final Package 3 has been received this is currently under review |  | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  | Jurisdictional differences and variation in Retailer expectations of MC are resulting in more complex processes.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Any changes that come from the review will determine the need for any further changes or documentation |  | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  | The volume of documents requiring approval and system integrator changes have delayed this work. |  |  | We are on track to complete documentation updates as part of project activities.
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 1 completed and partial scope executed. Currently on track within available schedule, but this item does depend on external parties (generally retailers) to drive the progress and completion |  | Cycle 1 Industry Testing successful. |  |  | Industry testing not completed. |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Detailed assessment undertaken and incorporated into system requirements and design. This will be assessed and monitored through testing, trial conversions and dress rehearsals |  | All solution designs are complete.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | Finalising systems before systems freeze and code lock-downs |  | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Change in systems approach has delayed progress in build activities. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.3 |  | The internal testing of market systems for your business | [5 empty] | PoC system/SIT/UAT testing underway |  | Testing is underway. 15 testers are working across all solution components. Cycle 1 of Industry testing has completed successfully. |  | Delays to systems build has impacted availability for testing. |  |  | We are on track to validate market systems changes as part of eHub Accreditation and Industry Testing activities.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Bilateral testing undertaken, Market trials underway eHub accreditation testing, planned for execution in Market Trials, cycle 2 |  | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. One issue related to SSL Certificate validation with AEMO remains. | intelliHUB has significant problems getting web service API connected to AEMO. Aemo have identified the issue and rectifying the issue at ther end. | Delayed waiting for new participant IDs to be set up by AEMO in pre-prod. |  |  | Select Solutions has successfully completed BPT Cycle 1 (internal test activity) and we are on track to participate in Industry Testing Cycle 2 activities as planned.
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | End to end transaction testing undertaken, volume testing planned |  | Testing with market systems is underway. |  |  |  |  | There are some risks associated with transaction and process implementations that may not be compatible between some participants. There is only a short period to address these issues during the Industry Testing phases.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Integrated Cutover Runsheet development. Workaround processes being identified. B2M and B2B treatments being documented |  | Working with ITCFG. Cutover planning is due to commence. |  | Dependent on internal and market planning activities and decisions. Transitional plan option being considered introduces uncertainty and additional complexity. |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | First trial conversion successfully completed. Further trial conversions planned. DRs planned and Data cleaning activity scheduled. Draft CutOver Runsheet developed. |  | Not yet due. |  |  |  |  | A High Level Transition Plan has been developed. A detailed plan will be developed to support the Industry Transition timeframe.
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Active Stream | Acumen Metering | Ausgrid Business Services | intelliHUB Pty Ltd | Metering Dynamics | Metropolis Metering Services Pty Ltd | Powermetric Metering Pty Ltd | Select Solutions (EASTENMP, GLOBALM, EASTENMC) | Spotless Advanced Metering | VECTORAMS | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [7 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [9 empty] | Further reviews of jurisdictional and ring-fencing requirements. Discussions and clarification with regulators.
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [9 empty] | Continuing analysis of commercial requirements between parties. Transition plan needs to be finalised quickly and clearly for all parties. |  |  | Contract amendments have been drafted, issued and a significant customer engagement activity is currently underway. Commercial activities are progressing to plan and are also being closely monitored in our governance framework as a key project risk.
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [9 empty] | Key assumptions being identified and decisions made to allow progress.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [9 empty] | Work progressing, additional staff being recruited.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [9 empty] | Working through differences and Retailer assumptions of MC services.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [9 empty] | Revised plan now in place for enhancing current systems and processes.
4.3 |  | The validation of business processes during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned in cycle 2 and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [7 empty] | All available resources have been assigned to the design & development tasks. |  | Additional resources being secured to bring back on schedule.
5.3 |  | The internal testing of market systems for your business | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule.
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [9 empty] | Test plans updated to progress available systems and replanning for revised schedule.
5.5 |  | The validation of performance of market systems during industry testing | [12 empty] | We are on track to participate in Industry Testing activities as planned in cycle 2 and will also be engaging additional parties for Bilaterial Testing with our industry customers and peers.
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [7 empty] | Member on ITCFG |  | Focus on key deliverables for transition and cutover. ITCFG & CPWG member. |  |  | Select Solutions is on track to complete our project transition, deployment and business readiness detailed planning by end of September, enabling implementation throughout Oct-Dec.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [12 empty] | Select Solutions is on track to complete detailed cutover planning by end of September, in readiness for dress rehersals and cutover in Nov-Dec.
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Embedded Networks
Embedded Network Manager (ENM) Readiness Assessment Reports
| 2017-09-11 |  |  | Please note that the below organisations are voluntarily self-reporting readiness as intending ENMs. This is not a reflection of their accreditation status or a complete list of all intending Embedded Network Managers. The list of Accredited Embedded Networks Managers can be found here:
http://www.aemo.com.au/-/media/Files/Electricity/NEM/Retail_and_Metering/Metering-Procedures/National-Electricity-Market-Accredited-Embedded-Network-Managers.pdf
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Ausgrid Business Services | At risk | Medium | The ICT and business projects are in test. A number of significant IT rebuilds were required in order to facilitate the new B2B, CATS and new minimum specification requirements. Test scripts are being executed internally and bilaterally to supplement Industry Testing. New interfaces for the customer to assist our customers in operating in the POC space with the first phase release continuing in UAT. Further enhancements are in development.
| Energy & Plant Management Pty Limited | Within schedule | Low | Preparing for accreditation. Attended Pre-Application Meeting 4/8/17 ENM Accreditation Application Forms submitted 7/8/17 Waiting for MarketNet Connection
| Energy Intelligence | Within schedule | Low | Waiting on preproduction. EI is close to completion of Application.
| Metropolis Metering Services Pty Ltd | Within schedule | Low | Metropolis has allocated July-November 2017 to complete systems enhancements and testing activities with a particular focus on Service Order, CSDN and Metering Data processes, with supporting MSATS Metering Coordinator transactions and change request processes.
| Momentum Energy | At risk | Medium | Material risks are related to probable issues with development and implementation of system changes within given timeframes. There are dependencies on external vendors to develop required changes and merge codes for B2B and B2M market transactions. There is also a lack of clarity from AEMO in terms of how the Victorian Distributors role will evolve related to MC. Also critical dependencies on external providers of MC role to meet their POC timeframes.
| Network Energy Services | Within schedule | Low | Submitted accreditation application | [7 empty] | Getting prepared to implement all aspects
| Watts Energy Pty Ltd | Within schedule | Low | Submitted accreditation application forms and progressing checklist requirements. | [7 empty] | Assuming amendments to Qld Electricity Act will pass in coming weeks
| WINConnect Pty LTD | At risk | Medium | [8 empty] | Currently addressing proposed implementation of scheme in Victoria.
| Choice Metering | Within schedule | Medium | Site management system near completion. ENM Policies and Procedures are to be developed, not commenced as yet. ISO9001 Accreditation process to commence early Oct17. Require information about updating MSATS, will dicuss at AEMO meeting 22Sep17 | [13 empty] | This is first report from Choice Metering
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
| Ausgrid Business Services | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Energy & Plant Management Pty Limited | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Energy Intelligence |  |  | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Metropolis Metering Services Pty Ltd | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium | At risk | Medium
| Momentum Energy |  |  | At risk | Medium | At risk | Medium | At risk | Medium |  |  | At risk | Medium
| Network Energy Services | Within schedule | Low | Within schedule | Low | Within schedule | Low | Within schedule | Low |  |  | Within schedule | Low
| Watts Energy Pty Ltd |  |  |  |  | Within schedule | Low
| WINConnect Pty LTD | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium | Not within schedule | Medium |  |  | Not within schedule | Medium
| Choice Metering | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium | Within schedule | Medium
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Energy Intelligence | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | Choice Metering | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | 61% - 70% | 91% - 99% | 71% - 80% | 71% - 80% | 100% | Completed (100%) | Completed (100%) | 91% - 99%
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | 21% - 30% | 91% - 99% | 51% - 60% | 71% - 80% | 100% | 81% - 90% | 71% - 80% | 41% - 50%
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed (100%) | 21% - 30% | Completed (100%) | 71% - 80% | 71% - 80% | 100% | 91% - 99% | 41% - 50% | Not started (0%)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 41% - 50% | 21% - 30% | 91% - 99% | 71% - 80% | 41% - 50% | 100% | 81% - 90% | 11% - 20% | Not started (0%)
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | 61% - 70% | 41% - 50% | 91% - 99% | 51% - 60% | 41% - 50% | 50% | 61% - 70% | 41% - 50% | Not started (0%)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | 61% - 70% | 91% - 99% | 71% - 80% | 71% - 80% | 100% | 91% - 99% | 71% - 80% | Completed (100%)
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | 51% - 60% | 1% - 10% | 91% - 99% | 51% - 60% | 61% - 70% | 75% | 61% - 70% | 71% - 80% | 41% - 50%
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | 81% - 99% | Completed (100%) | 71% - 80% | 61% - 70% | 100% | 71% - 80% | 71% - 80% | Not started (0%)
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | 61% - 70% | Completed (100%) | 71% - 80% | 61% - 70% | 100% | 71% - 80% | Completed (100%) | Not started (0%)
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | 21% - 30% | 41% - 50% | 91% - 99% | 41% - 50% | 41% - 50% | 75% | 41% - 50% | Completed (100%) | Not started (0%)
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 99% | 71% - 80% | Completed (100%) | 51% - 60% | 41% - 50% | 100% | 81% - 90% | 41% - 50% | 41% - 50%
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 41% - 50% | 11% - 20% | Completed (100%) | 51% - 60% | 41% - 50% | 100% | 81% - 90% | 51% - 60% | Not started (0%)
4.3 |  | The validation of business processes during industry testing | [5 empty] | 21% - 30% | 1% - 10% | 91% - 99% | 21% - 30% | 31% - 40% | 50% | 1% - 10% | Completed (100%) | Not started (0%)
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | 51% - 60% | 81% - 90% | 61% - 70% | 61% - 70% | 90% | 41% - 50% | 61% - 70% | 41% - 50%
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 81% - 99% | 41% - 50% | 81% - 90% | 51% - 60% | 51% - 60% | 75% | 41% - 50% | 61% - 70% | 41% - 50%
5.3 |  | The internal testing of market systems for your business | [5 empty] | 31% - 40% | 1% - 10% | Not started (0%) | 11% - 20% | 61% - 70% | 75% | 1% - 10% | Not started (0%) | 41% - 50%
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 21% - 30% | Not started (0%) | Not started (0%) | 11% - 20% | 61% - 70% | 100% | 1% - 10% | Not started (0%) | 31% - 40%
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 21% - 30% | 1% - 10% | Not started (0%) | 11% - 20% | 51% - 60% | 75% | Not started (0%) | Not started (0%) | Not started (0%)
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 51% - 60% | 41% - 50% | 61% - 70% | 61% - 70% | 31% - 40% | 90% | 41% - 50% | Not started (0%) | 31% - 40%
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not started (0%) | 11% - 20% | 61% - 70% | 61% - 70% | 1% - 10% | 75% | 1% - 10% | Not started (0%) | N/A
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Energy Intelligence | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | Choice Metering | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Completed
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Completed | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Not within schedule | Within schedule
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Completed
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | Within schedule
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Within schedule | Within schedule | Completed | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule
4.3 |  | The validation of business processes during industry testing | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | Not within schedule | Within schedule | Within schedule | Within schedule | Within schedule
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | Within schedule | At risk
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | At risk | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | Within schedule | At risk
5.3 |  | The internal testing of market systems for your business | [5 empty] | At risk | Within schedule | Not within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | At risk
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Within schedule | Within schedule | Not within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Within schedule | Within schedule | Not within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | Within schedule
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Within schedule | Within schedule | Within schedule | Within schedule | At risk | Within schedule | Within schedule | At risk | N/A
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Energy Intelligence | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | Choice Metering | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | MC supporting documents arising from MC Application submission complete.
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Working with ITCFG to understand impacts before completing planning |  |  | Implemetation plans to be revised in line with industry testing results.
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | Final reviews completed. |  |  |  | Retailer timeframes to assess and agree to the T&Cs of the LNSPs are extremely tight and require the same pool of resources needed for establishing contractual agreements with Metering Coordinators and Embedded Network Owners
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety) | [5 empty] | In progress. Will not be finalised until design and early prototypes of user systems are available. |  |  |  | Severe challenges with the level of effort required to translate system and process changes into business operational readiness
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | Reviews in progress. This is a significant logistical effort to negotiate agrements with each prospective party. |  |  | Metering Coordinator contractual arrangements being finalised with several major retailers. | Dependency on partnering with registered MC(s)
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | In hand. |  |  |  | Submission has been followed by initial response from AEMO and Momentum is working consistently towards resolving the highlighted gaps.
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | ABS acknowledges that a significant effort is required to produce all required procedures in a timely manner. Supporting documentation for registration of new role ENM is underway. |  |  | Metering Coordinator registration application submitted to AEMO. | Volume of information required following initial assessment is higher than expected
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | Awaiting final updates to policies and work instructions.
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | Relies on the above.
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business | [5 empty] | Relies on the above. |  |  | Training to be developed inline with industry testing. | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing |  |  |  | Need assistance with training for the use of MSATS browser, will request at next AEMO meeting 22Sep17
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation. | [6 empty] | Subject to confirmation on options in Victoria.
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | Policies, priocedures and work instructions have been idenitfied and are in update/generation. |  |  |  | Concerns regarding dependencies with external vendors, implementation of system changes and participation in industry testing
4.3 |  | The validation of business processes during industry testing | [5 empty] | Cycle 1 Industry Testing successful. |  |  | Industry testing not completed. | Delays from third parties are impacting our ability to participate in industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | All solution designs are complete. |  | Waiting on access to MSAT preproduction to determine if there are additional changes.
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | The implementation phase is nearing completion with final build tasks being completed in line with the testing schedule. |  | Waiting on access to MSAT preproduction to finalise process |  | System development is reliant on external vendors, any delays in final market procedures will impact readiness activities. |  |  |  | It is thought MSATS browser can be used for ENM NMI market updates, as qty of transactions is expected to be low. Communication with participants will be via email
5.3 |  | The internal testing of market systems for your business | [5 empty] | Testing is underway. 15 testers are working across all solution components. Cycle 1 of Industry testing has completed successfully. |  | Waiting on access to MSAT preproduction |  | The late delivery of our B2B code by the external provider doesn't allow enough time for internal testing
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | Configuration of the AEMO links to connect Ausgrid's file based and SMP gateways is complete. One issue related to SSL Certificate validation with AEMO remains. |  | Waiting on access to MSAT preproduction
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | Testing with market systems is underway. |  | Waiting on access to MSAT preproduction
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Working with ITCFG. Cutover planning is due to commence. |  |  |  | Transition plans are dependent on timely delivery of earlier program stages |  |  | Initial feedback from AEMO indicates a transitional approach to dealing with lagacy data in MSATS.
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | Not yet due. |  |  |  | Draft version of internal Momentum Transition and Cut Over Plan in progress
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | Ausgrid Business Services | Energy & Plant Management Pty Limited | Energy Intelligence | Metropolis Metering Services Pty Ltd | Momentum Energy | Network Energy Services | Watts Energy Pty Ltd | WINConnect Pty LTD | Choice Metering | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | Member on ITCFG
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | All available resources have been assigned to the design & development tasks.
5.3 |  | The internal testing of market systems for your business | [7 empty] | Once preproduction is available, we can test/amend/finalise/approve processes
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [7 empty] | Once preproduction is available, we can test this
5.5 |  | The validation of performance of market systems during industry testing | [7 empty] | Once preproduction is available, we can action this
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | Member on ITCFG
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## Third Party
| 2017-09-11 |  |  | Third Party Readiness Assessment Reports
| Organisation | Project status | Project risk rating | Overall project comment | [7 empty] | Participant & jurisdiction specific comment/s | [5 empty] | General notes
| Organisation | ACT |  | NSW |  | QLD |  | SA |  | TAS |  | VIC
|  | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk | Status | Risk
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%)
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Traffic Light Status
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Explanation of variance/Notes
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Mitigating actions
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate)
2.2 |  | The development, documentation and approval of updated internal policies that are consistent with jurisdictional regulations and requirements (e.g. safety)
2.3 |  | Amendments to all relevant contracts/commercial arrangements
2.4 |  | An assessment of the required accreditation and registration activities
2.5 |  | The fulfilment of accreditation and registration obligations
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business
3.3 |  | The identification, development and delivery of staff training to fulfil the operational functions/roles, as applicable to your business
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business
4.2 |  | The development, documentation and approval of appropriate business processes for your business
4.3 |  | The validation of business processes during industry testing
5. Market systems
5.1 | Market systems | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes
5.2 |  | The development and build of appropriate market systems for your business
5.3 |  | The internal testing of market systems for your business
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate)
5.5 |  | The validation of performance of market systems during industry testing
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals)
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
41% - 50%
51% - 60%
61% - 70%
71% - 80%
81% - 90%
91% - 99%
Completed (100%)
N/A
81% - 99%
Within schedule
At risk
Not within schedule
N/A
Completed
Low
Medium
High
N/A

## AEMO
AEMO Readiness Assessment Report
B. Overall project status
| A. Details | [6 empty] | Project status | Project risk rating | Comment
| Date | 2017-09-11 | [5 empty] | Within schedule | Medium | Executive Forum voted in favour of industry adopting a staged approach to transition to de-risk customer experiences whilst adopting new market arrangements. Key activities requiring industry input include: • Scenario development as part of contingency planning • Feedback and finalisation of the Industry Transition and Cut-over plan • The commencement of Cycle 2 of Market trials • Promptly lodging any registration and/or accreditation applications. The first MC registration has been completed, more are underway. Intending MC’s are entering into cycle 2 of market trials.
| Organisation | AEMO
C. Jurisdictional status
# | Organisation | ACT | NSW | QLD | SA | TAS | VIC | Status | Risk | Comment
1 | AEMO | √ | √ | √ | √ | √ | √ | Within schedule | Medium | NSW: Staged approach to transition impacts on jurisdictional legislation being analysed. VIC: Order-in-Council has been circulated for any final feedback (not formal consultation
2
3
4
5
6
D. Detailed status
# | Category | Criteria: What is your progress towards completing… | [5 empty] | Progress (%) | Traffic light status | Explanation of variance/Notes | Mitigating actions
1. Assessment and preparation
1.1 | Assessment and preparation | A high-level impact assessment of the POC reforms on your business | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.2 |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date | [5 empty] | 81% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
1.3 |  | Delivery of the Market Readiness Strategy and associated plans | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2. Legal, regulatory, contractual and policy
2.1 | Legal, regulatory, contractual and policy | A detailed assessment of the revised legal and regulatory framework (including any jurisdictional safety requirements, as appropriate) | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.2 |  | The development, documentation and approval of updated internal policies consistent with regulatory changes including jurisdictional regulations and requirements (e.g. safety) | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.3 |  | Amendments to all relevant contracts/commercial arrangements | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.4 |  | An assessment of the required accreditation and registration activities | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.5 |  | The fulfilment of accreditation and registration obligations | [5 empty] | N/A | N/A |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.6 |  | The publication of updated AEMO retail electricity market procedures and associated documentation | [5 empty] | Completed (100%) | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
2.7 |  | The publication of updated B2B retail electricity market procedures and associated documentation | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3. People
3.1 | People | A detailed assessment of the human resources required to fulfil the operational functions for your business | [5 empty] | 61% - 70% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.2 |  | The recruitment/assignment of human resources required to fulfil the operational functions for your business | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
3.3 |  | The development and delivery of training to staff in operational roles | [5 empty] | 71% - 80% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4. Business processes
4.1 | Business processes | A detailed assessment of business process impacts for your business | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.2 |  | The development, documentation and approval of appropriate business processes for your business | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.3 |  | The validation of business processes during industry testing | [5 empty] | 21% - 30% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
4.4 |  | The delivery of POC information sessions to participants | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5. Market systems
5.1 | Market systems - MSATS (EN/MC) | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | Completed (100%) | Completed |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.2 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.3 |  | The internal testing of market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.4 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.5 |  | The validation of performance of market systems during industry testing | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.6 | Market systems - B2B e-hub and MSATS | A detailed assessment of the market system impacts for your business, including requirements specification and design of changes | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.7 |  | The development and build of appropriate market systems for your business | [5 empty] | 91% - 99% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.8 |  | The internal testing of market systems for your business | [5 empty] | 81% - 90% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.9 |  | The testing of market system interfaces between AEMO and participants (including testing of credentials and connectivity, as appropriate) | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
5.1 |  | The validation of performance of market systems during industry testing | [5 empty] | 31% - 40% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6. Transition planning
6.1 | Transition planning | The preparation of a transition and cutover plan(s) for your business | [5 empty] | 51% - 60% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
6.2 |  | The successful completion of prerequisite transition activities (e.g. data migration and conversions, cutover dress rehearsals) | [5 empty] | 1% - 10% | Within schedule |  |  |  |  | POC implementation plans in place to prepare your business for compliance with the revised regulatory arrangements from the “go live” date
7. General notes
Not started (0%)
1% - 10%
11% - 20%
21% - 30%
31% - 40%
[12 empty] | 41% - 50% | Retailer
[12 empty] | 51% - 60% | Distributor
[12 empty] | 61% - 70% | Meter Provider
[12 empty] | 71% - 80% | Meter Data Provider
[12 empty] | 81% - 90% | Metering Coordinator
[12 empty] | 91% - 99% | Embedded Network Manager
[12 empty] | Completed (100%) | Embedded Network Operator
[12 empty] | N/A | Third Party B2B Participant
81% - 99%
Within schedule
At risk
Not within schedule
N/A
[12 empty] | Completed | √
x
Low
Medium
High
N/A

## Harvey Balls 10% (hidden)
ü
Completed
| 100 | 90 | 80 | 70 |  | 60 | 50 | 40 | 30 | 20 | 10 | 0
| 0 | 10 | 20 | 30 |  | 40 | 50 | 60 | 70 | 80 | 90 | 100
WITHIN SCHEDULE | [12 empty] | Risks | Low
Medium
High
AT RISK
NOT WITHIN SCHEDULE
|  |  | ~0% |  | ~50%
|  |  | ~10% |  | ~60%
|  |  | ~20% |  | ~70%
|  |  | ~30% |  | ~80%
|  |  | ~40% |  | ~90%