## Details
COMMISSIONING TEST PLAN | [7 empty] | USER INSTRUCTIONS
FACILITY DETAILS
[8 empty] | 1 | This spreadsheet must be completed and submitted to Market Operations to be regarded as a valid request for a Commissioning Test Plan for a Facility.
Market Participant: | GRIFFIN2
[8 empty] | 2 | Data entry is restricted to the areas shaded yellow and green (yellow being mandatory), which have built-in automatic checks to validate entered data.
Facility: | BW2_BLUEWATERS_G1
[8 empty] | 3 | The following fields are mandatory: Market Participant, Facility, Email Address, Start and End Trading Days, Purpose of Test and Test Description. The Commissioning Test Plan will not be accepted by System Management unless these fields are completed.
Contact Details: |  | Operational |  |  | Commercial
| Email | Todd.Shepherdson@bluewatersps.com.au |  |  | Andrew.Stevens@bluewatersps.com.au
| Mobile | 0407196708 |  |  | 0434607542 |  |  | 4 | For Commissioning Tests exceeding one Trading Day, please make copies of the 'DDMMYYYY' worksheet. The worksheet will automatically rename when entering the Trading Day of test within the Details worksheet.
| Phone | 97796202 |  |  | 92612835
| Fax | 97796236 |  |  | 92612880
[8 empty] | 5 | Details within the 'DDMMYYYY' worksheet (Commissioning Test Schedule) are also mandatory and required in order for the Commissioning Test Plan to be accepted by System Management.
Fuel Types: | Fuel "1" |  |  | Fuel "2" |  | Fuel "3"
| Coal | [6 empty] | 6 | Separate Commissioning Test Plan templates are required to be completed for each Facility registered in the Wholesale Electricity Market.
TEST DETAILS | [7 empty] | 7 | Please email all completed Commissioning Test Plan templates to Market Operations; market.operations@westernpower.com.au
Associated Outage No: | 210038 | [7 empty] | Commissioning Test Plan template v1.0
| START |  |  |  | END
Commissioning Test Period: | Trading Day |  | Trading Interval |  | Trading Day |  | Trading Interval
| 2014-10-27 |  | 8:00 |  | 2014-11-01 |  | 7:30
Purpose of Test: | Unit commissioning and testing after annual statutory outage.
Test Description | Statutory and functionality testing of safety systems
System Under Test: | Turbine and Boiler.
Contingency Plan: | Nil.

## 27102014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-10-27 | 8:00
2014-10-27 | 8:30
2014-10-27 | 9:00
2014-10-27 | 9:30
2014-10-27 | 10:00
2014-10-27 | 10:30
2014-10-27 | 11:00
2014-10-27 | 11:30
2014-10-27 | 12:00
2014-10-27 | 12:30
2014-10-27 | 13:00
2014-10-27 | 13:30
2014-10-27 | 14:00
2014-10-27 | 14:30
2014-10-27 | 15:00
2014-10-27 | 15:30
2014-10-27 | 16:00
2014-10-27 | 16:30
2014-10-27 | 17:00
2014-10-27 | 17:30
2014-10-27 | 18:00 | 0
2014-10-27 | 18:30 | 0 | [5 empty] | Pre start checks on all
2014-10-27 | 19:00 | 0 | [5 empty] | Auxcillary euipment
2014-10-27 | 19:30 | 0
2014-10-27 | 20:00 | 0 | [5 empty] | Test draft system
2014-10-27 | 20:30 | 0
2014-10-27 | 21:00 | 0
2014-10-27 | 21:30 | 0
2014-10-27 | 22:00 | 0 | [5 empty] | All Permit return
2014-10-27 | 22:30 | 0
2014-10-27 | 23:00 | 0 | [5 empty] | De-isolating and
2014-10-27 | 23:30 | 0 | [5 empty] | preparing plant for service
2014-10-28 | 24:00 | 0
2014-10-28 | 24:30 | 0 | [5 empty] | Cooling water systems
2014-10-28 | 25:00 | 0 | [5 empty] | in service
2014-10-28 | 25:30 | 0
2014-10-28 | 26:00 | 0
2014-10-28 | 26:30 | 0
2014-10-28 | 27:00 | 0
2014-10-28 | 27:30 | 0
2014-10-28 | 28:00 | 0 | [5 empty] | integin
2014-10-28 | 28:30 | 0
2014-10-28 | 29:00 | 0 | [5 empty] | Start draft system
2014-10-28 | 29:30 | 0
2014-10-28 | 30:00 | 0 |  | Diesel | medium |  |  | Lite boiler
2014-10-28 | 30:30 | 0 |  | Diesel | medium
2014-10-28 | 31:00 | 0 |  | Diesel | medium
2014-10-28 | 31:30 | 0 |  | Diesel | medium |  |  | Raise temperature and pressure
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## 28102014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-10-28 | 8:00 | 0 |  | Diesel | medium
2014-10-28 | 8:30 | 0 |  | Diesel | medium
2014-10-28 | 9:00 | 0 |  | Diesel | medium
2014-10-28 | 9:30 | 0 |  | Diesel | medium |  |  | Test fire ignitors
2014-10-28 | 10:00 | 0 |  | Diesel | medium |  |  | Check flame scanners
2014-10-28 | 10:30 | 0 |  | Diesel | medium
2014-10-28 | 11:00 | 0 |  | Diesel | medium
2014-10-28 | 11:30 | 0 |  | Diesel | medium
2014-10-28 | 12:00 | 0 |  | Diesel | medium
2014-10-28 | 12:30 | 0 |  | Diesel | medium
2014-10-28 | 13:00 | 0 |  | Diesel | medium |  |  | Ongoing Inspections of
2014-10-28 | 13:30 | 0 |  | Diesel | medium |  |  | Boiler
2014-10-28 | 14:00 | 0 |  | Diesel | medium |  |  | Condensate/feedwater
2014-10-28 | 14:30 | 0 |  | Diesel | medium
2014-10-28 | 15:00 | 0 |  | Diesel | medium
2014-10-28 | 15:30 | 0 |  | Diesel | medium
2014-10-28 | 16:00 | 0 |  | Diesel | medium |  |  | Tightness Test
2014-10-28 | 16:30 | 0 |  | Diesel | medium
2014-10-28 | 17:00 | 0 |  | Diesel | medium
2014-10-28 | 17:30 | 0 |  | Diesel | medium |  |  | Roll Turbine
2014-10-28 | 18:00 | 0 |  | Diesel | medium
2014-10-28 | 18:30 | 0 |  | Diesel | medium
2014-10-28 | 19:00 | 0 |  | Diesel | medium
2014-10-28 | 19:30 | 0 |  | Diesel | medium
2014-10-28 | 20:00 | 0 |  | Diesel | medium
2014-10-28 | 20:30 | 0 |  | Diesel | medium
2014-10-28 | 21:00 | 0 |  | Diesel | medium
2014-10-28 | 21:30 | 0 |  | Diesel | medium
2014-10-28 | 22:00 | 5 |  | Diesel | medium |  |  | Synchronise
2014-10-28 | 22:30 | 25 |  | Coal & Diesel | medium |  |  | 1st Mill In Service
2014-10-28 | 23:00 | 45 |  | Coal & Diesel | medium
2014-10-28 | 23:30 | 65 |  | Coal & Diesel | medium |  |  | 2nd Mill In Service
2014-10-29 | 24:00 | 85 |  | Coal & Diesel | medium
2014-10-29 | 24:30 | 104 |  | Coal & Diesel | medium
2014-10-29 | 25:00 | 104 |  | Coal & Diesel | medium |  |  | 3rd Mill In Service
2014-10-29 | 25:30 | 104 |  | Coal & Diesel | medium
2014-10-29 | 26:00 | 104 |  | Coal & Diesel | medium |  |  | High Pressure Turbine
2014-10-29 | 26:30 | 104 |  | Coal & Diesel | medium |  |  | Full Stroke Test of Main Stop
2014-10-29 | 27:00 | 120 |  | Coal & Diesel | medium |  |  | And Control Valves
2014-10-29 | 27:30 | 140 |  | Coal & Diesel | medium |  |  | Intermediate Pressure Turbine
2014-10-29 | 28:00 | 150 |  | Coal & Diesel | medium |  |  | Full Stroke Test of Intercept Stop
2014-10-29 | 28:30 | 150 |  | Coal & Diesel | medium |  |  | And Control Valves
2014-10-29 | 29:00 | 150 |  | Coal & Diesel | medium
2014-10-29 | 29:30 | 153.8 |  | Coal & Diesel | medium |  |  | Turbine Electronic Overspeed Test
2014-10-29 | 30:00 | 168.8 |  | Coal & Diesel | medium |  |  | Turbine Hardware Protection Test
2014-10-29 | 30:30 | 183.8 |  | Coal & Diesel | medium |  |  | Turbine Electronic Overspeed Test
2014-10-29 | 31:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine Hardware Protection Test
2014-10-29 | 31:30 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine Over Pressure Test
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## 29102014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-10-29 | 8:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 8:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 9:00 | 198.8 |  | Coal & Diesel | medium |  |  | Flame Scanner testing/tuning
2014-10-29 | 9:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 10:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 10:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 11:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 11:30 | 198.8 |  | Coal & Diesel | medium |  |  | Ongoing Inspections of
2014-10-29 | 12:00 | 198.8 |  | Coal & Diesel | medium |  |  | Boiler
2014-10-29 | 12:30 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-29 | 13:00 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-29 | 13:30 | 198.8 |  | Coal & Diesel | medium |  |  | Mills
2014-10-29 | 14:00 | 198.8 |  | Coal & Diesel | medium |  |  | Flyash
2014-10-29 | 14:30 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-29 | 15:00 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-29 | 15:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 16:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 16:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 17:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 17:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 18:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 18:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 19:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 19:30 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 20:00 | 198.8 |  | Coal & Diesel | medium |  |  | Boiler Feed Pump trip Tests
2014-10-29 | 20:30 | 198.8 |  | Coal & Diesel | medium |  |  | Test standby pump start up
2014-10-29 | 21:00 | 198.8 |  | Coal & Diesel | medium
2014-10-29 | 21:30 | 183.8 |  | Coal & Diesel | medium
2014-10-29 | 22:00 | 168.8 |  | Coal & Diesel | medium
2014-10-29 | 22:30 | 153.8 |  | Coal & Diesel | medium
2014-10-29 | 23:00 | 150 |  | Coal & Diesel | medium
2014-10-29 | 23:30 | 150 |  | Coal & Diesel | medium
2014-10-30 | 24:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 24:30 | 150 |  | Coal & Diesel | medium
2014-10-30 | 25:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 25:30 | 150 |  | Coal & Diesel | medium |  |  | High Pressure Heater Trip Tests
2014-10-30 | 26:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 26:30 | 150 |  | Coal & Diesel | medium
2014-10-30 | 27:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 27:30 | 150 |  | Coal & Diesel | medium
2014-10-30 | 28:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 28:30 | 150 |  | Coal & Diesel | medium
2014-10-30 | 29:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 29:30 | 153.8 |  | Coal & Diesel | medium
2014-10-30 | 30:00 | 168.8 |  | Coal & Diesel | medium
2014-10-30 | 30:30 | 183.8 |  | Coal & Diesel | medium
2014-10-30 | 31:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 31:30 | 198.8 |  | Coal & Diesel | medium
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## 30102014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-10-30 | 8:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 8:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 9:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 9:30 | 198.8 |  | Coal & Diesel | medium |  |  | Fabric Filter bag checks
2014-10-30 | 10:00 | 198.8 |  | Coal & Diesel | medium |  |  | Requires compartmets to be
2014-10-30 | 10:30 | 198.8 |  | Coal & Diesel | medium |  |  | isolated
2014-10-30 | 11:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 11:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 12:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 12:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 13:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 13:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 14:00 | 198.8 |  | Coal & Diesel | medium |  |  | Gas Air Heater Sector Plate
2014-10-30 | 14:30 | 198.8 |  | Coal & Diesel | medium |  |  | Set seal gaps
2014-10-30 | 15:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 15:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 16:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 16:30 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 17:00 | 198.8 |  | Coal & Diesel | medium |  |  | Ongoing Inspections of
2014-10-30 | 17:30 | 198.8 |  | Coal & Diesel | medium |  |  | Boiler
2014-10-30 | 18:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-30 | 18:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-30 | 19:00 | 198.8 |  | Coal & Diesel | medium |  |  | Mills
2014-10-30 | 19:30 | 198.8 |  | Coal & Diesel | medium |  |  | Flyash
2014-10-30 | 20:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-30 | 20:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-30 | 21:00 | 198.8 |  | Coal & Diesel | medium
2014-10-30 | 21:30 | 183.8 |  | Coal & Diesel | medium
2014-10-30 | 22:00 | 168.8 |  | Coal & Diesel | medium
2014-10-30 | 22:30 | 153.8 |  | Coal & Diesel | medium
2014-10-30 | 23:00 | 150 |  | Coal & Diesel | medium
2014-10-30 | 23:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 24:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 24:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 25:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 25:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 26:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 26:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 27:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 27:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 28:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 28:30 | 150 |  | Coal & Diesel | medium
2014-10-31 | 29:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 29:30 | 153.8 |  | Coal & Diesel | medium
2014-10-31 | 30:00 | 168.8 |  | Coal & Diesel | medium
2014-10-31 | 30:30 | 183.8 |  | Coal & Diesel | medium
2014-10-31 | 31:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 31:30 | 198.8 |  | Coal & Diesel | medium
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## 31102014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-10-31 | 8:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 8:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 9:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 9:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 10:00 | 198.8 |  | Coal & Diesel | medium |  |  | Mill performance testing
2014-10-31 | 10:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 11:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 11:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 12:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 12:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 13:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 13:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 14:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 14:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 15:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 15:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 16:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 16:30 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 17:00 | 198.8 |  | Coal & Diesel | medium |  |  | Ongoing Inspections of
2014-10-31 | 17:30 | 198.8 |  | Coal & Diesel | medium |  |  | Boiler
2014-10-31 | 18:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-31 | 18:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-31 | 19:00 | 198.8 |  | Coal & Diesel | medium |  |  | Mills
2014-10-31 | 19:30 | 198.8 |  | Coal & Diesel | medium |  |  | Flyash
2014-10-31 | 20:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-10-31 | 20:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-10-31 | 21:00 | 198.8 |  | Coal & Diesel | medium
2014-10-31 | 21:30 | 183.8 |  | Coal & Diesel | medium
2014-10-31 | 22:00 | 168.8 |  | Coal & Diesel | medium
2014-10-31 | 22:30 | 153.8 |  | Coal & Diesel | medium
2014-10-31 | 23:00 | 150 |  | Coal & Diesel | medium
2014-10-31 | 23:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 24:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 24:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 25:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 25:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 26:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 26:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 27:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 27:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 28:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 28:30 | 150 |  | Coal & Diesel | medium
2014-11-01 | 29:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 29:30 | 153.8 |  | Coal & Diesel | medium
2014-11-01 | 30:00 | 168.8 |  | Coal & Diesel | medium
2014-11-01 | 30:30 | 183.8 |  | Coal & Diesel | medium
2014-11-01 | 31:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 31:30 | 198.8 |  | Coal & Diesel | medium
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13

## 01112014
| COMMISSIONING TEST SCHEDULE | [7 empty] | COMMISSIONING TEST SCHEDULE PROFILES
(Make copy of sheet for additional Trading Days)
TIME |  | NET OUTPUT |  | FUEL MIX | TRIP RISK | SPECIFIC TESTS |  | COMMENTS
Date of test | Interval start time | Active Power (MW) | Reactive Power (MVAr) | Coal | Low, Medium or High | Technical Rule, Table A11.1 | Technical Rule, Table A11.2
2014-11-01 | 8:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 8:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 9:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 9:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 10:00 | 198.8 |  | Coal & Diesel | medium |  |  | Mill performance testing
2014-11-01 | 10:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 11:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 11:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 12:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 12:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 13:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 13:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 14:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 14:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 15:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 15:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 16:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 16:30 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 17:00 | 198.8 |  | Coal & Diesel | medium |  |  | Ongoing Inspections of
2014-11-01 | 17:30 | 198.8 |  | Coal & Diesel | medium |  |  | Boiler
2014-11-01 | 18:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-11-01 | 18:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-11-01 | 19:00 | 198.8 |  | Coal & Diesel | medium |  |  | Mills
2014-11-01 | 19:30 | 198.8 |  | Coal & Diesel | medium |  |  | Flyash
2014-11-01 | 20:00 | 198.8 |  | Coal & Diesel | medium |  |  | Turbine
2014-11-01 | 20:30 | 198.8 |  | Coal & Diesel | medium |  |  | Condensate/feedwater
2014-11-01 | 21:00 | 198.8 |  | Coal & Diesel | medium
2014-11-01 | 21:30 | 183.8 |  | Coal & Diesel | medium
2014-11-01 | 22:00 | 168.8 |  | Coal & Diesel | medium
2014-11-01 | 22:30 | 153.8 |  | Coal & Diesel | medium
2014-11-01 | 23:00 | 150 |  | Coal & Diesel | medium
2014-11-01 | 23:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 24:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 24:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 25:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 25:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 26:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 26:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 27:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 27:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 28:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 28:30 | 150 |  | Coal & Diesel | medium
2014-11-02 | 29:00 | 150 |  | Coal & Diesel | medium
2014-11-02 | 29:30 | 153.8 |  | Coal & Diesel | medium
2014-11-02 | 30:00 | 168.8 |  | Coal & Diesel | medium
2014-11-02 | 30:30 | 183.8 |  | Coal & Diesel | medium
2014-11-02 | 31:00 | 198.8 |  | Coal & Diesel | medium
2014-11-02 | 31:30 | 198.8 |  | Coal & Diesel | medium
| Start Date | End Date |  | Fuel Mix | Trip Risk | TR Table A11.1 | TR Table A11.2
| 2014-10-27 | 2014-11-01 |  | Coal | Low | C1 | S1
[5 empty] | Medium | C2A | S2
[5 empty] | High | C2B | S3
[6 empty] | C3A | S4
[6 empty] | C3B | S5
[6 empty] | C4 | S6
[6 empty] | C5 | S7
[6 empty] | C6 | S8
[6 empty] | C7 | S9
[6 empty] | C8 | S10
[6 empty] | C9 | S11
S12
S13