## Version control
National Energy Market
Regulatory Implementation Roadmap
Version | Date | Description
v1.0 | 2020-04-17 | First draft for review with industry and consumers at stakeholder forum of 21 April 2020.
v2.0 | 2020-05-06 | Second iteration, following further AEMO internal review and participant feedback. Presented to stakeholder forum on 8 May 2020, and published as part of market bodies prioritisation advice on 17 May 2020.
v3.0 - draft | 2020-08-04 | Next iteration, incorporating AEMC final determinations on WDR and 5MS/GS deferral, and other updates for presentation to stakeholder forum on 10 August 2020.
v3.0 - final | 2020-08-31 | Finalised version 3, incorporating outcomes following stakeholder engagement in August 2020, including some additional minor updates.

## Roadmap v3 - final
National Energy Market
Regulatory Implementation Roadmap |  |  |  | Key:
[5 empty] | Policy development/market design | [10 empty] | Rules development | [7 empty] | Procedure/guideline development
[5 empty] | Implementation - IT systems, processes | [10 empty] | Indicative IT implementation | [7 empty] | Engineering Implementation
|  |  |  | l | Committed Go-Live Date |  |  |  |  | p | Proposed Go-Live | [5 empty] | n | Indicative Go-Live |  |  |  |  | u | Estimated Go-Live | [6 empty] | p | Proposed Release date
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative | 2020 | [8 empty] | 2021 | [8 empty] | 2022 | [11 empty] | 2023 | [5 empty] | 2024 |  |  |  | 2025 |  |  |  | 2026
|  |  |  | Q1 |  | Q2 |  | Q3 |  | Q4 |  |  | Q1 |  |  | Q2 |  | Q3 | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4 |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement | [10 empty] | 5MS (IT platform) | l |  | 5MS (external) |  | l |  |  |  | GS (extern) |  |  | l | AEMC final determination - go-live 1 October 2021 (5MS), 1 May 2022 (GS)
Industry-wide | Consumer | Committed | Wholesale Demand Response Mechanism | [15 empty] | l | AEMC final determination - go live 24 October 2021
Retail | Consumer | Committed | Reducing Customer Switching Times | [15 empty] | l | Updated to align with 5MS go-live following stakeholder consultation in August 2020
Retail | Consumer | Committed | Metering Coordinator Planned Interruptions (MCPI) | [20 empty] | l | AEMC final determination - implementation by 30 March 2022
Retail | Operational | Committed | MSATS Standing Data Review | [19 empty] | v1 | l |  |  |  |  | v2 (small) |  |  | l | v1 aligned with MCPI implementation by 30 March 2022
Retail | Consumer | Committed | Electricity B2B changes | [16 empty] | l | v3.5 (business enhancements, schema changes) and v3.6 (Life support procedural and WDR B2B guide changes only)
Gas |  | Committed | Gas B2B changes (life support) | [16 empty] | l | IN003/20 (business enhancements, schema uplift)
Retail | Market | Proposed - Review | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | [17 empty] | n | AEMC recommended implementation 12 months after law and rule changes made
Retail | Consumer | Proposed - Review | Energy Consumer Data Right | [26 empty] | n | Implementation dictated by ACCC timings, assumed to be Q3 2022
Retail | Consumer | In progress | Updating the Regulatory Frameworks for Embedded Networks | [28 empty] | u | Implementation subject to the scope of the change
Retail | Market | Proposed - Review | Review of Competition in Metering | [28 empty] | u | (if required) |  |  |  |  | u | IT implementation likely but not yet clear, dependent on review outcomes
Wholesale | Reliability | Committed | Improving Transparency and Extending Duration of MT PASA | [5 empty] | l |  |  | p | Propose alternate go-live date for MT PASA based on covid-19 resource priorities and alignment with AEMO internal technology upgrade
Wholesale | Reliability | Proposed - Review | ST PASA - Replacement project and methodology update | [23 empty] | u | Estimated timing, subject to rule change process
Wholesale | Market | Proposed - Pending | Integrating Energy Storage Systems (ESS) | [15 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Synchronous Services Markets | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Reliability | In progress | Operating Reserve Market | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Fast Frequency Response Market Ancillary Services | [15 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Efficient management of system strength on the power system | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Capacity commitment mechanism for system security and reliability services | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Introduction of ramping services | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Rule change process co-ordinated with ESB initiatives. If Rule is made, IT implementation bundled with related ESB initiatives (where feasible)
Wholesale | Security | In progress | Primary Frequency Response Incentive Arrangements | [32 empty] | Indicative timing, subject to rule change process
Industry-wide | Security | Proposed - Review | System Strength Framework Review | [12 empty] | Indicative Execution Range: Legislation, Rules, Procedures, IT | [18 empty] | Indicative timing, dependent on review outcomes
Industry-wide | Security | Proposed - Review | Economy wide Cyber Security Strategy and Systems of National Security (Cth) | High Level Design | [8 empty] | Technical Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [15 empty] | Extended Exec Range | [5 empty] | Indicative timing, subject to Cth processes
ESB INITIATIVES WITH IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Market | Proposed - Review | Two-Sided Market - Intermediate
Industry-wide | Market | Proposed - Review | Ahead Market - Intermediate
Industry-wide | Security | Proposed - Review | System Security Services - Intermediate | High Level Design | [8 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Indicative Execution Range (ctd)
Industry-wide | Market | Proposed - Review | DER Integration - Intermediate
Industry-wide | Market | Proposed - Review | Coordination of Generation and Transmission Investment - Intermediate
Industry-wide | Reliability | Proposed - Review | Capacity Mechanisms - Long Term | High Level Design | [8 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Indicative Execution Range (ctd)
Industry-wide | Security | Proposed - Review | Thermal Generation Strategy - Long Term | High Level Design | [8 empty] | Market Design |  |  |  |  | Indicative Execution Range: Legislation, Rules, Procedures, IT | [17 empty] | Indicative Execution Range (ctd)
INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Wholesale | Security | Committed | Mandatory Primary Frequency Response |  |  |  | l | [10 empty] | Implementation timing shown is indicative and depends on individual generator circumstances, managed through the self-assessment process
Wholesale | Security | Committed | System Restart Services, Standards and Testing | [6 empty] | l | New guidelines apply to new contracts enacted after June 2021
Networks | Market | Committed | Guidelines to make the ISP Actionable | [5 empty] | l
Network |  | In progress | Network Planning and Access for Distributed Energy Resources | [18 empty] | Indicative Execution Range: Procedures, IT | [17 empty] | Indicative implementation only, subject to rule change process
Network |  | In progress | Allowing DNSPs to Charge for Exports to the Network | [18 empty] | Indicative Execution Range: Procedures, IT | [17 empty] | Indicative implementation only, subject to rule change process
Network |  | In progress | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | [18 empty] | Indicative Execution Range: Procedures, IT | [17 empty] | Indicative implementation only, subject to rule change process
ESB INITIATIVES WITH LIMITED IT SYSTEM IMPLEMENTATION IMPACTS
Industry-wide | Reliability | Committed | Reliability Measures - Interim | [5 empty] | l
Industry-wide | Market | In progress | Implementation of Renewable Energy Zones - Planning (Stage 1)
Wholesale | Security | Proposed - Pending | Visibility and Security of Dispatch (Stage 1) - Interim
Wholesale | Security | Proposed - Pending | Visibility and Security of Dispatch (Stage 2) - Interim | [18 empty] | Indicative, subject to determining the materiality of the issues
Networks | Market | Proposed - Pending | Minimum Mandatory DER Technical Standards - Interim | [8 empty] | p
Networks | Market | Proposed - Review | Cost Allocation Methodology - Inter-Regional Transmission - Interim
GAS INITIATIVES
Gas |  | Committed | DWGM simpler wholesale price | [29 empty] | l
Implemented as a single AEMO project
Gas |  | Committed | DWGM improvement to AMDQ regime | [28 empty] | l
Gas |  | In progress | Measures to Improve Transparency in the Gas Market | [11 empty] | p | Subject to agreement of Ministers and passage of legislation

## Schema changes v3 - final
National Electricity Market
Retail Go Live Roadmap |  |  |  | Key:
[5 empty] | Policy development/market design | [5 empty] | Rules development | [5 empty] | Procedure/guideline development
[5 empty] | Implementation - IT systems, processes | [5 empty] | Indicative IT implementation | [5 empty] | Engineering Implementation
|  |  |  | p | B2M/B2B Schema Release
Impacted Industry Sector | Primary Objective | Reform Status | Reform Initiative | 2020 |  |  |  |  | 2021 | [6 empty] | 2022 | [7 empty] | 2023
|  |  |  | Q1 |  | Q2 | Q3 | Q4 | Q1 |  | Q2 | Q3 | Q4 |  |  | Q1 |  | Q2 | Q3 |  | Q4 |  |  | Q1 | Q2 | Q3 | Q4
Schema Changes
***Note: Schema changes required 6 months before go-live (only applies to 5MS)
Industry-wide | Market | Committed | Five Minute Settlement (5MS) and Global Settlement | [6 empty] | p
Retail | Consumer | Committed | Reducing Customer Switching Times | [6 empty] | p
Retail | Operational | In progress | MSATS Standing Data Review (includes MCPI) | [13 empty] | p |  |  |  |  | p
Retail | Market | Proposed - Review | Regulatory Arrangements for Stand Alone Power Systems (SAPS - Priority 1) | [11 empty] | p | if required
`
Retail | Market | Proposed - Review | Energy Consumer Data Right | [16 empty] | p | if required
Retail | Market | In progress | Updating the Regulatory Frameworks for Embedded Networks | [18 empty] | p | if required
Retail | Market | Proposed - Review | Review of Competition in Metering | [18 empty] | p | if required |  |  |  |  | p | if required
Retail | Market | Proposed - Review | B2B changes | [10 empty] | p
Note: |  | AEMO notes schema releases in second half of 2022 are not aligned. Options for alignment will be explored once the scope and timing of initiatives have been firmed up.
No schema changes required for WDR

## Log of changes
Log of Changes
Roadmap Version | Date | Reform | Change
Version 3 - draft | 2020-08-04 | Wholesale Demand Mechanism | Updated go-live date to 24 October 2021 (as per Final Determination)
Version 3 - draft | 2020-08-04 | Five-minute settlement and global settlement | updated go-lives dates for three-month deferral to 1 October 2021 and 1 May 2022 respectively (as per Final Determination)
Version 3 - draft | 2020-08-04 | Metering Coordinator Planned Interruptions | Updated for AEMO standing data and procedural changes no later than 30 March 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | MSATS | Updated release date to 30 March 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | Energy Consumer Data Right | Updated for indicative go-live date of end of Q3 2022 (previously November 2021)
Version 3 - draft | 2020-08-04 | Cyber security reform | Updated timetable indicating potential for go-live Q4 2022 recognising priority of these reforms. There is however uncertainty around this program of work as reflected by the extended implementation phase out to end of 2024 (if required)
Version 3 - draft | 2020-08-04 | Electricity B2B changes and gas B2B changes | Included on roadmap
Version 3 - draft | 2020-08-04 | ST PASA replacement and methodology update | Included on roadmap
Version 3 - draft | 2020-08-04 | System services rule changes | These have been initiated by the AEMC and will be considered along side the AEMC’s system strength framework review, the primary frequency response incentives rule change, and the ESB’s post-2025 program
Version 3 - draft | 2020-08-04 | ESB Initiatives with IT System impacts | The indicative execution range has been shortened slightly, recognising intentions to have some aspects of these reforms in place by mid 2023. The roadmap has maintained an extended implementation phase out to mid 2026 for the longer term initiatives.
Version 3 - draft | 2020-08-04 | DER technical standards | Updated timeframes with proposed go live date of December 2020
Version 3 - draft | 2020-08-04 | AER’s guidelines for actionable ISP | Minor delay to indicative go live date to 21 August 2020
Version 3 - draft | 2020-08-04 | Implementation of REZs | Minor delay of 2 months with draft rules expected end of July 2020
Version 3 - draft | 2020-08-04 | Network Planning and Access for Distributed Energy Resources | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Allowing DNSPs to Charge for Exports to the Network | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Included on roadmap. Rule change initiated in July 2020
Version 3 - draft | 2020-08-04 | Making the ISP actionable | Removed - came into effect on 1 July 2020
Version 3 - draft | 2020-08-04 | Consumer Protection Review | Removed - completed as part of the retail competition review
Version 3 - draft | 2020-08-04 | Removal of Disincentives to Primary Frequency Response | Renamed Primary Frequency response Incentive arrangements
Version 3 - final | 2020-08-31 | Reducing Customer Switching Times | Changed the go-live date to 1 October 2021 (bundled with 5MS) following consultation process (short delay from July 2020 go-live date presented in version 3 draft on 10 August 2020). Updated status to committed.
Version 3 - final | 2020-08-31 | Wholesale Demand Response Mechanism | Updated status to committed. Final determination made 11 June 2020
Version 3 - final | 2020-08-31 | MSATS Standing Data Review | Updated status to committed.
Version 3 - final | 2020-08-31 | Reliability Measures - Interim | Updated timeframes in accordance with final rules that come into effect on 21 August 2020. Updated status to committed.
Version 3 - final | 2020-08-31 | Implementation of Renewable Energy Zones - Planning (Stage 1) | Updated name of reform to better reflect scope of the first stage of REZ implementation initiative. Updated status to In progress.
Version 3 - final | 2020-08-31 | Network Planning and Access for Distributed Energy Resources | Updated status to In progress as consultation has commenced
Version 3 - final | 2020-08-31 | Allowing DNSPs to Charge for Exports to the Network | Updated status to In progress as consultation has commenced
Version 3 - final | 2020-08-31 | Access, Pricing and Incentive Arrangements for Distributed Energy Resources | Updated status to In progress as consultation has commenced

## Definitions
Definitions and Instructions for Regulatory Implementation Roadmap
Heading / Term | Definition and Instructions
Impacted Industry Sector | Indicates the primary section of the industry that is impacted by the regulatory change. If two sections of industry are impacted, choose the primary section. If more that two sections are impacted, choose 'Industry-wide'. Wholesale = Generation, Wholesale Market and/or Contracting impacted by the rule change Networks = Transmission and Distribution networks impacted by the rule change Retail = Retailers, other contestable service providers and/or customers are primarily impacted by the rule change Industry-wide = More that two sections of the industry are impacted by the rule change
Reform Status | Committed = Final determination made; and/or implementation in progress In progress = Rule change in process e.g. consultation and draft determination stages Proposed - Pending = Rule change has been proposed but not yet initiated Proposed - Review = Review underway but outcomes (including potential rule changes) not yet confirmed Note: A reference to rule change may also include a law change; or a reference to a review process where the outcome will be a law or rule change
Go-live Date Status | Committed = Go-live date decided in final rule determination Proposed = Go-live date proposed in draft rule determination Indicative = An indicative go-live date has been suggested by the proponent or foreshadowed during review process Estimated = AEMO estimated go-live date (where no proposed timeline currently exists)
Implementation Status | Policy development / market design = early stage of the reform process i.e. prior to a rule change process commencing Rules development = a rule change process is in progress i.e. from rule change request submitted through to final rule determination Procedure/Guideline development = Procedural changes are in progress or required to implement the rule change Implementation - IT systems, processes implementation and engineering implementation
Key IT regulatory projects | Signficant implementation impact = Medium or major IT/system capex project required to implement the rule change by AEMO and/or industry Strategic reform initiatives = Initiatives identified by COAG Energy Council and/or Energy Security Board
Include on Roadmap? | Yes - Material (i.e. High or Medium impact) IT, system or engineering implementation project Yes - Strategic Reform e.g. COAG EC priority No - Not Material or Strategic No - Complete