## Slide 1: PROGRAM CONSULTATIVE FORUM Meeting pack
DATE: FRIDAY, 5 MAY 2017
TIME: 10.00 AM – 12.30 PM (AEST)
VENUE: AEMO OFFICES; MEL, SYD, ADE, BRI
TELECONFERENCE: DIAL IN: 1800 055 132; PIN: 34861978
CONTACT: poc@aemo.com.au

## Slide 2: Power of choice Program Update
AEMO Procedures
AEMO held a POC PWG meeting on 6th March 2017 - discussed WP3 (As built).
B2B Procedures
B2B-WG advised IEC of options in relation to an ‘as built’ consultation.
Systems
The SWG Focus Group released the draft SMP User Guide/Technical Guide on 24th April.
Readiness:
Held RWG on 4 April – reviewed second draft of Industry Accreditation and Registration Plan.
Transition & Cutover – industry feedback received on transition/cutover guiding principles and industry planning approach.
Accreditation & Registration - final version of Industry Accreditation & Registration Plan targeted for release on 28 April.

## Slide 3: AEMO Program Update – upcoming tasks
Program:
IEC meeting will be held on 8 May 2017
Next PoC Executive Forum will be held on 22 May 2017
AEMO Procedures (Work Package 3 “As built”):
AEMO will be releasing first stage of consultation for WP3 (As built) mid-May 2017.
B2B Procedures:
B2B-WG will support IEC outcomes.
Systems:
SWG meeting was held on 1st May – Review of SMP Guideline
AEMO continues to define and build market systems in preparation for Industry testing
B2M EN & MC MSATS patch will be deployed into Pre-Production on 22nd May for industry testing
Readiness:
Industry Testing – final drafts of the EN/MC Test Plan and Workbook to be released first week of May.
ITWG meeting was held on 28 April (webinar/teleconference only) and then followed by 12 May (AEMO’s MEL offices).
Next Readiness Participant Information Session will be on 9 May (overview of industry accreditation and registration processes)
Next RWG meeting will be 25 May.

## Slide 4
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview
High Level Program V5.2 – 21 April 2017
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & B2B
Effective Date (Go-Live)
DNSPs & Retailers to publish amended standard contracts
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
B2B – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
B2B – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Transition & Cut Over Planning
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
B2B
Plan
Execute
Plan
Registration & Accreditation
Pre-Prod Release
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination
P
P
Industry Test Planning
Industry Test Execution
Transition

## Slide 5
2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 | 
JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Today
Power of Choice (PoC) Program Overview – Readiness Work Stream
High Level Program V5.2 – 21 April 2017
For Information: poc@aemo.com.au
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Industry Test Planning EN/MC
Industry Test Execution EN/MC
Accreditation & Registration
Transition & Cutover
Transition & Cutover Planning
P
Publish
Readiness reporting
Industry Testing
1 Dec
Go-live date
Mid-Nov
Final Industry Test Report
10 Apr
EN/MC changes in pre-production
06 Mar
B2B Procedures Published
28 Feb
WP2 Procedures Published
Industry Test Planning B2B/Market Trial
Industry Test Execution B2B
Connectivity/functionality testing
Planning
Accreditation and Registration Period
Market Trial Execution
Transition & Cutover
Post Go-Live
Heightened Support
2 Oct
Industry Transition & Cutover Plan Published
5 Jun
Industry Test Plan B2B Published
Readiness Reporting
5 Jun
10 Jul
7 Aug
11 Sep
9 Oct
6 Nov
4 Dec
8 May
3 Apr
6 Mar
8 Feb
Mid-Aug
B2B changes in pre-production
22 May
EN/MC patch release
Test Set-up
EN/MC

## Slide 6: Power of Choice Milestones
Deliverable / Milestone | Project / Stream | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 02 Dec 16 | 
AEMO commences consultation of Fee Methodology | All |  | Nov 16 | 03 Nov 16 | 
AER publishes ring fencing & network exemption guidelines | - |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All | No later than 4 January 2017 | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes Fee Methodology first stage consultation | All |  | 16 Dec 16 |  | 
AEMO concludes second stage consultation (WP 2) | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
IEC ‘recommends’ B2B Procedures to AEMO’s Board | B2B: All | TBC Preceding AEMO Feb Board | 22 Jan 17 | 20 Feb 17 | 
AEMO publishes Draft Fee Methodology | All |  | 06 Feb 17 | 23 Feb 17 | 
AEMO concludes second stage consultation Fee Methodology | All |  | 21 Feb 17 | 10 Mar 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
Commencement of registration / accreditation activities | Readiness | To be determined in readiness strategy | 01 Mar 17 |  | 
AEMO Publishes Final Determination Fee Methodology | All |  | 31 Mar 17 | 21 Apr 17 | 
Industry testing period detailed planning commences | Readiness |  | Mar 17 | Mid-Feb 17 | 
Industry detailed cut-over and transition planning commences | Readiness |  | Apr 17 | Mid -Mar 17 | 
Industry testing and trial period commences | Readiness | To be determined in test plan | Aug 17 |  | 
DNSPs publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
Industry Accreditation and Registration activities completed | Readiness |  | Oct 17 |  | 
Industry cut-over and transition plan completed | Readiness |  | Oct 17 |  | 
DNSPs publish distributor deemed standard connection contracts | MC |  | 1 Dec 17 |  | 
Retailers publish Elect & Gas standard retail contracts | MC |  | 1 Dec 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 
Notes: Intent to Publish

## Slide 7: PoC - Program Overview Version history
This table summarises the changes between the Program Overview as information changes or becomes available.
Version | Date | Amendments
3.6 | 10 May 16 | Expanded key milestone dates.
3.7 | 1 Jun 16 | Included proposed dates for testing periods (Aug 17 – Nov 17). Expanded on proposed fee methodology timetable to accommodate consultation process.
4.0 | 10 Jun 16 | Arranged Program Overview into key workstreams Removed IEC milestones in lieu of SMP Draft Determination
4.1 | 23 Jun 16 | Increased AEMO’s “design phase” to carry on until the end of consultation (1 Mar 17) Altered WP 1 Procedure Change Process dates to accommodate additional four business days of consultation.
4.2 | 19 Aug 16 | Updated tracking; removed dates associated with B2B Procedures as a result of B2B Framework Rule being published
4.3 | 02 Sep 16 | Updated B2B Procedure consultation with AEMO’s proposed dates (pending IEC approval)
4.4 | 10 Oct 16 | Updated terminology – added ‘6 month outlook’ for Procedure development / consultation processes Updated key dates in relation to AEMO WP2 Procedures and B2B Procedure development / consultation Included key dates identified in Readiness strategy
4.5 | 17 Nov 16 | Amended dates for Fee Methodology consultation Updated B2B Procedure Consultation dates
4.6 | 16 Dec 16 | Updated Tracking
4.7 | 21 Dec 16 | Updated Industry Testing and Transition and cut-over activities to commence earlier. Removed achieved milestones (Sep 15 – Nov 16)
4.8 | 25 Jan 17 | Updated Fee Methodology timetable in accordance with AEMO consultation
4.9 | 16 Feb 17 | Removed version control updates prior to 3.5 Removed Industry meeting dates from Program overview (refer to the industry calendar publishes on www.aemo.com.au) Included a draft Readiness overview slide
5.0 | 21 Mar 17 | Removed Procedures Work stream outlook. Updated ‘As Built’ package timeframes
5.1 | 6 Apr 17 | Updated Readiness Work Stream overview following RWG and ITWG (Apr 2017)
5.2 | 19 Apr 17 | Removed Industry Test dates and extended Market Trial dates
5.3 | 21 Apr 17 | \Amended the ‘As built’ consultation commencement to mid-May 2017

## Slide 8: Market readiness update
Market Readiness
April Industry Readiness Reports – received 34 participant reports. Market Readiness Reports can be found here Industry Readiness Reporting.
Accreditation and Registration:
  Final version of the Industry Accreditation and Registration published on 28 April.
  Participant Information Session – 9 May; overview of industry accreditation and registration processes.
Industry Testing:
  ITWG discussed final drafts of the EN/MC Industry Testing Plan and Test Workbook on 28 April.
  ITWG to discuss final draft the Industry Test Strategy and an initial draft of the B2B Industry Test Plan on 12 May.
Transition & Cutover:
  AEMO developing a schedule and plan for engaging with industry participants.
  AEMO will send further communications on next steps to RWG by 1st week of May.

## Slide 9
Next Meeting:
Friday 25 May 2017