## Slide 1: Power of choice executive forum
September 2016
Presented BY AEMO

## Slide 2: AEMO Program Update
General:
Program is on schedule with good industry engagement at the working groups and feedback provided through formal / informal channels.
Critical path is B2B working group -> B2B Procedures -> system changes -> testing.
Program:
Initial PCF meeting occurred on 16 Sep 16. ‘Kick-off’, follow-up meeting will occur on Friday 7th October.
Initial IEC meeting was conducted on Tuesday13 September
AEMO Procedures
Procedure consultation has now been completed and released.
  Any new information post consultation will be dealt with once raised and will feed into ‘as built’ consultation.
Initial industry discussion took place on work package 2 registration and accreditation procedures on Friday 9 September
B2B Procedures
B2B working group has been established and have completed providing inputs into the B2B Procedures.
Systems
AEMO undertaking initial system scoping, outcomes will feed initial industry engagement of changes/updates to systems.
Readiness:
Readiness strategy , version 1, has been completed
Readiness Reporting plan is being updated with participant input.

## Slide 3: AEMO Program Update – upcoming tasks
Program:
PCF risk and issue review – October 2016
Website updates – more information shared / structure update early October.
AEMO Procedures:
Work package 2: registration and accreditation procedures will commence formal consultation on October 10
B2B Procedures:
As requested by the B2B working group, AEMO is undertaking go to draft updated B2B Procedures for B2B working group review by end of September 2016.
B2B working group anticipates to have initiated formal consultation on 20 October 2016
Systems:
AEMO will establish the systems working group and hold the initial session in late October 2016
Readiness:
Readiness reporting trial run will occur in November 2016

## Slide 4
2015 |  |  |  |  |  |  | 2016 |  |  |  |  |  |  |  |  |  |  |  | 2017 |  |  |  |  |  |  |  |  |  |  |  | 2018 | 
JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB
Working Groups’
Today
Planned Transitional and New IEC Meetings
Power of Choice (PoC) Program Overview
High Level Program V4.3 – 02 September16
For Information: poc@aemo.com.au
26 Nov
MC
Final Determination
17 Dec
EN Final Determination
MRP Draft Determination
10 Mar
MRP
Final Determination
1 Sep
EN & MC & MRP
Procedures Published
1 Mar
MC
Registration & EN MSL and Accreditation Documentation Published
1 Dec
EN & MC & MRP & SMP
Effective Date (Go-Live)
EN = Embedded Network, MRP = Meter Replacement Processes
MC = Metering Competition, SMP = Shared Market Protocols
Oct
SMP Advice published
EN/MC/MRP WP 1 Procedure Consultation
EN/MC/MRP Package 2 Development
EN/MC/MRP WP 2
Procedure Consultation
For detailed meeting schedule and agendas, see the 2016 industry meeting schedule.
Package 3 ‘As Built’ Development
WP 3 & ‘As built’ Procedure Consultation (If required)
MC /
EN /
MRP
30 Jun
SMP Final Determination
1 Aug
IEC Election Procedures Finalised
MC B2B Recommendation
1 Sep
IEC Election Complete - IEC Formed
1 May
SMP – IEC recommends B2B Procedures Finalised
07 Apr
SMP Draft Determination
1 Dec
MC & EN Ring fencing and network exemption guidelines
1 Sep
DNSPs to publish standard terms and conditions on which it will act as the initial Metering Coordinator
AEMO Requirements
SMP Conceptual IT Designs
SMP B2B Procedure Consultation
TRANS IEC
IEC Election
Election Procedures
& Operating Manual
Fee methodology *(if required)
1 Jun
SMP – AEMO publish B2B Procedures & Accreditation Process
Heightened Support
Procedures
Market Readiness
Supporting Activities
IT Systems
P
P
P
P
Market Readiness Strategy
Industry Training
Industry Testing
Transition / Cut Over
AEMO Design
All - IT Development / Internal Testing
Industry Testing
P
P
SMP Procedure Development
P
EN/MC/MRP Package 1 Development
MC Draft Procedures
P
Publish
SMP
Plan
Execute
Plan
Execute
Plan
Execute
Registration & Accreditation
Pre-Prod Release
Trans
Trans
Prod Release
P
P
P
AER - Electricity ring-fencing guideline 2016
Readiness Reporting Commences
Milestone
Working group meeting
Proposed IEC Meetings (Trans & New)
Program Milestones
10 Sep
MRP Direction paper published
EN Draft Determination

## Slide 5: Power of Choice Milestones
Deliverable / Milestone | Project | Description | Planned date | Expected date | Status
AEMC publish MRP Directions paper & EN draft determination | EN, MRP |  | 10 Sep 15 |  | 
AEMC publish SMP advice paper | SMP |  | Early-Oct 15 | 10 Oct 15 | 
AEMC publish final rule determination | MC |  | 24 Nov 15 | 26 Nov 15 | 
AEMC release final determination | EN |  | 17 Dec 15 |  | 
AEMC release draft determination | MRP |  | 17 Dec 15 |  | 
AEMC publish draft rule determination | SMP |  | Early-Feb 16 | 07 Apr 16 | 
AEMC publish final rule determination | MRP |  | 10 Mar 16 |  | 
AEMO pre-consultation workshops conclude | MC,EN,MRP |  | 11 Mar 16 |  | 
AEMO releases Pre-Consultation Paper | MC,EN,MRP |  | 08 Apr 16 |  | 
AEMO publishes notice first stage consultation | MC,EN,MRP |  | 22 Apr 16 |  | 
AEMC publish final rule determination | SMP |  | 26 May 16 | 30 Jun 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 31 May 16 |  | 
AEMO begins Readiness Workstream engagement | MC,EN,MRP |  | 20 Jun 16 | 21 Jun 16 | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 30 Jun 16 | 29 Jun 16 | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 15 Jul 16 | 20 Jul 16 | 
AEMO publishes final procedure determination | MC,EN,MRP | No later than 1 Sep 16 | 26 Aug 16 | 31 Aug 16 | 
AEMO publishes notice first stage consultation (WP2) | MC,EN,MRP |  | 10 Oct 16 |  | 
AEMO publishes notice first stage consultation | B2B: All |  | 10 Oct 16 | 20 Oct 16 | 
IEC Election complete – IEC formed | SMP | Noting this is a no later than date. | 01 Sep 16 | 01 Sep 16 | 
AEMO concludes first stage consultation | MC,EN,MRP |  | 15 Nov 16 |  | 
Notes: Intent to Publish

## Slide 6: Power of Choice Milestones
Deliverable / Milestone | Project | Description | Planned date | Expected date | Status
AEMO concludes first stage consultation | B2B: All |  | 15 Nov 16 | 25 Nov 16 | 
AEMO commences development of Fee Methodology | SMP | If required | Nov 16 | Sep 16 | 
AER publishes ring fencing & network exemption guidelines | MC,EN |  | 01 Dec 16 |  | 
AEMO publish draft procedure determination | MC,EN,MRP |  | 13 Dec 16 |  | 
AEMO publish draft procedure determination | B2B: All |  | 13 Dec 16 | 23 Dec 16 | 
System implementation period commences | All |  | Mid Dec 16 |  | 
AEMO concludes second stage consultation | MC,EN,MRP |  | 30 Dec 16 | 16 Jan 17 | 
AEMO concludes second stage consultation | B2B: All |  | 30 Dec 16 | 20 Jan 17 | 
AEMO seeks IEC recommendation for B2B changes | B2B: All | TBC Preceding AMEO Feb Board | 22 Jan 17 | Late Feb 17 | 
AEMO publishes final procedure determination | MC,EN,MRP | Obligation is no later than 1 Mar 17 | 01 Mar 17 | 28 Feb 17 | 
AEMO publishes final procedure determination | B2B: All | Obligation is no later than 1 Jun 17 | 01 Mar 17 | 06 Mar 17 | 
AEMO publishes Fee Methodology (participant fee structure) | SMP | If required | 01 Mar 17 |  | 
AEMO commences readiness (registration/accreditation) | All | To be determined in readiness strategy | Mar 17 |  | 
Proposed commencement of industry testing | All | To be determined in test plan | Aug 17 |  | 
DNSPs to publish T&C’s on which it will act as the initial MC | MC |  | 1 Sep 17 |  | 
PoC Effective date | All |  | 1 Dec 17 |  | 
Notes: Intent to Publish

## Slide 7: AEMO Procedure update
AEMO has structured Embedded Networks and Metering Competition rule changes into three work packages, with NER consultation to be completed by the following timelines:
  1 September 2016 (Work Package 1)
    Metrology Procedures, MSATS Procedures, Service Level Procedures
  1 March 2017 (Work Package 2)
    Accreditation/Deregistration Procedures, Exemption Procedures, ENM Service Level Procedures
  1 December 2017 (Work Package 3)
    Jurisdictional metrology amendments, etc.

## Slide 8: Key dates / milestones
Work Package 1: AEMO published the final determination on 31 August 2016
Work Package 2: consultation timelines are detailed below
Work Package 3: consultation is scheduled to commence in July 2017
10 October 2016 | AEMO publishes Notice of First Stage Consultation
15 November 2016 | Submissions close for First Stage of Consultation
13 December 2016 | AEMO publishes Notice of Second Stage Consultation (Draft Report and Determination)
16 January 2017 | Submissions close for Second Stage of Consultation
28 February 2017 | AEMO publishes Final Report and Determination

## Slide 9: B2b Procedure update
Four key Procedures updates:
  Service Order Process
  Customer Site Details Notification
  Meter Data Process
  One Way Notification
Other documents
  Technical Specification
  Business Rules Guide
  Glossary update for B2B terminology
  ROLR Procedure Part B
Consultation process (subject to IEC approval)
  Procedure Consultation on Initial Draft procedures set to start on October 20
  Draft procedures published on 23 December
  Final procedures published on 6 March 2017
6 March 2017 Final B2B Procedures are set to be published
The B2B procedure stream will also assist in System testing and Market Readiness stream activities

## Slide 10: B2b Procedures update
Following 30 June 2016 release of the final rule, the IEC election and B2B working group was formed in July 2016 to complete the B2B procedure update.
12 members have been chosen including four from each Industry group Retailers, Distributors and Metering Providers.
B2B Working Group has now met 9 times since early August.
Upcoming events
  22 September - B2B Working Group Workshop to discuss Technical Delivery specification and outstanding matters
  27 September – B2B Working Group Workshop – Procedure Review.

## Slide 11: market readiness update
Readiness Working Group (RWG) established Jul-16 and has since met on two occasions
Market Readiness Strategy developed and finalised with the RWG
Industry Readiness Reporting Plan developed with the RWG (including reporting templates) and in near-final form
Participant Information Sessions scoping undertaken with the RWG prior to start of content development by AEMO

## Slide 12: Market readiness strategy
Market Readiness – Definition
Successful implementation of all activities by AEMO and NEM participants for a seamless transition to the new procedural arrangements starting 1 Dec 2017 (MC; MRP; EN; B2B)
Market Readiness Strategy – Overarching Document
Developed by AEMO in collaboration with industry (RWG)
Market Readiness Strategy – Purpose
Sets out a plan for managing, coordinating, informing, monitoring and reporting on AEMO and NEM participants’ operational preparedness for transition to 1 Dec 2017

## Slide 13: Market Readiness Strategy
Market Readiness Strategy – Inside Scope
Market readiness phases (develop/test market interfaces)
Stakeholder engagement activities (POC forums, enquiries)
Reporting and monitoring processes (reg. progress reports)
Participant Info’ Sessions (procedure changes, industry test)
Market Readiness Strategy – Outside Scope
Any consequential changes/testing required to support the changes made to market interfacing systems/processes
Other regulatory obligations (eg. new safety requirements)
RWG forum will discuss external dependencies / outside scope matters that impact participants’ operational preparedness

## Slide 14: Market readiness strategy
Market Readiness Strategy – Readiness Phases
Planning (develop Strategy, supporting plans, templates)
Industry Testing (develop supporting plan, testing, trial)
Accreditation and Registration (develop supporting plan)
Industry Transition and Cutover (develop supporting plan)
Confirmation of operational preparedness for go-live
Post go-live heightened support (bed-in ops ~3 months)

## Slide 15: Supporting plans
Industry Readiness Reporting Plan
Process, templates for progress reports (due Sep-16)
Accreditation and Registration Plan
Process, dates, acc/reg requirements, reports (due Mar-17)
Industry Testing Plan
Process, dates, pre-requ. activities, reports (due Jun-17)
Industry Transition and Cutover Plan
Process, dates, transition principles, support (due Oct-17)
Industry Risk and Issue Management Plan
Process for identifying, tracking, addressing risk/issues

## Slide 16: readiness progress reporting
Industry Readiness Reporting Plan
Sets out the readiness criteria that AEMO and participants will report against (traffic light and % progress reporting)
Reporting templates developed with RWG, covering:
  * assessment/preparation * legal/regulatory/contractual/policy * people * bus. processes * market systems * transition planning
Monthly readiness reporting from November 2016
Readiness Assessment Reports – Company-level reporting by NEM participants and AEMO (due mid-Nov)
Market Readiness Report – Industry-level aggregated reporting by AEMO (due late-Nov)
AEMO to publish all reports on its website

## Slide 17: Participant information sessions
Six participant info’ sessions to be presented by AEMO
AEMO is utilising the RWG to scope sessions (tailor content)
Face-to-face, ½ day, procedures change/obligations focus:
  Overview of POC key obligations (Oct-16)
  Detailed walk-throughs of POC key obligations:
    Comp. in metering, meter replace’t processes (Nov-16)
    Embedded networks (Apr-17)
    Electricity B2B framework / e-hub (Apr-17)
  Overview of accred’n and regist’n processes (Apr-17)
  Overview of industry testing processes (Jul-17)

## Slide 18: Upcoming readiness activities
Participant Information Session #1 to be presented by AEMO in mid-Oct
Monthly readiness reporting by NEM participants and AEMO starts mid-Nov; AEMO publishes reports late-Nov
RWG meeting in late-Nov
Participant Information Session #2 to be presented by AEMO in late-Nov