## Slide 1: POC Industry CUTOVER PLANNING
July 2017

## Slide 2: Industry Cutover planning
Cutover Objective;
Facilitate a coordinated industry cutover of market operations for AEMO and NEM participants and continued service delivery to NEM end‑use customers effective from “go‑live”.
Industry Cutover Period;
Systems cutover commences COB Friday, 1 December 2017 and ends 9am Monday, 4 December 2017

## Slide 3: Industry Cutover planning
Cutover Principles;
All participants and AEMO will adopt and follow the POC Industry Cutover plan.
NEM participants and AEMO are responsible for developing their own internal cutover plans. These plans should have regard to the key activities, dates, times, etc. set out in the Industry Cutover Plan.
Where possible and practicable to do so, minimise and effectively manage the number of in flight transactions during cutover activities.
The industry cutover approach will be based on a ‘fix-on-fail/roll-forward’ approach in which AEMO and all Participants will commit to cutting over and avoid rollback by addressing problems as and when they arise.
If participants have system issues during cutover they must notify AEMO and the market as soon as possible.
The Industry Cutover Plan will endeavour to limit jurisdictional differences for cutover activities where possible.

## Slide 4: Industry Cutover planning
Proposed Approach
Create an Industry Cutover Plan, in conjunction with ITCFG representatives identifying cutover tasks to build the overall plan,
  Record actual tasks, duration (start times) and responsibilities
  To be utilized to execute dress rehearsals as well as the actual Industry Cutover
  Review and identify any possible changes required to the cutover tasks
AEMO to provide a central point of industry cutover coordination
  Coordinated communication to participant cutover teams
  Provide industry cutover status, any issues during the cutover period
Conduct 2 cutover practice runs (Dress Rehearsals) prior to ‘Go-Live’ cutover weekend to validate the cutover plan (Dress Rehearsal dates TBC)
Modify the Cutover Plan based on inputs from Industry Testing and Dress Rehearsal findings
  Potential impacts to the overall timeline or tasks

## Slide 5: ITCFG - Industry Cutover planning
Out of Scope
Identifying, defining, developing or assessing POC Readiness or Readiness Criteria
  Any dependencies will be managed by the Readiness Working Group and will be completed by all participants prior to the commencement of cutover. If not met then there is an expectation participants will implement work arounds to manage transition and cutover activities.
Additional or modified Contingency Arrangements
  Contingency arrangements are defined in the B2B Technical Delivery Specifications or the relevant MSATS documentation. The Cutover plan will not detail additional contingency arrangements contrary to these procedures.