| Business to Market – MSATS General rules that apply to all CRs: - Need to consider if the CR is prospective or retrospective, for retrospective CRs raised at cutover if it has an actual change date/completion date that is before the cutover date then we do not need to do anything with those CRs. - For any CRs raised prior to the 1 December 2017 that have a current objection logging period of greater than 1 business day, at the time of MSATS’s CR processing on the 1 December 2017 those CRs will move to the next stage in their life cycle. VICAMI is still under consideration pending order of council expected to be released in May 2017. |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Item no | Process | Sub Process - Brief description of the current process | Cross ref notes to B2M or B2B transactions | Existing regulatory obligation for this process | State | Market roles impacted | Initial transition plan expectations | Pre-Shutdown activities | During Shutdown activities | Post go-live activities (Rules and Procedures apply) | Other Notes, including any “In flight” arrangements |
| 1 | Transfers | Change of Retailer resulting in the transfer of a NMI from one Retailer to another Retailer. | Change Requests 1000, 1010, 1020, 1030 & 1040 | MSATS Procedures: CATS Procedure Principles and Obligations. | NSW, SA, ACT, QLD, TAS, VIC | FRMP MDP MPB MPC MC | N/A | N/A | N/A | - Transfers with deleted read type codes (NI, NB) will be cancelled on 1 Dec 17 - Transfers assigning FRMP as the RP, or the LNSP as the RP for meters other than 5,6,7 with a proposed date on or after 1/12/17 will be cancelled on 1 Dec 17 - Transfers assigning MDP and MP roles where there is not a valid MC appointed for the NMI with a proposed date on or after 1/12/17 will be cancelled on 1 Dec 17. This is a consequence of the previous point. |  |
|  |  | Change of Retailer resulting from error corrections of small NMI transfers | Change Requests 1021, 1022, 1023, 1024, 1025, 1026, 1027, 1028, 1029 |  |  |  |  |  |  |  |  |
| 2 | Transfers | Change of Retailer where FRMP is not the RP | Change Requests 1050, 1051 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | FRMP MDP MPB MPC MC | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |  |
| 3 | Transfers | Change of Retailer resulting from the transfer of a Child NMI from one retailer to another retailer | Change Requests 1080, 1081, 1082, 1083, 1084 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | FRMP MDP MPB MPC MC | N/A | N/A | N/A | - Transfers with deleted read type codes (NI, NB) will be cancelled on 1 Dec 17 - Transfers assigning FRMP as the RP, or the LNSP as the RP for meters other than 5,6,7 with a proposed date on or after 1/12/17 will be cancelled on 1 Dec 17 - Transfers assigning MDP and MP roles where there is no valid MC appointed for the NMI with a proposed date on or after 1/12/17 will be cancelled on 1 Dec 17. This is a consequence of the previous point |  |
| 4 | Transfers | Change of Retailer for Child NMI where FRMP is not the RP | Change Requests 1090, 1091 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | FRMP MDP MPB MPC MC | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result any open CRs will be cancelled on 1 December 2017 |  |
| 5 | Provide Data | Provide Actual Change Date | Change Request 1500 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP FRMP MC | N/A | N/A | N/A | - On 1 Dec 17, when/if a CR 1500 is sent and the corresponding CR has been cancelled by AEMO as part of cutover activities the CR1500 will be rejected by the MSATS. |  |
| 6 | Create NMI | LNSP to create a NMI | Change Requests 2000, 2001 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP ROLR MC MPB MPC MDP FRMP | N/A | N/A | N/A | - 2000 change requests with an effective date proposed on or post 1 December 2017 and has invalid details for RP and hence it can have invalid details of MPB, MPC, and MDP will be cancelled on 1 Dec 17 for all jurisdictions other than Victoria. | Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 7 | Create NMI | LNSP to create a Tier 1 NMI | Change Request 2003 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP ROLR MC MPB MPC MDP FRMP | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result any open CRs will be cancelled on 1 December 2017 |  |
| 8 | Create NMI | ENM to create Child NMIs | Change Requests 2020 2021 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LR ROLR MC MPB MPC MDP FRMP ENM | N/A | N/A | N/A | - 2020 initiated by LR with proposed date on or after 1 Dec 17 will be cancelled on 1 Dec 17. - 2020 change request with proposed date on or post 1 December 2017 and has invalid details for RP and hence it can have invalid details of MPB, MPC, and MDP will be cancelled on 1 Dec 17 | Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 9 | Create NMI | LNSP to create NMI, metering installation details, and MDM data stream | Change requests 2500 2501 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP ROLR MC MPB MPC MDP FRMP | N/A | N/A | N/A | - 2500 change request with proposed date on or post 1 December 2017 and has invalid details for RP and hence it can have invalid details of MPB, MPC, and MDP will be cancelled on 1 Dec 17 - Change requests that do not have the MDM contributory suffix and/or Network Tariff Code provided where the proposed date is on or after 1/12/2017 will be cancelled on 1 Dec 2017 due to these fields being mandatory in these CRs post 1 Dec 17 The validation on these CRs will continue post 1dec 2017 and if the mandatory fields are not completed in the CR then the CR will be rejected. | Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 10 | Create NMI | ENM to create NMI, metering installation details, and MDM data stream details for Child NMIs | Change requests 2520 2521 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LR ROLR MC MPB MPC MDP FRMP ENM | N/A | N/A | N/A | - CR 2520 initiated by LR with proposed date on or after 1 Dec 17 will be cancelled on 1 Dec 17 - 2520 change request with proposed date on or after 1 December 2017 and has invalid details for RP and hence it can have invalid details of MPB, MPC, and MDP will be cancelled on 1 Dec 17 - Change requests that do not have the MDM contributory suffix and/or Network Tariff Code provided where the proposed date is on or after the 1/12/2017 will be cancelled on 1 Dec 2017 due to these fields being mandatory in these CRs post 1 Dec 17. The validation on these CRs will continue post 1dec 2017 and if the mandatory fields are not completed in the CR then the CR will be rejected. | Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 11 | Maintain Metering | Creating Metering Installation details Exchange of Metering Information | Change requests 3000 3001 3004 3005 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MPB | N/A | N/A | N/A | - 3000 and 3004 Change requests that do not have the MDM contributory suffix and/or Network Tariff Code provided where the proposed date is on or after the 1/12/2017 will be cancelled on 1 Dec 2017 due to these fields being mandatory in these CRs post 1 Dec 17 The validation on these CRs will continue post 1Dec 2017 and if the mandatory fields are not completed in the CR then the CR will be rejected. |  |
| 12 | Maintain Metering | Create tier 1 metering installation details | Change requests 3003 3053 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MPB | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |  |
| 13 | Maintain Metering | Change Metering Installation details | Change requests 3050 3051 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MPB | N/A | N/A | N/A | Post 1 Dec 2017 the mandatory fields of MDM Contributory suffix and Network Tariff Code need to exist for all current registers in MSATS. This means that on completion of these CR’s MSATS will perform validation to ensure these fields are already in MSATS or the CR. If these fields will be blank at the completion of these CR’s then the system will reject these CR’s. This will happen with any inflight CR’s when MSATS comes back on line and with any future CR’s raised after 1 Dec 2017. Two new error codes have been created where these fields are missing. They are 5059 - MDM Contributory Suffix is Mandatory And 5060 - Network Tariff Code is Mandatory |  |
| 14 | Maintain Metering | Advanced change metering installation details, and advanced exchange of metering | Change requests 3080 3081 3090 3091 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MC | N/A | N/A | N/A | - CR1500 is required for CRs 3080 & 3090 post 1 Dec 17, CRs will not complete until CR1500 is submitted. For inflight CR’s post 1 Dec 17 a CR1500 will be required for these to complete even though the relevant participant may not have received an RDAT. AEMO will run a report to provide to the MDP’s for them to send the CR1500 to complete any inflight CR’s post 1 Dec 2017. - Post 1 dec 2017 the mandatory fields of MDM Contributory suffix and Network Tariff Code need to exist for all current registers in MSATS. This means that on completion of these CR’s MSATS will perform validation to ensure these fields are already in MSATS or the CR. If these fields will be blank at the completion of these CR’s then the system will reject these CR’s. This will happen with any inflight CR’s when MSATS comes back on line and with any future CR’s raised after 1 Dec 2017. Two new error codes have been created where these fields are missing. They are 5059 - MDM Contributory Suffix is Mandatory And 5060 - Network Tariff Code is Mandatory |  |
| 15 | Maintain Metering | Change network tariff code | Change requests 3100 3101 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP ENM | N/A | N/A | N/A | N/A | No impact |
| 16 | Maintain data stream | Create MDM data stream | Change requests 4000 4001 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP | N/A | N/A | N/A | N/A | No impact |
| 17 | Maintain data stream | Exchange of data stream information | Change requests 4004 4005 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP | N/A | N/A | N/A | N/A | No impact |
| 18 | Maintain data stream | Create MDM data stream Exchange of data stream information | Change requests 4003 4053 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |  |
| 19 | Maintain data stream | Change NMI Data stream | Change requests 4050 4051 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP | N/A | N/A | N/A | N/A | No impact |
| 20 | Maintain NMI | Update Next Scheduled Read Date | Change requests 5070 5071 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | MDP | N/A | N/A | N/A | N/A | No impact |
| 21 | Maintain NMI | Backdate a NMI | Change requests 5001 5021 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP ENM | N/A | N/A | N/A | N/A | CR5021 can only be initiated by AEMO. These types of requests would not be processed by AEMO unless they will be in a completed status before cutover. Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 22 | Maintain NMI | Change a NMI | Change requests 5050 5051 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP | N/A | N/A | N/A | N/A | No impact |
| 23 | Maintain NMI | Change a 1st tier NMI Standing data | Change request 5053 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | LNSP | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017N/A |  |
| 24 | Maintain NMI | Change a NMI – customer classification code | Change requests 5054 5055 | MSATS Procedures: CATS Procedure Principles and Obligations. | ALL | FRMP | N/A | N/A | N/A | N/A | No impact |
| 25 | Maintain NMI | Change NMI embedded network (Child) | Change requests 5060 5061 | MSATS Procedures: CATS Procedure Principles | ALL | ENM LR | N/A | N/A | N/A | - CRs initiated by LR with proposed date on or after 1 Dec 17 will be cancelled on 1 Dec 17 |  |
| 26 | Maintain NMI | Change parent name | Change requests 5080 5081 | MSATS Procedures: CATS Procedure Principles | ALL | FRMP LNSP |  |  |  | - Post 1 Dec 2017 these CR’s can only be initiated by the LNSP so any CR’s where the effective date is post 1 Dec 2017 and were raised by the FRMP will need to be cancelled. |  |
| 27 | Maintain NMI | Make NMI a child NMI | Change requests 5090 5091 | MSATS Procedures: CATS Procedure Principles | ALL | LNSP | N/A | N/A | N/A | These CRs are disabled from 1 December 2017, as a result CRs will be cancelled on 1 December 2017 |  |
| 28 | Change Roles | Change LNSP | Change requests 6100 6110 | MSATS Procedures: CATS Procedure Principles | ALL | LNSP | N/A | N/A | N/A | N/A |  |
| 29 | Change Roles | Change MDP | Change requests 6200 6210 | MSATS Procedures: CATS Procedure Principles | ALL | FRMP MC MDP | N/A | N/A | N/A | - CR1500 is required for CR 6200 post 1 Dec 17, CR will not complete until CR1500 is submitted. For inflight CR post 1 Dec 17 a CR1500 will be required for this to complete even though the relevant participant may not have received an RDAT. AEMO will run a report to provide to the MDP’s for them to send the CR1500 to complete any inflight CR post 1 Dec 2017. |  |
| 30 | Change Roles | Change MC | Change requests 6300 6301 | MSATS Procedures: CATS Procedure Principles | ALL | MC MDP | N/A | N/A | N/A | Any change request with a proposed date on or after 1/12/17, will be cancelled as the MC roles will not be valid. |  |
| 31 | Change Roles | Change LR | Change requests 6400 6401 | MSATS Procedures: CATS Procedure Principles | ALL | LR | N/A | N/A | N/A | N/A | No impact |
| 32 | Change Roles | Change LR Child NMI | Change requests 6421 | MSATS Procedures: CATS Procedure Principles | ALL | LR | N/A | N/A | N/A | N/A | No impact |
| 33 | Change Roles | Change ROLR | Change requests 6500 6501 | MSATS Procedures: CATS Procedure Principles |  | ROLR | N/A | N/A | N/A | N/A | Ability for ROLR to object will be disabled from 1 December 2017 – AEMO believes no impact with this change |
| 34 | Change Roles | Change MPB, MPC, or Both | Change requests 6700 6701 | MSATS Procedures: CATS Procedure Principles | ALL | MC MDP | N/A | N/A | N/A | - CR1500 is required for CR 6700 post 1 Dec 17, CR will not complete until CR1500 is submitted. For inflight CR post 1 Dec 17 a CR1500 will be required for this to complete even though the relevant participant may not have received an RDAT. AEMO will run a report to provide to the MDP’s for them to send the CR1500 to complete any inflight CR post 1 Dec 2017. |  |
| 35 | Change Roles | Change Multiple Roles – MC, MDP, MPC, MPB | Change requests 6800 6801 | MSATS Procedures: CATS Procedure Principles | ALL | MC FRMP MDP | N/A | N/A | N/A | - CR1500 is required for CR 6800 post 1 Dec 17, CR will not complete until CR1500 is submitted. For inflight CR post 1 Dec 17 a CR1500 will be required for this to complete even though the relevant participant may not have received an RDAT. AEMO will run a report to provide to the MDP’s for them to send the CR1500 to complete any inflight CR post 1 Dec 2017. |  |
| 36 | Auto change roles | Change LR – Child NMI – Auto | Change Request ECLR | MSATS Procedures: CATS Procedure Principles |  |  | N/A | N/A | N/A | N/A | No Impact |
| 37 | Auto change roles | Change Secondary FRMP – Parent NMI | Change Request EFPR | MSATS Procedures: CATS Procedure Principles |  |  | N/A | N/A | N/A | N/A | No Impact |
| 38 | AEMO only | Standing data updates | Change requests 5100 5101 | MSATS Procedures: CATS Procedure Principles |  |  | N/A | N/A | N/A | N/A | No Impact |
| 39 | AEMO only | Invoke BCT for ROLR | Change requests ROLR | MSATS Procedures: CATS Procedure Principles |  |  | N/A | N/A | N/A | N/A | No Impact |
| 40 | AEMO only | Invoke BCT Process | Change requests BCxx | MSATS Procedures: CATS Procedure Principles |  |  | N/A | N/A | N/A | N/A | No Impact |

| Item no | Process | Sub Process - Brief description of the current process | Existing regulatory obligation for this process | State | Market roles impacted | Initial transition plan expectations | Pre-Shutdown activities | During Shutdown activities | Post go-live activities (Rules and Procedures apply) | Other Notes, including any specific procedural arrangements or obligations. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Re-Energisation Service Orders | After Disconnection for Non-Payment | B2B Procedures: Service Orders v2.2. | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements on the 1 Dec 2017 Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 May be a slight impact to SDQ data for LNSP NMIST. |
|  |  | Sticker Removal |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Retrospective Move In |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | New Reading Required |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Blank |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from current jurisdicational requirements on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 2 | De-energisation Service Orders | Pillar box, Pit or Pole Top | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 |
|  |  | Pillar Box, Pit or Pole Top (non-payment) |  |  |  | Service order has been received and acknowledged by DB. No raising or scheduling a DNP for the period from 23/11 to 1/12. This will reduce the amount of same day reconnections | No activity required as no new requests will be raised between 23/11/17 and 1/12/17. | Contingency not required as no new requests will be raised between 23/11/17 and 1/12/17. | BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Fuse |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Fuse (non-payment) |  |  |  | Service order has been received and acknowledged by DB. No raising or scheduling a DNP for the period from 23/11 to 1/12. This will reduce the amount of same day reconnections | No activity required as no new requests will be raised between 23/11/17 and 1/12/17. | Contingency not required as no new requests will be raised between 23/11/17 and 1/12/17. | BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Sticker |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Blank |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on the 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 3 | Adds & Alts Service Orders | Install Hot water | B2B Procedures: Service Orders v2.2. | SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required as no new requests will be raised between 1/11/17 and 1/12/17 for SA & ACT and 16/11/17 and 1/12/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 |
|  |  | Install Controlled Load |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required as no new requests will be raised between 1/11/17 and 1/12/17 for SA & ACT and 16/11/17 and 1/12/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Move Meter |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required as no new requests will be raised between 1/11/17 and 1/12/17 for SA & ACT and 16/11/17 and 1/12/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Install Meter |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11/17 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required as no new requests will be raised between 1/11/17 and 1/12/17 for SA & ACT and 16/11/17 and 1/12/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Remove Meter |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type after 1pm on 1 Dec 2017. No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Exchange Meter |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise this sub type later than 1/11/17 for SA & ACT and16/11 QLD & TAS No transition for VIC as assumption is that the VIC DB’s will continue to perform this service under the OIC. No transition in NSW as this service order type is not used. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required as no new requests will be raised between 1/11/17 and 1/12/17 for SA & ACT and 16/11/17 and 1/12/17 in QLD and TAS. | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation. BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 4 | Allocate NMI Service Order |  | B2B Procedures: Service Orders v2.2. | NSW, TAS | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise this service order after 1pm on 1 Dec 2017. | DB will process the service order as long as it has been received prior to the agreed stop initiating time. | Contingency not required On the 1/12 and if the NMI is still a greenfield site then a process will be performed to update the NMI with the correct MC, MDP and MP roles. | DB to send response. BAU processes to continue for macks & tacks. Report to be produced by the AEMO of greenfield NMI’s. DB’s to confirm that these NMI’s are still valid and require the roles to be changed to contestable service providers and MC. (see BCT section) BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 |
| 5 | New Connection Service Orders | Temporary |  | SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers. (refer to New Connection Section) Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and responded to via email to the email address in the RoCL, using the new connection templates in the plan. The templates will be based on requests and responses as per version 3.0 of the B2B Procedures. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/12/2017 then the NMI will follow the updating of roles process.(refer BCT section). Report to be produced by the AEMO of greenfield NMI’s. DB’s to confirm that these NMI’s are still valid and require the roles to be changed to contestable service providers and MC. (see BCT section) BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36 |
|  |  | Temporary in Permanent |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers.(refer to New Connection Section) Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and responded to via email to the email address in the RoCL, using the new connection templates in the plan. The templates will be based on requests and responses as per version 3.0 of the B2B Procedures.s. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/12/2017 then the NMI will follow the updating of roles process.(refer BCT section). Report to be produced by the AEMO of greenfield NMI’s. DB’s to confirm that these NMI’s are still valid and require the roles to be changed to contestable service providers and MC. (see BCT section) BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
|  |  | Permanent |  |  |  | Service order has been received and acknowledged by DB. Retailers not to raise new connection service orders later than 1/11/17 for regulated metering. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency processes. Juridictional: Regulated Metering; Each jurisdiction will have their own plan that has been agreed to by Retailers.(refer New Connection section) Non regulated or for new connections that Retailers know will definitely be scheduled to be performed after the 1/12/17; The service will be requested and responded to via email to the email address in the RoCL, using the new connection templates in the plan. The templates will be based on requests and responses as per version 3.0 of the B2B Procedures. | DB to send response. BAU processes to continue for macks & tacks. Any new connections that are inflight with the DB’s after the 1/12/17 and will not be metered and serviced before the 1/12/2017 then the NMI will follow the updating of roles process.(refer BCT section). Report to be produced by the AEMO of greenfield NMI’s. DB’s to confirm that these NMI’s are still valid and require the roles to be changed to contestable service providers and MC. (see BCT section) BAU to commence using new service order requests as per version 3.0 of the B2B Procedures. |  |
| 6 | Special Read Service Orders | Check Read | B2B Procedures: Service Orders v2.2. | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time . | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | Requests prior to 1 Dec, will be sent in R33 with any responses sent post 1 Dec in R36. |
|  |  | Final Read |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Blank |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. Tack’s and mack within normal timeframes as per tech guidleines. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency processes | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 7 | Meter Reconfiguration Service Orders | Change Controlled Load | B2B Procedures: Service Orders v2.2. | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Change Timeswitch |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Change Tariff |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 8 | Meter Investigation Service Orders | Tamper | B2B Procedures: Service Orders v2.2. | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017 | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Inspect |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017 | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Meter Test |  |  |  | Service order has been received and acknowledged by DB. Stop initiating transaction from 1pm on 1 Dec 2017 | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 9 | Supply Abolishment Service Order |  | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Retailers not to raise this sub type after 1pm on 1 Dec 2017 No transition for VIC | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 10 | Miscellaneous Service Order |  | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Service order has been received and acknowledged by DB. No raising from 24 Nov 2017. | DB will process the service order as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 11 | Customer and Site Details Notification | Customer Details Request | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Stop initiating transaction from 30 Nov 2017. | RB will process the CDR as long as it has been received prior to the agreed stop initiating time | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Customer Details Notification |  |  |  | Stop initiating transaction from 1pm on 1 Dec 2017 | DB will process the CDN as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation | Process of ringing and emailing life support will continue. |
|  |  | Customer Details Reconciliation |  |  |  | Run to your normal schedule. No reconciliations between 1/11/17 to 1/2/18 | N/A | N/A | N/A |  |
|  |  | Site Access Notification |  |  |  | Stop initiating transaction from 1pm on 1 Dec 2017. | DB will process the CDN as long as it has been received prior to the agreed stop initiating time | Contingency not required | DB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 12 | One Way Notification | Meter Exchange Notification | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP | Stop initiating transaction from 1pm on 1 Dec 2017. | RB will process the OWN as long as it has been received prior to the agreed stop initiating time | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
|  |  | Network Tariff Notification |  |  |  | Stop initiating transaction from 1pm 1 Dec 2017. | RB will process the OWN as long as it has been received prior to the agreed stop initiating time | Contingency not required | RB to send response. BAU processes to continue for macks & tacks. No follow up reconciliation |  |
| 13 | Meter Data Process | Provide Meter Request | B2B Procedures: Service Orders v2.2 | NSW, SA, ACT, QLD, TAS, VIC | FRMP DNSP MDP | Stop initiating transaction from 1pm 1 Dec 2017. | DB will process the PMD as long as it has been received prior to the agreed stop initiating time | Contingency not required | Recommencement be reviewed and revisited during cutover to determine how long it’s going to take for systems to be back on line, bct runs to be processed and backlog of meter data to processed. |  |
|  |  | Verify Meter Data Request |  |  |  | Stop initiating transaction from 1pm 1 Dec 2017. | DB will process the VMD as long as it has been received prior to the agreed stop initiating time If DB’s systems can’t carry over the request then transition will be for them to reject any open VMD’s using ‘invalid data’.using details with CUTOVER. Rejections of VMD’s can commence on the 29th Nov 2017 @ 11.59pm. | Contingency not required | Recommencement be reviewed and revisited during cutover to determine how long it’s going to take for systems to be back on line, bct runs to be processed and backlog of meter data to processed. | Where there is an inflight and the participant hasn’t received a rejection prior to batch handlers going down they should expect an accept or reject within the regulated timeframes. |
|  |  | Meter Data Notification |  |  |  | 5pm AEST on 1 Dec 2017 to align with MDM data. | RB will process the MDN as long as it has been received prior to the agreed stop initiating time | Contingency not required | Recommencement of data delivery will be as soon as all cutover activities have been completed and systems are implemented and live. | Week 20 R2 settlement is due to be run on 1 Dec 2017. |

| New Connection Process for each Jurisdiction. |  |
| --- | --- |
| Jurisdiction - Distributor | Process |
| South Aust - SAPN | - What is the cut off time for DNSP’s where service and metering can be guaranteed by the 1/1/18 for a New Connection? - SA Power Networks are not proposing any major cut off time with regards to receiving New Connection Service Orders - SA Power Networks propose that the final New Connection Service Order be sent at the close of business the day before cut over. - Retailers are reminded that the New Connection Service Order does not act as the trigger for any timing obligations to complete work in SA. Timing obligations start when all pre-requisites have been achieved (the receipt and acceptance of the New Connection Service Order being one of these) including direct contact with SA Power Networks by the REC (when they are ready for site connection) to make an agreed appointment time with SA Power Networks. - Retailers should note that the receiving and acceptance of any New Connection Service Orders by SA Power Networks any time prior to and up to this cut off time does not guarantee that all work associated with that New Connection being fully completed by SA Power Networks (e.g. SA Power Networks may have accepted the New Connection Service Order and determine that they can/will only provide infrastructure and service provision/energisation activities (up to the meter isolator) for some New Connections completed after 1 December 2017). - Where this is the case the Retailer will be required to organise their Metering Service Provider to install the relevant metering and complete the final site energisation tasks. - SA Power Networks are looking to be flexible with regards to the completion of open work at the time of cut over and are currently considering its position with regards to completing the installation of required metering. This may include installing SA Power Networks Type 5 or 6 metering after 1 December 2017. - SA Power Networks is not in a position at this stage to make a blanket rule with regards to metering (there are a number of factors that need to be considered in greater detail including obligations, metering and resource logistics and customer impacts) but intend to provide this level of detail to Retailers following an analysis of all open Connection related work within our systems. - SA Power Networks expect to be in a position to complete this comprehensive review of all open Connection related work (both New Connections and Additions & Alterations) during July and August 2017. - SA Power Networks will be in contact with the relevant Retailer to discuss and inform them of: - The broad plan and expected treatment of each open item raised by that Retailer. - SA Power Networks will aim to have this initial view for discussion by the end of August 2017 - SA Power Networks will ensure that we make it clear to the relevant Retailer no shorter than 1 month prior to any actual site related work needing to be completed (i.e. work schedule in our systems to be completed on 1 December 2017 will be visible by 1 November 2017) how each individual work item will be treated. - SA Power Networks are expecting that open and regular communication (not relying solo on the response to an open service order) will be required during the months prior and post 1 December 2017 to ensure the required coordination has been established to minimise customer impacts. - What will the process be for sites that have been created by the DNSPs but it is still a greenfield site and will not be metered and serviced by 1/1/18? Will they be made extinct and an Allocate NMI is to be raised with the new roles or will a process be put in place to change the roles upon instruction from the Retailer to update MSATS with the new roles? What is industry’s preferred process? - SA Power Networks expects that where possible, NMI’s already established within MSATS but not yet connected, but require role updates (MC, MPB, MDP) will be managed via MSATS Transaction rather than making the NMI extinct. We expect that this level of detail will be determined once we complete the analysis of all open Connection related work within our systems. |
| Queensland – Ergon & Energex | Scenario 1 - New Connection – Energex or Ergon Energy Network nominated as RP, MDP and MPB (install a Type 6) - New Connection Service Order Requests can be raised up until 1pm on the 23/11/2017 with no contingency mode thereafter. - New Connection Service Order Requests that will not able to be completed by the 30/11/2017, will be responded to with a “Not Completed” SO Response with an ExceptionCode of “Service Provider Cancellation” on the 28/11/2017. - New Connection Service Order Requests that were “Not Completed” will have their NMI’s abolished in MSATS, if a NMI was previously created. (Discussion was had around role changing instead of abolishing need to confirm with QLD whether they’re still going to abolish) Scenario 2 - New Connection – Energex or Ergon Energy Network not nominated as RP, MDP and MPB (install a Type 4) - New Connection Service Order Requests can be raised up until 1pm on the 30/11/2017 with no contingency mode thereafter. - New Connection Service Order Requests that will not able to be completed by the 30/11/2017, can live through the cutover. |
| ACT – ActewAGL | 1. What is the cut off time for DNSP’s where service and metering can be guaranteed by the 1/1/18 for a New Connection? It is AAD’s intention to stop taking orders for metering services approximately 4 weeks prior to 1 December 2017. In the ACT this ‘order’ is submitted using a Request for Service form – RFS (Note: site readiness date indicated by applicant must be < 1st December). 2. What will the process be for sites that have been created by the DNSPs but it is still a Greenfield site and will not be metered and serviced by 1/1/18? Will they be made extinct and an Allocate NMI is to be raised with the new roles or will a process be put in place to change the roles upon instruction from the Retailer to update MSATS with the new roles? What is industry’s preferred process? AAD will instruct the applicant (electrical contractor, customer or customer’s representative) to liaise with a FRMP to arrange metering for any RFS (where metering services are requested) received by AAD from an applicant approximately 4 weeks prior to 1 December, where AAD cannot satisfy the appointment request prior to 1 December 2017. AAD will accept and manage all metering works requests consistent with AAD’s Model Standing Offer terms and conditions (for up to 20 connections) up to approximately 1st November, applying discretion for metering service requests for 21+ meter installations received after approximately 1st November. AAD processes require the receipt of both a New Connection SORD and RFS before a NMI is created at MSATS. Normally the RFS is received well before the New Connection SORD; the RFS is used to drive the NMI creation in AAD systems (NOT the New Connection SORD) to allow for associated field works to occur. Once these two prerequisites have been met, the NMI is then created at MSATS (usually within 24hr). During the 4 week period prior to 1 December 2017 FRMPs must submit New Connection SORDs with all roles populated; otherwise AAD cannot publish the NMI to MSATS. Where all roles are not provided, or where AAD are nominated in the metering roles but cannot fulfil the metering request due to appointment unavailability, AAD will TACK ‘reject’ the New Connection SORD with appropriate event code and description. Where AAD have previously accepted metering works; yet due to delays (AAD related e.g. resourcing, weather, scheduling etc.) have been unable to complete the meter installation on the original appointment date (or have not provided an appointment date), AAD will re-schedule and complete those metering works as previously agreed (albeit with a revised appointment date that may fall after 1 December 2017). AAD will look to maintain appropriate metering stocks to cater for these scenarios. Where AAD have previously accepted metering service requests; yet have been unable to complete those works due to defects (caused by electrician e.g. site access, safety etc.) or customer / site readiness issues (e.g. change of electrician, delays in building works etc.), AAD will not re-schedule and instruct the applicant to contact a FRMP to arrange metering. AAD are currently seeking clarity on how to do this within the confines of a post 1 December legislative environment. AAD are seeking to mitigate the risk of Retailers not having established commercial agreements with Metering Coordinators (MC’s) pre 1 December 2017; leaving MCs with insufficient time to mobilise resources to fulfil Retailer requests for metering services where AAD are no longer legally allowed to do so. AAD want to ensure customer needs can continue to be met should participants fail to be ready on 1 December. This risk has been raised at the PCF and is supported by AAD. This is our intent at the moment; however this may be subject to change. AAD have been and will continue to engage with industry to inform AADs new connection / metering process going forward. |
| NSW – Ausgrid | - Ausgrid encourages retailers to cease nominating the LNSP as the RP in 'Allocate NMI' service orders from 01/11/2017 unless they can guarantee meter installation and connection to the network prior to 01/12/2017. Where a retailer nominates itself as the RP and its own metering service providers, Ausgrid will continue to advise the ASP of the need to contact the retailer to arrange metering - This is the process today. ASPs have also been advised not to collect meters if the installation is likely to occur after 01/12/2017. However, Ausgrid will continue to allocate meters to ASPs intending to complete installation and upgrade works right up to 30/11/2017. - Ausgrid is currently investigating options that does not involve the extinction of the NMI. There are contractual obligations linked to the provision of a NMI to an ASP that we would not want to be broken and may not be able to transfer them to a new NMI. I will update you as we make progress on this matter.(Discussion was had around role changing instead of abolishing need to confirm Ausgrid’s position) |

| BCT Process |  |  |
| --- | --- | --- |
| Scenario | Requirements | Responsibility |
| NMI’s that have the FRMP as the MC for existing sites with 1-4 metering | A list of NMI’s needs to be produced. | FRMP |
|  | FRMP needs to appoint a contestable MC | FRMP |
|  | Approval needs to be sought from the MC who is going to be appointed for each NMI. | FRMP |
|  | Approval needs to be sought from other participants who will be impacted by the change of MC for each NMI. | FRMP |
|  | AEMO needs to receive these approvals. - Due to the volume of approvals AEMO will provide a process where participants (not new MC’s) can advise AEMO that they will accept the changes via the BCT. - AEMO will make a list of these participants available for FRMPs to view to reduce the amount of individual approvals they are required to seek. | FRMP/AEMO |
|  | Once all approvals have been received, a template that AEMO has created will need to be completed and sent to AEMO with a copy of the approvals (not the participants that are on the published list) | FRMP |
|  | BCT run as per lists provided by the FRMP | AEMO |
| NMI’s that have the LNSP as the MC and metering is not going to be provided by the LNSP | A list of NMI’s needs to be produced of greenfield sites. | AEMO |
|  | List needs to be verified, and advice provided whether these NMIs are required and need roles updated or can be made extinct | LNSP |
|  | FRMP needs to appoint a contestable MC | FRMP |
|  | Approval needs to be sought from the MC who is going to be appointed for each NMI. | FRMP |
|  | Approval needs to be sought from other participants who will be impacted by the change of MC for each NMI. | FRMP |
|  | AEMO needs to receive these approvals. - Due to the volume of approvals AEMO will provide a process where participants (not new MC’s) can advise AEMO that they will accept the changes via the BCT. - AEMO will make a list of these participants available for FRMPs to view to reduce the amount of individual approvals they are required to seek. | FRMP/AEMO |
|  | Once all approvals have been received, a template that AEMO has created will need to be completed and sent to AEMO with a copy of the approvals (not the participants that are on the published list) | FRMP |
|  | BCT run as per lists provided by the FRMP | AEMO |