## Slide 1: 5MS & GS Industry Testing Working Group
Tuesday 3 February 2021
WebEx only: **Please disconnect from your workplace VPN for the WebEx call**
PLEASE NOTE THIS MEETING WILL BE RECORDED FOR THE PURPOSE OF PREPARING MINUTES

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol.
Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol.
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require.
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
Tui Grant

## Slide 4: Agenda **Please disconnect from your workplace VPN for the WebEx call**
# | Time | AGENDA ITEM | Responsible
1 | 10:30 – 10:35 | Welcome, introduction and apologies | Tui Grant
2 | 10:35 – 10:40 | Agenda | Vishnu Vijayan
General Update |  |  | 
4 | 10:40 – 11:00 | 5MS Program Update – date changes, summarising impacts and industry feedback | Greg Minney
5 | 11:00 – 11:30 | 5MS Staging Update – impact of date changes, arrangements for invitation industry testing | Tui Grant
6 | 11:30 – 11:30 | Test Scenarios defined for Retail testing go live | Tui Grant
7 | 11:30 | General Questions | All

## Slide 5: Program Update
Greg Minney

## Slide 6
Revised Retail Go-Live Timeline
Critical path timeline indicates completion of Retail stream activities for a 31-May-21 go-live
  Based on detailed planning and reasonable estimates, predicated on timely resolution of issues
Additional contingency could be added to improve certainty
  Would result in a 21-Jun-21 go-live
  Offers greater certainty in achieving Retail Go-Live date
  Better meets participant objectives of date certainty
Consequences of late June go-live
  Compresses the schedule through the remainder of the program to 5MS market go-live
  Close to Market Trial start (05-Jul-21), creates resourcing conflict if stabilisation issues occur
  Later to switch-on 5-min meter data collection capability – for AEMO, MDPs and Participants alike
  Compresses participant time for UFE soft start transition activities
Options for Consideration
  31-May-21 go-live date with 21-Jun-21 as a fallback. To be determined by a checkpoint in early March.
  21-Jun-21
AEMO preference is for Option 1
  Allows maximum time for transition activities after Retail Go-Live through to market go-live
Seeking participant views
  Input is requested by Friday 05-Feb-21
  Exec forum to be scheduled for 11-Feb-21 at 13:00

## Slide 7: Initial Impact Assessment Key dates
Area | Original Date | New Date | Implication
5MS Rule Commencement | 1 Oct 21 | No change | No change to 5MS market start date Risk assessment requires review and re-rating to reflect revised schedule
UFE soft start | 1 Oct 21 | No change | Compresses available DNSP population time for some UFE Standing data activities and may result in re-scheduling of activities Leads to potentially less accurate UFE on 1 Oct 21 soft start
GS Rule Commencement | 1 May 22 | No change | No impact expected
5MS Market Trial | 5 July 21 | No change | No change to start date for 5MS market trial Acknowledge heightened risks around timely commencement
Dispatch IT Go-Live | 1 Apr 21 | No change | No impact expected
Settlements IT Go-Live | 15 Apr 21 | Mid-May | Will now go-live before Retail MDM Further testing required to allow for this Date currently being finalised, mid-May expected
Regulatory roadmap | Various | No change | No change currently anticipated to any dates: Customer Switching, WDR Regulatory roadmap session currently being arranged at which the overall view can be reviewed

## Slide 8: 5MS Program Timeline – Option 1 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 31/05/21
Note: Pre-prod and Settlement dates under review

## Slide 9: 5MS Program Timeline – Option 2 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 21/06/21
Note: Pre-prod and Settlement dates under review

## Slide 10: External Milestones Impacted by Change – Proposed
ID | Milestone | Previous Date | Option 1 | Option 2 | Owner
L1-19 | AEMO Metering Solution - Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | [17-May-21] | [17-May-21] | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | 22-Jun-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | [16-Apr-21] | [16-Apr-21] | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | 12-Jun-21 | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | [13-May-21] | [13-May-21] | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | 14-May-21 | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | [29-Mar-21] | [19-Apr-21] | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | [29-Mar-21] | [19-Apr-21] | AEMO
[Settlements dates under review]

## Slide 11: Actions to mitigate participant program impacts
Area | Mitigation | Participant Category | Implementation Status | Impact support
Bilateral Testing | Staging environment to support more extensive B2B and B2M bilateral testing | Retailer, DNSP, MDP | Currently provided | Increased support for participant bilateral testing programs in advance of Retail pre-prod availability
5-minute Meter Data | Reduce period between retail platform go-live and acceptance of 5 minute granularity metering data | MDP | Under Consideration | Maximises transition window for the delivery of 5 minute metering data to AEMO prior to rule commencement
UFE | AEMO Support for bulk population of NCONUML | DNSP | Not currently Planned | Reduce impact of smaller transition window for the population of NCONUML NMIs, once approved
Industry Testing | Extend Industry Test period in advance of Retail Platform go-live | Retailer, DNSP, MDP | Only option 2 | Increase opportunity for participant process testing in upgraded environment prior to go-live

## Slide 12: Impacts to Participants
AEMO will endeavour to minimise impacts to participant programmes in meeting overall 5MS and GS rule commencements. We anticipate many of the impacts will entail replanning of activity in-line with available market capability. Key areas impacted may include:
At the TFG scheduled for 29-Jan, impact on the Metering Transition Plan Activities (1-3) will be undertaken
ITWG will realign activity and participant availability for Invitation Industry Test
AEMO will reissue Retail Industry Go-Live plan to support rescheduling of new cutover dates
Readiness Survey #6 will include specific questions to consolidate view of industry impacts
Participants are asked to identify other areas requiring industry consideration at upcoming RWG
  Timing of metering data delivery migration for interval meters to MDFF Format
  Adjusting the plans for the commencement of 5-minute metering data delivery to AEMO, and potentially retailers/ DNSPs
  Adjusting the timing for the population of NMI Standing data and NCONUML - for those activities with direct capability dependency on Retail Platform deployment
  Timing of participant implementation of capability delivered with Retail Platform, including B2M via API capability
  Rescheduling Industry Test involvement and resourcing
  Rescheduling planned cutover activity

## Slide 13: 5MS Staging Update
Tui Grant

## Slide 14: General Update
5MS Staging Environment
Outage on the 02 Feb – 03 Feb to allow for security protocols to be updated.
Outage scheduled 08 Feb -12 Feb to move MDM to the ‘end state’ platform
5 minute settlement run being completed for participants who want to test with a fresh example. Should be available in Staging COB today

## Slide 15: 5MS Staging Environment Defects – 08-Jan-21
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Action​
2805 | Screen display issue only - An extra TNI2 field is getting displayed under Address Information section in NMI Master, Point in Time NMI Master Summary and NMI Discovery Type 1 and Type 2 search page.​ | In Progress | It is a display issue only no functionality affected​ Release in staging planned for 15 Jan
2185​ | Unable to login to MSATS with newly created or updated user id and password​ | Closed​ | Once created/updated in MSATS users can reset password by logging onto the market portal​ Release in staging planned for 22 Jan
2655 | In flight CRs during schema upgrade do not get published with correct aseXML | Closed | REQ/PEND/COM etc still produced as expected but will have an incorrect asexml response
2856 | Staging: Cleanackhandler sometimes sends incorrect X-initiatingParticipantID request header | In Progress | No impact to participants Release in staging planned for 22 Jan
2880 | Event Only Nack from Participant Results in a badack | In Progress | Acknowledge the file from MSATS browser to remove the badack Release in staging planned for 15 Jan
2882 | CATS Report Requests not getting processed in Staging for ENERGYAP, TCAUSTM, TCAMP | Closed | Issue only affects some participants Release in staging planned for 16th Dec
2890 | Updated Data Stream type for K1 and Q1 not reporting correctly in C1 | Closed | Release in staging planned for 16th Dec
3060 | Staging: B2B and metering functionality are not working | Closed | All functionality now restored.
3063 | Unable to change B2M participant schema and receiving protocol when there are B2B outbound messages in outbox | Closed | Work around is to ensure both are empty before you update
3099 | Report requests are not getting picked up for Report Generation processing | Closed | Initial investigations indicate that this is an environment issue and is being addressed as a priority but I do not have a firm eta at this point.

## Slide 16: Upcoming meetings
Current as at 02/02/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 17: Test Scenarios Defined for Retail
Tui Grant

## Slide 18: Questions