## Slide 1: 5MS Industry Testing Working Group #14
Wednesday, 23 March 2021 10:00 – 12:00AM (AEDT)
By Webex

## Slide 2: Agenda
No. | Time (AEDT) | Agenda item | Presenter
Preliminary matters |  |  | 
1 | 10:00 – 10:10 | Welcome | Tui Grant
2 | 10:10 – 10:20 | Actions from previous meetings | Tui Grant
3 | 10:20 – 10:30 | Testing and Deployment Dates | Greg Minney
3 | 10:30 – 10:45 | Settlements Industry Testing | Tui Grant
4 | 10:45 – 11:00 | Retail Invitation Testing | Tui Grant
5 | 11:00 – 11:10 | Market Trial Test Preparation | Tui Grant
Matters for discussion |  |  | 
6 | 11:10 – 11:20 | Training | Tui Grant
7 | 11:20 – 11.30 | Forward Meeting Plan | Tui Grant
8 | 11:30 | Meeting Close | Tui Grant

## Slide 3: Open Actions
Item | Action required | Responsible | Action update | By
13.1.1 | AEMO to see if we can use a production 30-minute file and generate a 5-minute settlement file for staging. | AEMO | Unable to do this easily but will be generating a 5 minute file from the MSATS staging environment and can put this into the Settlements staging environment | 23-Mar-2021
13.7.1 | 5MS will send out two invites for MSATS training | AEMO | Invites have been sent for these training sessions. | 23-Mar-2021
13.7.2 | AEMO to send out training invites for Practitest for those involved in invitation testing | AEMO | Invites sent | 26-Mar-2021
13.7.3 | AEMO to confirm which participants need to re certify or re accredited as part of these changes | AEMO | Confirmed that anyone changing a system which generates a market asexml will need to use the self-serve certification functionality in MSATS. MDP,LNSP,MC roles need to contact the metering group within AEMO to verify if they require additional certification | 23-Mar-2021

## Slide 4: Testing and Deployment Dates
Greg Minney

## Slide 5: Program Update and Timeline
Current as at 05-03-2021
Industry Go-Live Plan final version for Dispatch & Bidding issued 8th March
Retail: System Integration Testing (SIT) and User Acceptance Testing (UAT) in progress. ​
Bidding: SIT and UAT Complete. Performance Testing is in progress.
Settlements: UAT and Performance Testing in progress. ​
Settlements Industry Test on track to commence 23-Mar-21
5-min Bidding Phased Go-Live on track for 01-Apr-21

## Slide 6: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
08-Apr
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
12-May [TBC]
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline

## Slide 7: Settlements Industry Testing
Tui Grant

## Slide 8: Settlements- Industry Testing
The new settlement system is available to industry in Pre-Production since the 22 March 2021.
This is an opportunity for participants to familiarise and verify the new invoice and reports are compatible with your systems before this goes into production on the 17 May.
There is no formal AEMO coordinated testing for this deployment beyond the publishing of select weeks (next slide). Participants can choose if they wish to review the output or wait and simply receive it for the first time at go-live
If you do decide to test and encounter an issue you can email or contact AEMO Support Hub who will raise a service ticket. Any defects identified will be published on the weekly defect report sent out via the 5MS mailbox.
We will be using data from the Pre-Production instance of MSATS as input into settlements.
  NOTE: this is the current production version of MSTATS i.e. not 5MS
Participants will be able to use the RM reports from MSTATS for reconciliation purposes

## Slide 9: Settlements - Industry Testing
3 settlement runs will be generated and made available on:
23rd March - PRELIMINARY - Week 39/2020 (Settlement dates – 20/09/2020 to 26/09/2020)
26th March – FINAL - Week 37/2020 (Settlement dates – 06/09/2020 to 12/09/2020)
30th March – REVISION - Week 21/2020 (Settlement dates – 17/05/2020 to 23/05/2020)
Post deployment of the new Retail solution 3 more settlement runs will be generated
  Will these be from newly generated data or will we use migrated data
PRELIMINARY - Week TBA
FINAL - Week TBA
REVISION - Week TBA
The invoices will be thirty-minute invoices in line with what participants can expect at go-live of the new solution.
Five-minute testing will be conducted as part of Market Trials in July.

## Slide 10: Retail Invitation Testing
Tui Grant

## Slide 11: Retail Invitation Testing
The new retail solution will be available to industry in Pre-Production from the 19 April 2021.
This is an opportunity for all participants to familiarise and verify the changes to retail.
AEMO will be conducting coordinated testing (Invitation Testing) with a select number of participants before deployment into production. We will use the original participants who volunteered before the go-live date change.
If you do decide test and encounter an issue you can email or contact AEMO Support Hub who will raise a service ticket. Any defects identified will be published on the weekly defect report sent out via the 5MS mailbox.
We will generate data from the new retail solution in Pre-Production as input into 3 settlement runs.
Participants will be able to use the RM reports from MSTATS for reconciliation purposes

## Slide 12: Retail Invitation Testing
Daily meetings will be conducted during the invitation industry testing period at 10:00am EST and will be open to all participants who wish to attend. The focus of these meetings will be on the progress of the formal test cases.
During this period a daily report will be sent with testing progress. This report will be sent to all parties registered with the ITWG but will only contain test outcomes for the coordinated testing effort.
A daily defect report will be sent during the test execution window to all parties.

## Slide 13: Market Trail Preparation
Tui Grant

## Slide 14: Market Trials – Industry Test Focus Group
Industry Test Focus Group will be a small group of ITWG participants representing various NEM roles.
Focus group will be responsible for defining the test coverage for the Industry Testing/Market Trials.
  Test scenario identification.
  Test case preparation.
  Data requirement definitions.
  Test execution timeframes.
  Consideration on defining the number of test cycles required.
Plans developed by the focus group will be circulated to the wider ITWG for input and consideration
Nominations / confirmations will also be called for those participants planning to participate in Market Trial execution as part of the planning process. This activity will commence in May as we head toward market trials.
In the lead up to Market Trials the pre-production systems will be refreshed form production. Date to be confirmed.

## Slide 15: Training
Tui Grant

## Slide 16: Training
Back to Agenda
MSATS Training
  Following on from the discussions at the last ITWG 2 training sessions will set up to provide participants who wish to attend an overview of MSATS.
    Session 1 - 22 March
    Session 2 - 6 April
Practitest Training for participants involved int the retail invitation testing will be conducted just prior to the start of testing.
    Session 1 - 5 April
    Session 2 - 7 April
Further training will be available in the lead up to Market Trials for Practitest.

## Slide 17: Forward meeting plan
Tui Grant

## Slide 18: Proposed upcoming ITWG meeting content
Date | Meeting | Proposed content
Wed 27 Apr 2021 | ITWG #15 | Update on Settlement Release Update on Retail Testing Review of scenarios proposed for market trials
If you have any suggested agenda topics, please contact 5MS@aemo.com.au