## Slide 1: 5MS Industry Testing Working Group #15
Tuesday, 27 April 2021
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Topic | Presenter
Preliminary matters​ |  |  |  | 
1​ | 10:00 – 10:10​ | Welcome​ |  | Tui Grant​
2​ | 10:10 – 10:20​ | Actions from previous meetings​ |  | Tui Grant​
3​ | 10:20 – 10:30​ | Defects |  | Tui Grant
3​ | 10:30 – 10:45​ | Retail Invitation Testing​ |  | Tui Grant​
4​ | 10:45 – 11:00​ | Market Trial Test Preparation​ |  | Tui Grant​
Matters for discussion​ |  |  |  | 
5 | 11:00 – 11:20​ | Forward Meeting Plan​ |  | Tui Grant​
6​ | 11:20 – 11.30​ | Meeting Close​ |  | Tui Grant​

## Slide 4: Welcome
Tui Grant

## Slide 5: Actions from Previous Meetings
Tui Grant

## Slide 6: Open Actions
Item ​ | Action required​ | Responsible​ | Action update​ | Due by
14.1.1​ | AEMO to see if we can use a production 30-minute file and generate a 5-minute settlement file for staging. ​ | AEMO​ | Complete Market Trial Workshop | 31-Mar-2021​

## Slide 7: Defects ​
Tui Grant

## Slide 8: 5MS Staging Environment – 23 April 2021
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Stream | Action​
4090 | RM43 report is throwing error(1809 -> Security validation) when requested from MSATS. | Closed | Retail | RM43 report is throwing an error. Scheduled to be deployed into staging 1st April
4159 | Incorrect event is being sent to participant for an invalid aseXML message submitted by participant. | In Progress | Retail | Incorrect error message is being sent when we receive an invalid schema message.
4161 | Getting "StoreProcFunctionalException-FW410_SUBMIT_USP -> Please contact Helpdesk" error when submitting CR1000 from MSATS | Closed | Retail | 

## Slide 9: 5MS Pre Production – 23 April 2021
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Stream | Action​
4043 | Prudential External Alert - BUSALERT_PRUD_EXT_GRT_EXPIRE11 not generating alerts | In Testing | Settlements | This alert is not generated when guarantee expire Expected to be delivered 23 April
4127 | Settlements - FCASREGIONRECOVERY Report is not being generated for participants | In Progress | Settlements | Expected to be delivered 23 April
4148 | Settlements Direct screen has additional categories being displayed | Closed | Settlements | Screen is still able to be used. Expected to be delivered 23 April
4160 | Meter Data Report Publishing is not able to be displayed in the settlement direct screen | In Progress | Settlements | Expected to be delivered 23 April
4183 | Issues with Publishing Direct/Settlement Direct APi - getAvailabileFiles is timing out without specificing the PublishingCategoryID | Closed | Settlements | If participants use the PublishingCategoryID the API responses correctly.
4201 | CDEII Report Issue | In Testing | Settlements | This report is not generated in all instances. Expected to be delivered 23 April
4333 | Settlements UAT - Settlement Direct - Settlements Direct Change to exclude Version | In Testing | Settlements | The settlement direct screen is missing the version column on the screen. Expected to be delivered 23 April
4324 | Settlements UAT - NEM Public Daily Energy Summary report not generated | In Progress | Settlements | This report is not being generated and displayed on the settlement direct screen. Expected to be delivered 23 April
4323 | Settlements UAT - NEM Confidential Daily Energy Summary report not generated | In Progress | Settlements | This report is not being generated and displayed on the settlement direct screen. Expected to be delivered 23 April
4322 | Settlement UAT - NEM NMAS Recovery Reconciliation reports not generated | In Progress | Settlements | This report is not being generated and displayed on the settlement direct screen. Expected to be delivered 23 April
4321 | NEM Directions Recovery Reconciliation not being generated in Settlement Direct | In Progress | Settlements | This report is not being generated and displayed on the settlement direct screen. Expected to be delivered 23 April

## Slide 10: 5MS Pre Production – 23 April 2021
Forecasting, SD/CD
Issue ID​ | Description​ | Status​ | Stream | Action​
4392 | Settlements Direct: The text reports do not have the .txt extension | In Progress | Settlements | Files are downloading with an incorrect .file name extension which affects the opening of these files Expected to be delivered 23 April
4533 | Credit Support is missing a filed on the credit support page | In Progress | Settlements | Expected to be delivered 23 April
4539 | r39_p1 in MSATS Pre-production returning r35 acks | Closed | MSATS | Even if you update to the latest schema CATs transactions are returning acks in r35 format.
4607 | Incorrect event codes 201 and 202 are valid B2B codes that are being applied to B2M incorrectly should be 3021 and3022 | In Progress | MSATS | Incorrect error codes returned when errors occur in meter read files submitted to AEMO
4563 | MSATS meter data enquiry screen is return duplicate rows of data | In Progress | MSATS | Date is being4547 displayed twice – confirmed it is only in the DB once.
4547 | Screen display issue – MDMT batch handler incorrectly showing as down for some participants | In Progress | MSATS | The correct information is displayed directly under the incorrect message
4443 | Run Date/Time field mandatory for RM11 incorrectly | In Progress | MSATS | Participant forced to enter a run date and time when select report via screen.

## Slide 11: Retail Invitation Testing​
Tui Grant

## Slide 12: Retail Invitation Testing​

## Slide 13: Market Trial Test Preparation​
Tui Grant​

## Slide 14: Market Trials - Changes
Changes effective from 01st OCT 2021
Retail
MDMT files will no longer be accepted for interval meters – only MTRD files
UFE reports will be available
Settlements
All data from 1st October onward will be derived in 5 minute format
UFE will be displayed on invoices but not used in any calculations
New UFE reports available
Dispatch and Bidding
Able to submit bids in 5 minute increments with varying values for each 5 minute period.
Considerations
  Do we test the transition settlements (5 days of 30 minute data and days of 5 minute data)
  Do we test full 5 minute settlements
  What volume of meter reads would participants like to see flow through
  Do we reflect the 5 minute bidding in the settlements invoices
  Over what period would you like to conduct the tests
Tui Grant

## Slide 15: Market Trials – Proposed Scope
  Dispatch and Bidding
  Enter bids in current mode and verify the actual cut over date (i.e. submit bids in varying values).
  Enter bids in the new variable values post change date
  Energy bids and FCAS
  Trading price
  An Intervention - To be confirm
  Including bids price caps – rolling sums, FCAS and energy bids – To be confirmed
  Market Suspension – To be confirmed
  Settlements
  Daily settlement runs for the transition week – 5 days of 30 minute 2 days of 5 minute
  Followed by 3 weeks of daily 5 minute runs and normal weekly runs
  Reallocations
  Publishing of UFE reports
  Settlement reports
  Test population of SRA_PRUDENTIAL_CASH_SECURITY
  Retail
  Change of Retailer for a 5 minute meter
  Confirm MDP rejection of MTMD interval files
  Confirm successful submission of MTMD for basic
  Publishing of UFE report
  NCONUML
  Type 7 meter read files
  Network bills generated for FRMP’s
Tui Grant

## Slide 16: Market Trials – Proposed Scope
  Assumptions
  Refresh wholesale and retail data.
  Testing week will be based on the production settlement week.
  MDP’s are able to provide reasonable volumes of 5 minute reads to both and AEMO and other participants
Tui Grant

## Slide 17: Market Trial Test Preparation​ - Next Steps
Confirm Scope
Commence Registrations
Confirm data refresh dates
Prepare settlement weeks based on simulated 1st Oct date
Organise Practitest training for market trials
Confirm assumptions

## Slide 18: Forward Meeting Plan
Tui Grant

## Slide 19: Upcoming Meetings AEMO | Program Calendar and Timelines
Current as at 13/04/2021

## Slide 20: General Questions
Tui Grant

## Slide 21: Meeting Close
Tui Grant

## Slide 22: Appendix

## Slide 23: Appendix
UPDATE