## Slide 1: 5MS & GS Program Consultative Forum #29
Thursday, 28 January 2021
This meeting is recorded for the purpose of minute taking.

## Slide 2: AEMO Competition Law Meeting Protocol
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.

## Slide 3: Agenda
# | Time | Topic | Presenter
1 | 10:30 – 10:35 | Welcome | Peter Carruthers
2 | 10:35 – 10:40 | Actions from previous meetings | Anne-Marie McCague
3 | 10:40 – 11:40 | Program Update | Multiple
4 | 11:40 – 12:10 | Industry Risks and Issues | Anne-Marie McCague
5 | 12:10 – 12:25 | Market Go-live Criteria and Process | Greg Minney
6 | 12:25 – 12:30 | Readiness Working Group Update | Greg Minney
7 | 12:30 | Forward meeting plan | Anne-Marie McCague
8 | 12:30 | General Questions | Peter Carruthers
9 | 12:30 | Meeting Close | Peter Carruthers

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Actions from Previous Meetings
Anne-Marie McCague

## Slide 6: PCF Actions
No. | Status | Action | Comment
28.3.1 | Closed | AEMO to provide a definition of critical and non-critical functionality for the 5MS Retail Solution. | No longer relevant.
28.5.1 | Closed | AEMO to reflect the discussions at PCF#28 in the Industry Risk and Issue discussion at Executive Forum #11. | Complete
28.5.2 | Closed | AEMO to update Industry Risks and Issues Register post Executive Forum #11. | Complete

## Slide 7: Program Update
Rowena Leung

## Slide 8: Retail Go-Live Delay - Introduction
On 05-Jan-21, AEMO’s 5MS Program notified participants of a delay to the Retail deployment into both pre-Prod (01-Feb) and Prod (09-Mar)
This delay was driven by 2 new issues, coupled with existing Retail timeline pressures and lack of schedule contingency
2 options for a new Retail go-live date are identified – late May and late June. Participant views are sought.
5MS commencement on 01-Oct-21 is unchanged
The AEMO 5MS team acknowledges there are implications for industry participants and the 5MS Program
Today we plan to:
  Explain the nature of the issues encountered in the Retail stream
  Identify two Retail go-live date options and discuss pros and cons
  Review implications of delay
  Open discussion with PCF
  Review next steps

## Slide 9
Migration to Enterprise Azure – Key Reason
  AEMO has completed its MDM build on what is called an “Interim” Cloud Platform. A corresponding project has run in parallel to 5MS to build an “Enterprise” Cloud Platform which contains significant improvements in stability, performance and security. 5MS found unforeseen technical complexities in moving to the Enterprise platform, which required remediation and a revised approach.
Challenges with Cutover Dress Rehearsal
  The program is completing multiple Dress Rehearsals for Cutover before deploying into Pre-Prod. A number of issues were identified and resolved through the rehearsal, this used up schedule and a further re-run is required before deploying.
Performance of Key RM Reports
  The RM11 and RM16 reports do not met performance targets, despite re-coding to address performance issues. The program team needs time to remediate to ensure performance targets meet industry expectations.
  For context, the functional delivery is accurate and the other RM Reports are ready for live deployment.
AEMO Response
  Identified resourcing dedicated to teams to address issues
  Put in place daily governance arrangements to allow for faster issues escalation and resolution
  Escalating the technical issues with its technology partners.
Key Drivers of Delay and AEMO Response

## Slide 10: 5MS Program – IT Systems Status
Stream | Commentary
Retail | Core product build complete. Integration & User Acceptance Testing program is extensive. ~4500 test cases completed out of 5000. Parallel testing undertaken and defects in the process of being fixed Several rounds of performance testing undertaken and a number of improvements made Software is in Staging environment for participant interface testing since 3Q 2020 Key risk area of meter data ingestion is solid and performing to spec New issues encountered with Azure migration and cutover dress rehearsal Performance, end-to-end solution stability, final testing incomplete.
Dispatch | On schedule for 01-Apr-21 go-live
Settlements | Proposal to switch the order of Settlements and Retail deployment Additional testing of the new Settlements solution with the current MDM solution required accordingly. The Settlements solution pre-prod and go-live dates will be revised by approx 4 wks accordingly. Build complete and in User Acceptance Test. Overall no significant defects or issues, high level of confidence in product. Independent certification of settlements calculations – initial findings available, small number of material matters, now remedied. Date change is expected to impact AEMO internal only, no industry impact envisaged.
 | Go-live date impacted
 | At risk
 | On schedule

## Slide 11
Revised Retail Go-Live Timeline
Critical path timeline indicates completion of Retail stream activities for a 31-May-21 go-live
  Based on detailed planning and reasonable estimates, predicated on timely resolution of issues
Additional contingency could be added to improve certainty
  Would result in a 21-Jun-21 go-live
  Offers greater certainty in achieving Retail Go-Live date
  Better meets participant objectives of date certainty
Consequences of late June go-live
  Compresses the schedule through the remainder of the program to 5MS market go-live
  Close to Market Trial start (05-Jul-21), creates resourcing conflict if stabilisation issues occur
  Later to switch-on 5-min meter data collection capability – for AEMO, MDPs and Participants alike
  Compresses participant time for UFE soft start transition activities
Options for Consideration
  31-May-21 go-live date with 21-Jun-21 as a fallback. To be determined by a checkpoint in early March.
  21-Jun-21
AEMO preference is for Option 1
  Allows maximum time for transition activities after Retail Go-Live through to market go-live
Seeking participant views
  Input is requested by Friday 05-Feb-21
  Exec forum to be scheduled for 11-Feb-21 at 13:00

## Slide 12: Initial Impact Assessment Key dates
Area | Original Date | New Date | Implication
5MS Rule Commencement | 1 Oct 21 | No change | No change to 5MS market start date Risk assessment requires review and re-rating to reflect revised schedule
UFE soft start | 1 Oct 21 | No change | Compresses available DNSP population time for some UFE Standing data activities and may result in re-scheduling of activities Leads to potentially less accurate UFE on 1 Oct 21 soft start
GS Rule Commencement | 1 May 22 | No change | No impact expected
5MS Market Trial | 5 July 21 | No change | No change to start date for 5MS market trial Acknowledge heightened risks around timely commencement
Dispatch IT Go-Live | 1 Apr 21 | No change | No impact expected
Settlements IT Go-Live | 15 Apr 21 | Mid-May | Will now go-live before Retail MDM Further testing required to allow for this Date currently being finalised, mid-May expected
Regulatory roadmap | Various | No change | No change currently anticipated to any dates: Customer Switching, WDR Regulatory roadmap session currently being arranged at which the overall view can be reviewed

## Slide 13: 5MS Program Timeline – Option 1 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 31/05/21
Note: Pre-prod and Settlement dates under review

## Slide 14: 5MS Program Timeline – Option 2 Level 1 and External Level 2 Milestones 1/2
Current as at 15-01-2021
R3 Go-live : 21/06/21
Note: Pre-prod and Settlement dates under review

## Slide 15: External Milestones Impacted by Change – Proposed
ID | Milestone | Previous Date | Option 1 | Option 2 | Owner
L1-19 | AEMO Metering Solution - Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L1-22 | Settlements Platform Go-Live | 19-Apr-21 | [17-May-21] | [17-May-21] | AEMO
L2-M10 | 5 minute files in MDFF format accepted by AEMO | 1-Apr-21 | 22-Jun-21 | 22-Jun-21 | AEMO
L2-M11 | Industry Test Preparation completed by Participants for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | Participants
L2-M12 | Industry Test Preparation completed by AEMO for MDM and B2M Go-Live | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-M24 | Retail MDM (incl. B2M) Go-Live | 9-Mar-21 | 31-May-21 | 21-Jun-21 | AEMO
L2-RE19 | Industry Go-Live Plan - Settlements finalised | 19-Mar-21 | [16-Apr-21] | [16-Apr-21] | AEMO
L2-RE29 | Retail MDM (incl. B2M) Invitation Industry Test Commences | 1-Feb-21 | 19-Apr-21 | 10-May-21 | AEMO
L2-RE30 | Retail MDM (incl. B2M) Invitation Industry Test Concludes | 3-Mar-21 | 21-May-21 | 12-Jun-21 | AEMO
L2-RE32 | Settlements Industry Test Concludes | 14-Apr-21 | [13-May-21] | [13-May-21] | AEMO
L2-RE35 | Industry Go-Live Plan final - Release 3 - Retail MDM | 25-Jan-21 | 16-Apr-21 | 14-May-21 | AEMO
L2-S10 | Settlements Industry Test preparation completed by participants | 17-Feb-21 | [29-Mar-21] | [19-Apr-21] | Participants
L2-S11 | Settlements Industry Test preparation completed by AEMO | 17-Feb-21 | [29-Mar-21] | [19-Apr-21] | AEMO
[Settlements dates under review]

## Slide 16: Actions to mitigate participant program impacts
Area | Mitigation | Participant Category | Implementation Status | Impact support
Bilateral Testing | Staging environment to support more extensive B2B and B2M bilateral testing | Retailer, DNSP, MDP | Under consideration | Increased support of participant bilateral testing programs in advance of Retail pre-prod availability
5-minute Meter Data | Reduce period between retail platform go-live and acceptance of 5 minute granularity metering data | MDP | Under Consideration | Maximises transition window for the delivery of 5 minute metering data to AEMO prior to rule commencement
UFE | AEMO Support for bulk population of NCONUML | DNSP | Not currently Planned | Reduce impact of smaller transition window for the population of NCONUML NMIs, once approved
Industry Testing | Extend Industry Test period in advance of Retail Platform go-live | Retailer, DNSP, MDP | Only option 2 | Increase opportunity for participant process testing in upgraded environment prior to go-live

## Slide 17: Impacts to Participants
AEMO will endeavour to minimise impacts to participant programmes in meeting overall 5MS and GS rule commencements. We anticipate many of the impacts will entail replanning of activity in-line with available market capability. Key areas impacted may include:
At the TFG scheduled for 29-Jan, impact on the Metering Transition Plan Activities (1-3) will be undertaken
ITWG will realign activity and participant availability for Invitation Industry Test
AEMO will reissue Retail Industry Go-Live plan to support rescheduling of new cutover dates
Readiness Survey #6 will include specific questions to consolidate view of industry impacts
Participants are asked to identify other areas requiring industry consideration at upcoming RWG
  Timing of metering data delivery migration for interval meters to MDFF Format
  Adjusting the plans for the commencement of 5-minute metering data delivery to AEMO, and potentially retailers/ DNSPs
  Adjusting the timing for the population of NMI Standing data and NCONUML - for those activities with direct capability dependency on Retail Platform deployment
  Timing of participant implementation of capability delivered with Retail Platform, including B2M via API capability
  Rescheduling Industry Test involvement and resourcing
  Rescheduling planned cutover activity

## Slide 18: Next Steps
PCF discussion
  Open discussion on implications, mitigations, preferences
Feedback sought from participants
  By Friday 05-Feb-21
  Preferred option, why, strength of views
  Via email 5MS@aemo.com.au
  AEMO 5MS Team is available for discussion on implications
Executive Forum
  Enable Execs to comment/question
  Summarise options feedback
  Advise of decision
  Date/time: 11-Feb-21 at 13:00

## Slide 19: Industry Risks and Issues

## Slide 20: Purpose of this session
This session will review risks in light of the proposed changes in dates to the Retail and Settlements systems pre-production and production releases
The purpose is:
New risks have been established where appropriate to ensure clarity in the risk definition
To identify new risks and issues as a result of the change in dates and discuss mitigation measures To review the impact of the change in date on existing risks and issues

## Slide 21: No Remaining Contingency for Retail Deployment
Risk ID | Description | Residual Rating (Proposal) | Comments
R32 | No Remaining Contingency for Retail Deployment There is a risk that an issue may be identified through the remaining scheduled testing of the Retail IT Solution which could result in a delay to the release as there is no remaining contingency. | Critical | Proposing that Residual Likelihood be changed to Almost Certain and Residual Consequence be set at Major which gives a Residual Risk Rating of Critical. Proposing that trend should remain as Worsened Issue 12 has been raised by AEMO and R32 should consequently be closed
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​
Issue ID | Description | Rating | Mitigations
I12 | No Remaining Contingency for Retail Deployment Issues identified during Dress Rehearsal 2 and Azure migration coupled with existing Retail timeline challenges mean that delays have occurred within the 5MS Retail workstream. There is no schedule contingency within this workstream to compensate for the time needed to remediate these issues therefore the scheduled go-live of 09-Mar-21 will not be met. | High | The Retail systems program has been reviewed and the timeline has been revised to provide sufficient time to remediate the identified issues AEMO response program developed Impacts to dependent AEMO and Participant activities will be assessed, and overall program milestones updated

## Slide 22: New Risks (1/4)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R33 (NEW) | Further delays to AEMO Retail Systems impact 5MS rule commencement critical path There is a risk that further delays beyond those identified put the critical path through market trial to 5MS rule commencement (01-Oct-21) at risk | Critical | Significant | Inherent Likelihood: Possible Inherent Consequence: Extreme Actions: To be monitored through reporting to PCF and AEMO readiness reporting AEMO has: identified resourcing dedicated to teams to address issues put in place daily governance arrangements to allow for faster issues escalation and resolution is escalating the technical issues with its technology partners Checkpoints to be established with PCF to monitor effectiveness of mitigations Residual Likelihood: Unlikely Residual Consequence: Extreme
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 23: New Risks (2/4)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R34 (NEW) | Delay to AEMO 5MS Retail impacts participants readiness There is a risk that the delayed availability of the 5MS Retail solution impacts participants readiness programs resulting in delays in some participants programs. | Critical | TBD | Inherent Likelihood: Possible Inherent Consequence: Major Residual Likelihood: to be determined after feedback received Residual Consequence: to be determined after feedback received Actions: Mitigation measures to be identified should there be an impact Risk rating to be reviewed post Readiness Round 6 results and timeline decision Enhanced bilateral testing in 5MS Staging Environment being investigated
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 24: New Risks (3/4)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R35 (NEW) | Compression of window for transition 5-min metering data delivery There is a risk that the compression of the Metering Transition Plan results in the transition of NMIs to 5-min granularity at an unsustainable rate | Significant | Medium | Inherent Likelihood: Possible Inherent Consequence: Major Actions: Update Metering Transition Plan to reflect capability availability dates Support delivery of 5-minute metering data from Retail platform deployment maximise transition window – under consideration Align Participant readiness reporting to updated MTP dates Industry to prioritise activation of 5MS essential meters when planning rollouts Monitor participant impacts and programs via readiness reporting and RWG interaction Residual Likelihood: Unlikely Residual Consequence: Major
R36 (NEW) | Compressed MTP transition windows for the population of NCONUML NMIs impacts the accuracy of UFE Reporting Risk that a subset of the MTP standing data and NCONUML population activities are dependent on capability made available by the deployment of the Retail Platform, will not be completed prior to the UFE soft start on 1/10/21 resulting in less available data to calculate UFE accurately | Medium | Medium | Inherent Likelihood: Possible Inherent Consequence: Moderate Actions: Update Metering Transition Plan to reflect impacted activity transition windows for participants Assessment of accuracy impacts for UFE based on participant readiness reporting against revised timeframes Residual Likelihood: Unlikely Residual Consequence: Moderate
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 25: New Risks (4/4)
Risk ID | Description | Inherent Rating | Residual Rating | Comments
R37 (NEW) | New 5MS Retail Solution Go-Live Dates impact other regulatory change programs There is a risk that the changes to the 5MS retail timeline may have impacts on other AEMO change programs (e.g. Customer Switching or WDR) which may result in a need for those programs to replan having knock-on effects to the industry. | Significant | Medium | Inherent Likelihood: Possible Inherent Consequence: Major Actions: AEMO to increase effort in integration coordination internally and provide updates to participants WDR program communicating impacts through WDR channels Residual Likelihood: Unlikely Residual Consequence: Major
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 26: Impact to Existing Risks (1/2)
Risk ID | Description | Residual Rating (Proposed) | Comments
R06 | Interaction with other industry changes that have already been adopted through rule changes Significant regulatory changes across the energy sector will stretch resources allocated to market change programs, resulting in potential impacts to participants resourcing and program delivery. | Significant | This risk focuses on the demand on industry resources as a result of change programs such as WDR and Customer Switching. The changes in the Retail and Settlements release dates are closer to the WDR timeline which may put added pressure or risk on some participants Proposing that trend should be Worsened Actions: Review the impact of the change to timeline on this risk through feedback from participants and the Readiness Reporting #6 and reassess risk at RWG AEMO is establishing an industry facing Integration Coordination Forum
R11 | The AEMO business and operations are not ready for 5MS Rule Commencement on 1 Oct 21 The AEMO business may not be ready to deliver the full extent of the 5MS deliverables by 5MS and GS rule commencement including business processes and resource training, results in failure of Go Live for 5MS and GS Program | Medium | While the changes in Retail and Settlements date do impact AEMO’s 5MS Program, the focus of this risk is on the AEMO business readiness. The impact of the changes in dates for retail and settlements to AEMO’s business and operational readiness to support 5-min expected to be minor. Actions: Proposing that trend should be changed to Worsened until results of Readiness Round 6 have been reviewed
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 27: Impact to Existing Risks (2/2)
Risk ID | Description | Residual Rating (Proposed) | Comments
R18 | Potential for implementation approach to materially increase Program costs An overall inefficient implementation of 5MS/GS rule change resulting in increased overall industry cost (i.e. greater cost impact to customers) | Significant | AEMO is currently reviewing the AEMO costs associated with a change in Retail Go-Live date. Potential for increase in participant program costs depending on individual participant circumstances Proposing to increase the residual likelihood to Likely and Residual Consequence to Moderate which will increase the rating to Significant Proposing to change the trend to Worsened Actions: This risk should be reviewed after AEMO has completed its review of costs Mitigations as described in R34 to reduce impact on participant programs
R28 | AEMO Systems Deployment Cutover Risk The current approach to the AEMO systems deployments elements of the cutover has the Retail stream (the most complex and riskiest) going first on 9 March, then both the Dispatch and Settlements systems deployments together 3 weeks later on 1 April. There is a risk that the Retail deployment could lead to push back on the following deliveries from the 5MS program, the AEMO business and/or market participants. | Medium | This specific risk was mitigated through moving the Settlements date to 19-Apr-21 The change to the Retail Go-Live requires reconsideration of the Settlements Go-Live date Trend is improving since the Settlement dependencies on Retail have been removed. Actions: Remove the dependencies between the go-live of Retail and Settlements solutions, enabling Settlements solution to go-live before retail solution. Conduct additional Settlements testing to facilitate this Bidding system deployment is still separate from both Settlements and Retail system.
​ | Improving​ ​ No Change /Stable​ ​ Worsened ​

## Slide 28
Are there any new risks or issues to be raised?

## Slide 29: Market Go-live Criteria and Process – Draft for Discussion
Greg Minney, Readiness Manager

## Slide 30: Objectives
Confirm approach, timing and decision rights for Market Commencement for 5MS rule on 01-Oct-21.
Outline criteria and measurement / assurance approach.
Market Commencement Assessment:
  Readiness criteria for rule commencement and level of participant readiness as output of each industry readiness survey.
  Assessment of criteria essential for rule commencement and overall participant readiness.
  Regular Steering Committee and Executive Forum review of criteria and assessment of contingency requirements.
  PCF review of detailed assessment for each round of readiness reporting.
  AEMO Steering Committee to determine contingency implementation requirements.

## Slide 31: Capability Essential for 5MS Rule Commencement
The Program has established critical capability that must be in place to support the smooth operation of NEM at 5MS rule commencement.
  Generators and MNSPs are able to submit 5-min offers
  Generators representing >80% of regional load are reporting ‘On-track’ to be able to submit 5-minute granularity offers
  All essential meters* are able to produce and store 5-min data
  100% of MPs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities.
  100% of MCs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities.
  All essential meters* are able to deliver 5-min metering data
  100% of MDPs associated to essential metering are reporting ‘On-track’ for all applicable MTP activities.
  AEMO capability
  The 5-minute bidding and dispatch solution, including the web bidding interface, is deployed and operationally stable.
  The Metering Data Management (MDM) solution is deployed is deployed and operationally stable.
  The 5-minute settlement solution is deployed is deployed and operationally stable.
* See definitions in 5MS Readiness Documents
Where delivery of this capability is seen at risk, contingencies will be required to facilitate 5MS Rule Commencement

## Slide 32: Status reporting and supporting observations
Progress and status assessment based on readiness reporting against participant-specific readiness criteria.
Status reporting to be supported by observed activity.
Incorporates the identification and potential activation of contingency approaches where essential capability is compromised.
Reviews to incorporate both essential capability and participant readiness:
  Essential capability (Part A) – is the criteria that must be in place for operation of the 5-minute rule.
  Participant readiness (Part B) – although not essential , the level of participant preparation that supports the effective implementation of both 5MS and GS, including GS Soft Start.

## Slide 33: 5MS Rule Commencement - Draft
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
Activity | Status | Comments
AEMO Business Readiness for 5MS and GS (Part A) |  | Bidding Platform deployed for Industry test on Schedule. Retail Platform deployment being rescheduled with impact to dependent activities, Settlement platform go-live to mid-May. Rescheduling of platform deliveries is not expected to impact 5MS commencement or 5MS market trial.
Essential Industry Capabilities for 5MS commencement (Part A) |  | On track for 1 Oct 21 commencement, Metering Data Providers and MPs reporting on track. Generators reporting on-track delivery.
Other industry capabilities for 5MS and GS (Part B) |  | Non-essential activities across all participant types reported on track.
Summary: 5MS Rule Commencement |  | All components of 5MS Essential capability on track for Rule Commencement timeframe, replanning of AEMO Platform Deployments underway and heightened risk profile noted.
On track
On track
On track
On track
Risk 1
Risk 2
Risk 1

## Slide 34: Part A 5MS Essential Capability - Draft
Responsible Participant | Essential Criteria | Status | Comments
Generator | Generators and MNSPs are able to submit 5-min offers |  | Generators representing 95% of NEM volume reporting on-track
MP, MC | All essential meters* are able to produce and store 5-min data |  | 10/10 MPs reporting on track, 1 MP/MC did not respond to survey #5 Rollout plans for all critical meters being confirmed with participants
MDP | All essential meters* are able to deliver 5-min metering data |  | MDPs for Essential meters are reporting programs on track
AEMO | The 5-minute bidding and dispatch solution, including the web bidding interface is deployed |  | AEMO platform deployed for Industry test , on track for 1 April production deployment
 | The Metering Data Management (MDM) solution is deployed |  | Mitigation Action: Replanning underway for Retail platform deployment. No impact expected on 5MS commencement and 5MS market trial.
 | The 5-minute settlements solution is deployed |  | Mitigation Action: AEMO settlement Platform deployment to be rescheduled in line with retail platform - no impact to 5MS market trial or rule commencement. Marked as amber due to consequential impacts on date arising from Retail go-live re-planning.
Summary - Essential Criteria | - | - | Reschedule of AEMO Retail and Settlement Platform Deployment against plan. Market Trials and Rule commencement timeframes not expected to be impacted
On track
On track
On track
On track
Risk 1
Risk 1
 | On track | On track for commencement date
 | Risk 1 – Risk to major milestones or deliveries | Remediation or contingency activation required to ensure on track delivery for Rule Commencement
 | Risk 2 – Risk to rule commencement | Cannot be addressed with available contingencies to be on track for commencement date
On track
Risk 1
Risk 1
On track

## Slide 35: Part B – Other Industry Capabilities - Draft
Responsible Participant | Criteria | Status | Comments
Retailer | Receive and process 5-minute metering data. Receive and process 5-minute settlement data. |  | 19/19 retailers (representing 95% of retail load) reporting ‘on track’. 17/19 retailers plan to participate in industry testing and Market trials.
DNSP | Receive and process 5-minute metering data. |  | 10/10 reporting ‘on track’ to receive 5-minute data.
 | Provide GS metering and standing data updates (incl. NCONUML). |  | 10/10 reporting ‘on track’ for GS updates. 1 participant flagged risk to x-boundary metering for unknown x-boundary meters.
TNSP | Receive and process 5-minute metering data |  | 7/7 reporting 'on track' to receive 5-minute data, 2/7 have intention to receive 5 minute data prior to rule commencement
 | Provide GS metering and standing data updates |  | 7/7 reporting program and NMI Standing Data creation on track
MDP | Provide 5-minute metering data T1-3 distribution connected meters, type 7 meters. |  | MDPs representing 8% (1570 meters)of Tranche 1 distribution meters are currently not reporting against MTP. 100% of MDPs report ‘on track’ for delivery of interval metering data by 1 October.
 | Provide type 4, 4A, Vic Ami metering data at 5-minute granularity., by 1 December 2022 |  | Majority of Roll-out scheduled to commence 3rd quarter of 2021. Summary rollout plans requested for impacted participants 100% of MDPs reporting ‘on track’ for interval meter delivery at rule commencement.
 | Provide basic metering data for tier 1 NMIs to AEMO. |  | Roll-out plans for 45% of outstanding tier 1 basic meters required. MDPs reporting on track for availability prior 1/10/2021. All responsible MDPs reporting ‘on track’ for delivery of required metering data.
MP, MC | All T1-3,4* meters are able to produce and store 5-minute data. |  | MPs reporting ‘on track’ for metering installation, and confirmation of roll-out plans will be sought.
Summary | - | - | 
On track
On track
On track
On track
On track
On track

## Slide 36: Readiness Working Group Update
Greg Minney

## Slide 37: Readiness Working Group Update
Platform Go-Live Plans:
Finalisation of retail industry go-live plan will be provided to incorporate:
    updates to timings
    PVM approach, and
    to confirm dates for deployment
Settlement Draft industry Go-live plan to be circulated for comment
Bidding Industry Go-live plan to be drafted for comment
Transition Focus Group
Agenda for TFG scheduled for 29-Jan-21 will incorporate:
    Proposed changes to the MTP
    Upcoming MTP Activities
    MTP CATS transaction volume management
    GLOPOOL TFG requirements
    Cross boundary guidelines
  Invitation Industry Test planning - Retail
  Scenarios distributed for consideration by participants, participants to reconsider availability for testing
  Planned data refresh of pre-prod as at 14-Dec-20
  Planning for conduct will take place in ITWG and with focused sessions for participating organisations

## Slide 38: Readiness Working Group Update
Readiness Risk Review
Review of readiness risks conducted
No major change in trends noted
RWG feedback on Programme risks incorporated into PCF risk review
Will be reassessed at next RWG in light of changes to AEMO platform delivery timeframes
Upcoming activity
RWG:
  Impacts of Retail and Settlement reschedule
  Review of draft Settlements Industry Go Live Plan
  Review of Draft Bidding Go-live Plan
  Updates to readiness survey to incorporate further readiness activities
  Updates Retail Industry go-live plan and response to industry feedback
ITWG
  Planning for Invitation Industry Test – Retail
  Data availability for Settlements Industry Test

## Slide 39: Readiness Working Group Update
Staging Environment
Outage will take place in early February to migrate across to end state solution – MSATS/ Retail only impacted and will be unavailable for a period of 5 days.
Staging data is a copy of Production as of 31 Jul-20.
Full functionality for B2B testing is supported in the staging environment for participants wanting to perform bilateral testing including 30-minute and 5-minute reads.
B2M functionality is also able to be tested in the MSATS staging environment for any participant wanting to perform testing of B2M ahead of the deployment to Pre-Production.
Participants can refer to the Functional Deployment Matrix for more details of capability.
Dispatch Industry Test
Limited industry activity noted to date for Bidding platform – No significant defects identified
  Update release will be scheduled for February to remediate defects identified in AEMO UAT

## Slide 40: Forward Meeting Plan
Anne-Marie McCague

## Slide 41: High-Level Plan for 2021
Month | Topics | Month | Topics
January | AEMO go-live decision making process Risk Review Readiness and go-live dashboard | June | Market Trial prep status Debrief on Retail Go-Live [TBD]
18 February | Retail Solution Status Exec Forum Agenda | July | Market Trial progress Readiness Reporting #8
18 March | Dispatch Cutover Preparation Status Readiness Reporting #6 5MS Rule Commencement check point Checkpoint on Retail Solution timeline | August | Market Trial progress Risk Review – focus on rule commencement Exec Forum Agenda
23 April | Debrief on Dispatch go-live Risk Review Retail Cutover Plan [TBD] | September | Results of Market Trial Preparing for 1 Oct – Ind Go-Live Plan review Readiness Reporting #9
May | Readiness Reporting #7 Exec Forum Agenda Approach to Global Settlements engagement | October | Debrief and reconfirmation of approach for Global Settlements
This table provides a list of key topics. The normal updates will also be provided at each PCF. This table will evolve as the year progresses.

## Slide 42: Upcoming meetings
Current as at 20/01/2021
https://aemo.com.au/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement

## Slide 43: General Questions
Peter Carruthers

## Slide 44: Meeting Close
Peter Carruthers

## Slide 45: Appendix

## Slide 46: Readiness Dashboard Part A - Essential Capability Status supporting evidence – Draft
Criteria | Capabilities | March | May | July | Sept
AEMO Capability | Metering: | Deployment of Metering Platform schedule | Metering Platform deployed for 30 Minute operation | Business Operations Stable | Market Trial Conducted successfully
 | Receive and Process 5 minute metering data | Metering Platform Industry testing Conducted | Business operations stable | 5MS Capability in place for Market Trial | 
 | Support 5 Minute Profiling |  |  | Market Trial Planned | 
 | Settlements: | Platform Industry testing underway | Platform deployed for 30 Minute operation | Business Operations Stable | Market Trial Conducted successfully
 | Support 5 minute Settlement processes | Platform deployment on track for scheduled date | Business operations stable | Capability in place for Market Trial | 
 |  |  |  | Market Trial Planned | 
 | Dispatch (Bidding): | Platform Industry testing underway | Platform deployed for Transition mode operation | Platform Stable | Market Trial Conducted successfully
 | Support 5 Minute bidding services | Platform deployment on track for scheduled date | Business operations stable | Capability in place for Market Trial | Bidding table updates in place
 | Provide 5 Minute web bidding interface | Bidding table updates in place | Bidding table updates in place | Market Trial Planned | 
 |  |  |  | Bidding table updates in place | 
Essential Bidding | Generators: | Testing of upgrades commenced | Testing of upgrades | Deployments of 5 Minute Capability (Transition mode) | Deployments of 5 Minute Capability (Transition mode)
 | generators representing at least 80% of load in each region are capable of providing 5 minute bids |  | Initial deployments of 5 Minute Capability (Transition mode) | Market Trial Participation Planned | Market Trial Participation Planned
Essential Metering | MP's upgraded ensured that essential meters are capable of providing 5 minute metering data | Metering rollout plans with reported progress versus MTP | Metering rollout plans with reported progress on track | Metering rollout plans with reported progress on track | Metering rollout plans Completed
 | MDPs are able to provide 5 minute metering data for essential meters for settlement | Metering rollout plans available Accreditation initial meetings held Program Progress being Reported on track | Accreditation Updates planned / Underway | Market Trial Participation | Market Trial Participation
 |  |  | Initial Delivery of 5 minute data for Settlement | Accreditation updates Achieved / Underway | Accreditation updates Achieved
 |  |  |  | Initial Delivery of 5 minute data for Settlement | Initial Delivery of 5 minute data for Settlement

## Slide 47: Readiness Dashboard Part B - Participant Readiness Status supporting evidence - Draft
Participant | Capabilities | March | May | July | Sept
Retailers | Receive and process 5 minute metering data |  | Planned participation in Market Trials | Participation in Market Trial | Market Trial successful participation
 | Receive and process 5 minute Settlement statements |  | Level of bi-lateral testing of B2B processes | Level of bi-lateral testing of B2B processes | 
DNSPs/ TNSPs | Receive and process 5 minute metering data | Published plans for Standing data and Metering upgrades | On track delivery against Standing Data and Metering Upgrades | On track delivery against Standing Data and Metering Upgrades | On track delivery against Standing Data and Metering Upgrades
 | Provide GS Metering and Standing Data updates (inc. NCONUML) |  |  | Market Trial Participation | Market Trial successful participation
MDPs | Provide 5 minute Data T1-3 Distribution connected metering data | Published plans for T1 Basic Meter Delivery, Accreditation Updates planned Rollout Plans for T1-3 4*, 7 - distribution connected | On track delivery for T1 Basic Meter Delivery | On track delivery for T1 Basic Meter Delivery | T1-3, Type 7 distribution connected meters providing 5 minute metering data for Settlement T1 Basic Meter Data completed
 | Provide T1 Basic Metering Data |  | Level of bi-lateral testing of B2B processes | Level of bi-lateral testing of B2B processes | 
 | Provide MDFF Interval Data / Inc |  | Ontrack for T1-3, 7 distribution connected metering data delivery | Ontrack for T1-3, 7 distribution connected metering data delivery | 
MDPs | Provide 5 Minute metering Data (4, 4A, VicAMI) | Rollout Plans Provided | Rollout Plans Provided | Market Trial Participation | All Interval Metering Data delivered via MDFF
MPs | T1-3 distribution connected metres capable of producing 5 Minute Data | Metering rollout plans with reported progress versus MTP | Metering rollout plans with reported progress on track | Metering rollout plans with reported progress on track | Metering Rollout Completed