## Slide 1: 5MS Program Consultative Forum Update
Friday, 7 May 2021
This meeting is recorded for the purpose of minute taking.
Please disconnect from your workplace VPN for the WebEx call

## Slide 2: AEMO Competition Law Meeting Protocol
Under no circumstances must Participants share Competitively Sensitive Information. Competitively Sensitive Information means confidential information relating to a Participant which if disclosed to a competitor could affect its current or future commercial strategies, such as pricing information, customer terms and conditions, supply terms and conditions, sales, marketing or procurement strategies, product development, margins, costs, capacity or production planning.
AEMO is committed to complying with all applicable laws, including the Competition and Consumer Act 2010 (CCA). In any dealings with AEMO regarding proposed reforms or other initiatives, all participants agree to adhere to the CCA at all times and to comply with this Protocol. Participants must arrange for their representatives to be briefed on competition law risks and obligations.
Participants in AEMO discussions must:
Ensure that discussions are limited to the matters contemplated by the agenda for the discussion
Make independent and unilateral decisions about their commercial positions and approach in relation to the matters under discussion with AEMO
Immediately and clearly raise an objection with AEMO or the Chair of the meeting if a matter is discussed that the participant is concerned may give rise to competition law risks or a breach of this Protocol
Participants in AEMO meetings must not discuss or agree on the following topics:
Which customers they will supply or market to
The price or other terms at which Participants will supply
Bids or tenders, including the nature of a bid that a Participant intends to make or whether the Participant will participate in the bid
Which suppliers Participants will acquire from (or the price or other terms on which they acquire goods or services)
Refusing to supply a person or company access to any products, services or inputs they require

## Slide 3: Agenda
# | Time | Topic | Presenter
1​ | 11:30 – 11:35​ | Welcome​ | Peter Carruthers​
2​ | 11:35 -11:45 | Retail Checkpoint Criteria | Graeme Windley
3​ | 11:45 – 11:50 | Industry Test Status | Greg Minney
4 | 11:50 – 11:55 | Conclusions and Next Steps | Peter Carruthers
5​ | 11:55 – 12:00 | General Questions | Peter Carruthers​
6 | 12:00 | Meeting Close | Peter Carruthers

## Slide 4: Welcome
Peter Carruthers

## Slide 5: Retail Checkpoint Criteria Update

## Slide 6: Approach to Retail Status Updates
18-Feb PCF
Forward Planning for Retail
Update on Interim Checkpoint Criteria Status
18-Mar PCF
March Checkpoint Criteria – assessment and outcomes
Pre-prod – status and go/no-go date
Production go-live – checkpoint date and criteria, go/no-go date
08-Apr
Pre-Prod Go/No-Go email
19-Apr
Retail Industry Testing Commences
14-May
Retail Go/No-Go Communicated to PCF via email
23-Apr PCF
April Checkpoint Criteria - assessment and outcomes
Go/No-Go – confirm date
19-May PCF
Confirming Go/No-Go
Issue management
Replanning (if necessary)
31-May
5MS Retail/ Metering Solution Go-Live
Key milestones
Communication timeline
07-May
PCF Update Session

## Slide 7: Retail Checkpoint Criteria
Criteria​ | Description | Status | Commentary
Testing | All UAT test cases executed with no critical defects that cannot be remedied for 31 May go-live. | In Progress | All test cases executed. Re-testing for defect fixes remains in progress. Defect numbers related to functionality are low. However open defects remain related to environment, data, performance testing and industry testing. These are being fixed/re-tested but time remaining is limited and workarounds are being examined.
Solution Stability | End-to-end solution operating stably in Test with no process blockers or unexplainable pauses/interruptions to processing. | In Progress | Overall solution stability has improved. However, some pre-prod stability issues have been experienced, and there is a Microsoft ticket, resulting in the incorrect writing of data, that is to be resolved (an edge case that we are struggling to reproduce).
Remediation | Known remediation work (internal reports performance, business activity monitoring) completed and remediation for any new defects scheduled. | In Progress | Internal work on Operational Reporting and Business Activity Monitoring continues. Readiness of all key Operational Reports for go live as per AEMO business team expectations remains open and is being discussed with the business.
Performance | “Day in the Life Testing” completed with no performance issues identified that cannot be remedied for 31 May go-live. | In Progress | Some delays have impacted the progress of Day In The Life testing. There has been a performance issue with respect to the time to recover from issues that result in Configuration Data and Standing Data slowing down, which AEMO is remediating.
Production Deployment | Data migration on track and no blockers to meeting criteria/schedule for pre-production deployment. |  | Production data migration has commenced and is on time. Final reviews of cutover timeline are being completed and industry workshop is scheduled.
Industry Test | Retail Industry Testing on track. |  | 2 industry issues identified in from Industry Testing, see overleaf. Overall positive progress by industry in completing assigned test cases.
Emerging Issue | Covid-19 in India | Open | Impacts from escalating Covid-19 situation in India are starting to emerge, notwithstanding the significant and proactive mitigation measures undertaken by TCS. Situation is being monitored with regular reports to the Project and Executive.
Overall |  |  | 31 May go-live is at risk. Go-live decision is subject to executive steering committee approval. Decision dates have been aligned to industry notification dates.

## Slide 8: Industry Test Status

## Slide 9: Industry Testing
Invitation Industry test Progress:
  Test Scenario Status as at 6/5
  Issue Status:
    1 open High , 14 open Medium
  Release planned for 17th May to close multiple items
  No defects that impact multiple participants
  A number of participant issues have resulted from under-speced Preprod environment (being addressed) , will not impact production.
File Length on MTRD transactions:
  Noted impact to multiple participants (2)
  AEMO to update to 45 characters
  Timing of delivery to be confirmed
File naming in MTRD response
  AEMO impact position to retain validation
  Participants to address validation and processing, may require workaround
XML reporting header for RM16, 27, etc optional fields not populated when automatically generated
  Initial feedback:
    One participant impacted – assessing changes required, 2 participants indicate no impact
  AEMO impact assessment in progress - delivery (if committed) will not be in place for 31 May and require some work around
Passed | Failed | Not Complete | No Run | Blocked | N/A | Total
39 | 4 | 12 | 25 | 1 | 10 | 91

## Slide 10: Readiness actions
Cutover Planning:
  Timings for cutover being reviewed, including impacts of extended B2B / B2M outage on business operations
  Confirmation of fix on fail approach to deployment- may extend cutover into Monday rather than implement a rollback
  Establishment of metering data delivery restart approach to incorporate staggered restart
  Refinement of participant impact
NCONUML Delivery:
  Capability may not be available at go-live – but expected to be available mid June
  Impacts to participant NCONUML activation requested, noting available transition plans indicate minimal population during June

## Slide 11: Conclusions and Next Steps

## Slide 12: Next Steps
Email notification to PCF on 14-May
Retail Industry Go-Live Plan – walkthrough session with RWG on 17-May, confirm final details and known defects
Next PCF 19-May will provide an update on status

## Slide 13: Meeting Close
Peter Carruthers