## Sheet1
STRAWPERSON: Industry metering transition - DRAFT for initial discussion with Transition Focus Group - 23 September 2019
CATEGORY | ID | SUB-CATEGORY | ID | ACTIVITY | ASSUMPTIONS | RESPONSIBILITY | ID | DEPENDENCIES | VOLUME/SIZE CONSIDERATIONS | DIRECTLY AFFECTED PARTIES | TRANSITION START DATE | TRANSITION END DATE | RULE / PROCEDURE TIMING | TRANSITION OBJECTIVE / OUTCOME | Comments (by AEMO or from TFG)
METER INSTALLATION AND RECONFIGURATION
| S01 | Type 1-3 meters | A1 | Identify which meters need replacing or reconfiguring | Meter Installation Type Codes in MSATS are correct and reliable | MP |  |  |  | MC, MP |  | 2019-11-30 |  | Type 1-3 meters requiring replacement or reconfiguration identified
|  |  | A2 | Initial assessment of whether data storage exemptions may be required |  | MP | D1 | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2019-11-30 |  | Initial assessment of potential data storage exemptions completed
|  |  | A3 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  | MC |  |  |  | AEMO |  | 2019-12-31 |  | Approach and timframes visible to affected parties
|  |  | A4 | Install or reconfigure meters as required |  | MP | D2 | Accreditation requirements met |  | MP, AEMO |  | 2021-04-30 | By 1 July 2021 | All type 1-3 meters 5min compliant | What is the contingency in situations where the meter can't be replaced or reconfigured e.g. access issue? Readiness reporting to be leveraged to ensure appropriate progress.
|  |  | A5 | Apply for data storage exemptions as required |  | MP | D3 | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2021-04-30 | By 1 July 2021 | Data storage exemptions submitted and assessed | AEMO will need to queue applications. MP's don't any issue here.
| S02 | Subset of type 4 meters - TNI, Market Generator or SGA | A6 | Identify which meters need replacing or reconfiguring |  | MP |  |  |  | MC, MP |  | 2019-11-30 |  | Subset of type 4 meters requiring replacement or reconfiguration identified | Data cleanse of meter installation type codes may be required in MSATS. Same as first issue AEMO to run report.
|  |  | A7 | Initial assessment of whether data storage exemptions may be required |  | MP | D4 | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2019-11-30 |  | Initial assessment of potential data storage exemptions completed | MP'S don't see any issue here.
|  |  | A8 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  | MC |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO |  | 2019-12-31 |  | Approach and timframes visible to affected parties | FRMPs to discuss/determine with MCs/MDPs which meters require reconfiguration and/or upgrades and ensure plans are put in place to ensure 5-minute data provision and AEMO accreditation requirements are met. i.e. ensure contractual arrangements are met. AGL provided an update to the wording in this. MP'S don't see any benefit in providing this. Where required the MP will provide notification and contact customer.
|  |  | A9 | Install or reconfigure meters as required |  | MP |  | Accreditation requirements met |  | MP, AEMO |  | 2021-04-30 | By 1 July 2021 | All subset of type 4 meters 5min compliant | BAU for the MP. Accreditation still be considered.
|  |  | A10 | Apply for data storage exemptions as required |  | MP |  | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2021-04-30 | By 1 July 2021 | Data storage exemptions submitted and assessed | AEMO will need to queue applications
| S03 | Cross Boundary meters (EXISTING) | A11 | Identify which meters need to be installed, replaced or reconfigured |  | MP |  |  |  | MC, MP |  | 2019-11-30 |  | Cross boundary meters which need to be installed, replaced or reconfigured identified | Data cleanse of meter installation type codes may be required in MSATS. Part of the AEMO report
|  |  | A12 | Initial assessment of whether data storage exemptions may be required |  | MP | D1 | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2019-11-30 |  | Initial assessment of potential data storage exemptions completed
|  |  | A13 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  | MC |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO |  | 2019-12-31 |  | Approach and timframes visible to affected parties | FRMPs to discuss/determine with MCs/MDPs which meters require reconfiguration and/or upgrades and ensure plans are put in place to ensure 5-minute data provision and AEMO accreditation requirements are met. i.e. ensure contractual arrangements are met
|  |  | A14 | Install or reconfigure meters as required |  | MP |  | Accreditation requirements met |  | MP, AEMO |  | 2021-04-30 | By 1 July 2021 | All applicable cross boundary meters 5min compliant
|  |  | A15 | Apply for data storage exemptions as required |  | MP |  | Final Data Storage Exemption Procedure published by AEMO |  | AEMO |  | 2021-04-30 | By 1 July 2021 | Data storage exemptions submitted and assessed | AEMO will need to queue applications
| S04 | Cross Boundary meters (GS REQUIRED) | A16 | Identify which meters need to be installed, replaced or reconfigured |  | MP |  |  |  | MC, MP |  | 2020-07-01 |  | Cross boundary meters which need to be installed, replaced or reconfigured identified | Data cleanse of meter installation type codes may be required in MSATS. Part of the AEMO report
|  |  | A17 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration |  | MC |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO |  | 2020-12-31 |  | Approach and timframes visible to affected parties | FRMPs to discuss/determine with MCs/MDPs which meters require reconfiguration and/or upgrades and ensure plans are put in place to ensure 5-minute data provision and AEMO accreditation requirements are met. i.e. ensure contractual arrangements are met
|  |  | A18 | Install or reconfigure meters as required |  | MP |  | Accreditation requirements met |  | MP, AEMO |  | 2021-06-30 | By 6 Feb 2022 | All applicable cross boundary meters 5min compliant
| S05 | New and replacement Type 4 | A19 | Install 5-minute capable meters as required (BAU) |  | MP |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | N/A | N/A | From 1 Dec 2018
| S06 | New and replacement Type 4A | A20 | Install 5-minute capable meters as required (BAU) |  | MP |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | N/A | N/A | From 1 Dec 2019
| S07 | New and replacement VIC AMI meters | A21 | Install 5-minute capable meters as required (BAU) |  | MP |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | N/A | N/A | From 1 Dec 2018
| S08 | New and replacement SAMPLE Meters | A22 | Install 5-minute capable meters as required (BAU) |  | MP |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | N/A | N/A | From 1 Dec 2018
| S09 | Pre-1 Dec 2018/19 Type 4, 4A, VICAMI and SAMPLE meters | A23 | Install 5-minute capable meters as required (BAU) |  | MP |  |  |  | MP, MDP, Retailer NSP, Affected Customer, AEMO | N/A | N/A | From 1 Dec 2018/19
| S10 | SCADA Data | A24 | [6 empty] | AEMO, MDP |  |  |  |  | Will SCADA DATA be provided in 5m and when if the MDP stats sending prior to 1 Jul 2021
| S11 | Special Site | A25 | [6 empty] | AEMO, MDP |  |  |  |  | AEMO need to review Special site calculations
METER DATA DELIVERY
| S12 | Type 1-3, subset of 4 |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - MDPs to provide 30min up until 30 June 2021 and Market Customers to be 5min capable by 1 July 2021 - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 July 2021 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants in period up to 1/7/21 to support retailer / DB readiness requirements
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  | 2021-04-01 | By 1 July 2021 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  | 2021-04-01 | By 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S13 | Cross Boundary meters (EXISTING) |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | Consider MDP aggregation requirements/services to support 'not 5min ready' participants in period up to 1/7/21 to support retailer / DB readiness requirements
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  | 2021-04-01 | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021 for 30 minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  | 2021-04-01 | By 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S13 | Cross Boundary meters (NEW) |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | Consider MDP aggregation requirements/services to support 'not 5min ready' participants in period up to 1/7/21 to support retailer / DB readiness requirements
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  | 2021-04-01 | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021 for 30 minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  | 2021-04-01 | By 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S15 | New and replacement Type 4 |  | Provide forward plan to AEMO and industry |  | MDP | [5 empty] | 2021-07-01 |  | Approach and timframes visible to affected parties | Monitor requirement for B2B process that supports change to 5-minute data delivery
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO, MDP |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | From 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S16 | New and replacement Type 4A |  | Provide forward plan to AEMO and industry |  | MDP | [5 empty] | 2020-06-30 |  | Approach and timframes visible to affected parties | Monitor requirement for B2B process that supports change to 5-minute data delivery
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer | 2021-07-01 |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Aggregation Services consideration not required if metering data delivery transition commences post 1/7/21
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO, MDP |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to AEMO to support five-minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | From 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S17 | New and replacement VIC AMI meters |  | Provide forward plan to AEMO and industry |  | MDP | [5 empty] | 2020-06-30 |  | Approach and timframes visible to affected parties | Monitor requirement for B2B process that supports change to 5-minute data delivery
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer | 2021-07-01 |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants if transtion commences prior to July 2021
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO, MDP |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | From 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S18 | New and replacement SAMPLE Meters |  | Provide forward plan to AEMO and industry |  | MDP | [5 empty] | 2020-06-30 |  | Approach and timframes visible to affected parties | Consideration of responsibility for sample metering andif exemptions required
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer | 2021-07-01 |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants - if transition commences prior to july 2021
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO, MDP |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to AEMO to support five-minute settlement
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | From 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S19 | Pre-1 Dec 2018/19 Type 4, 4A, VICAMI and SAMPLE meters |  | Provide forward plan to AEMO and industry |  | MDP | [5 empty] | 2020-06-30 |  | Approach and timframes visible to affected parties | Monitor requirement for B2B process that supports change to 5-minute data delivery Meters not mandated for migration until replaced
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants
|  |  |  | 5min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  |  | By 1 Dec 2022 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021
|  |  |  | Create/activate export and import (active (kWh) and reactive (kVArh)) energy datastreams in CNDS table |  | MDP |  | - Information from MP as required - AEMO and Participant systems can process register level Datastream CRs e.g. CR4xxx |  | AEMO, MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | From 1 July 2021 | Register level datastreams active in CNDS table as per AEMO procedures
| S20 | Type 7 metering installations |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer |  |  | By 1 July 2021 | MDPs delivering 5min metering data to Participants to support five-minute settlement | Consider MDP aggregation requirements/services to support 'not 5min ready' participants in period up to 1/7/21 to support retailer / DB readiness requirements
|  |  |  | 5min metering data delivered to AEMO (MDFF) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  | 2021-04-01 | By 1 July 2021 | MDPs delivering 5min metering data to AEMO to support five-minute settlement | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021
| S21 | Non-contestable unmetered loads |  | DNSP, MSP and end user agree on profiles and algorithms |  | MDP | [8 empty] | MDPs to coordinate
|  |  |  | AEMO Metering Business approve MDP NCONUML profiles/algorithms |  | MDP | [8 empty] | Avoid potential bottleneck of approvals MDM needs to be live Need to consider interactions between accreditation update requirements and the NCUL approvals (AEMO and industry resourcing impacts). Reaccreditation is dependent on system changes (including NCUL system requirements)
|  |  |  | 5min metering data delivered to Participants (B2B) |  | MDP |  | - Required systems are in place to support 5min data delivery - Accreditation requirements met |  | AEMO (accreditation), MDP, Retailer, Generator, TNSP, DNSP, Customer | Bi - lateral agreement |  | By 1 July 2021 | MDPs delivering metering data to support participant billing of NCUML | Consider MDP aggregation requirements/services to support 'not 5min ready' participants in period up to 1/7/21 to support retailer / DB readiness requirements
|  |  |  | 5min metering data delivered to AEMO (MDFF) |  | MDP |  | - AEMO systems are in place to support 5min data delivery, aggregation and netting as required - MDP Accreditation requirements met |  | AEMO, MDP |  | 2021-04-01 | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | AEMO aggregation capability needs to be in place for 5 and 15min meter data delivery pre-1 July 2021
| S22 | Tier 1 basic metering data |  | Delivery of tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO |  | MDP |  | Required MSATS standing data in place |  | MDP, AEMO |  | 2021-04-01 | By 1 July 2021 | MDPs delivering metering data to support Global Settlement Calculations | Need to ensure MDPs don't send data to the LR where the LR = GLOPOOL
| S23 | Meter data delivery to AEMO for all interval meters |  | All interval meter data delivered to AEMO in NEM 12 MDFF |  | MDP |  | -MDP systems to deliver NEM 12 for settlement in place |  | MDP, AEMO |  |  | From 1July 2021 | MDPs delivering interval data to AEMO via NEM12 MDFF
|  |  |  | 30 min metering data delivered to AEMO (MDFF) (Export and import (active (kWh) and reactive (kVArh)) energy metering data as applicable) |  | MDP |  | - Required systems are in place to support 30 min data delivery - Accreditation requirements met |  | AEMO, MDP |  |  | From 1 July 2021 | MDP's delivering
MSATS STANDING DATA CREATION AND MAINTENANCE
| S24 | Cross-boundary supplies |  | Create cross-boundary NMIs |  | DNSP |  | Cross boundary installations identified and assessed |  | AEMO, MPs, MDPs, Retailers and Generators |  | 2021-06-30 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | Will these NMIs be prohited from being transferred in MSATS? How do we ensure the new NMIs are not objected to erroneously Will the creation of a the second NMI (receiving DB), for the same cross boudary supply, impact Settlements if it created pre 1 Dec 2020
| S25 | Cross-boundary supplies |  | Create Datastreams in MSATS |  | MDP |  | Cross boundary NMIs created in MSATS |  | AEMO, MPs, Retailers, Generators and DNSPs |  | 2021-06-30 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S26 | Cross-boundary supplies |  | Create registers in MSATS |  | MP |  | Cross boundary NMIs created in MSATS |  | AEMO, MDPs, Retailers, Generators and DNSPs |  | 2021-06-30 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S27 | Non-contestable unmetered loads |  | B2BWG to consider potential recommendations to the IEC to better support 1 to many scenarios |  | B2BWG |  |  |  | AEMO, MPs, MDPs, Local Retailers, Generators, TNSPs and DNSPs |  | 2019-11-30 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S28 | Non-contestable unmetered loads |  | Create NCUL NMIs in MSATS | 1 part process i.e. NMIs are to be created when the new NCUL NMI Class Code is available in MSATS | DNSP |  | Dependent on NMI Class Code timings |  | AEMO, MPs, MDPs, Local Retailers, and Generators |  | 2021-04-01 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S29 | Non-contestable unmetered loads |  | Create Datastreams in MSATS |  | MDP |  | NCUL NMIs created |  | AEMO, MPs, Local Retailers, and Generators |  | 2021-04-01 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S30 | Non-contestable unmetered loads |  | Create registers in MSATS |  | MP |  | NCUL NMIs created |  | AEMO, MDPs, Local Retailers, and Generators |  | 2021-04-01 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021
| S31 | New NMI classification codes - BULK |  | Update NMI Class Codes for existing NMIs as required |  | TNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S32 | New NMI classification codes - NCUL |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  | 10's of thousands | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S33 | New NMI classification codes - DWHOLESAL |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S34 | New NMI classification codes - NREG |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S35 | New NMI classification codes - XBOUNDRY |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S36 | New NMI classification codes - GENERATR |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S37 | New NMI classification codes - WHOLESAL |  | Update NMI Class Codes for existing NMIs as required |  | DNSP |  |  |  | AEMO and Retailers |  |  | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | NMI Discovery impact i.e. not recognised code AEMO to monitor application of certain codes e.g. NREG Can we decouple NMI request vs NMI COM? If market customers are not ready early then the risk profile goes up! AEMO to provide Participants a list of NMIs, including their NMI Classification Code, which they believe needs to be updated for reconciliation/validation purposes.
| S38 | LR and FRMP fields |  | Update LR and FRMP to GLOPOOL for existing NMIs as required |  | AEMO |  | Bulk update capability and processes are in place | Significant | AEMO and All Participant Types |  | 2022-02-05 | 2022-02-06 | To remove the financial liability of Retailers for bulk connection points | Updates must be effective 6 Feb 2022 Consider opt in opt out out independent update (shared script rules) options In flight CRs will be included in the updates
| S39 | Tier 1 basic meter datastreams |  | Create/activate tier 1 basic meter datastreams as required |  | MDP |  | Potential for bulk update assistance from AEMO | Significant | AEMO and Local Retailers |  | 2021-04-01 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | Bulk update capability and processes may be required Check to see if a NMI cteate activity is required e.g. Tasmania
| S40 | VIC TUOS datastreams |  | Update Datastream type codes associated with VIC TUOS |  | MDP |  | Required updates identified |  | AEMO and MDPs |  |  | By 1 July 2021
| S41 | Meter installation type code in MSATS |  | Complete data cleanse of meter installation type code in MSATS |  | MP | [5 empty] | 2019-11-30 | By 1 July 2021 | To support the calculation of UFE from 1 July 2021 | Industry feedback is that metering type code data is inconsistently applied.
METERING ACCREDITATION UPDATES
| S42 | MP accreditation update |  | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  | MP | [8 empty] | AEMO needs to manage reaccreditation, uses queues, can take over a month to complete each application
|  |  |  | Confirm scope/scale of change with AEMO |  | MP
|  |  |  | If needed, apply for accreditation update |  | MP
| S43 | MDP accreditation update |  | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation |  | MDP
|  |  |  | Confirm scope/scale of change with AEMO |  | MDP
|  |  |  | If needed, apply for accreditation update |  | MDP