## Slide 1: NOTES 5MS/GS Transition Focus Group #6: Implementing the Metering transition plan
Monday 6th April, 2020
WEBEX ONLY
This slide pack was developed for the Transition Focus Group meeting. This version of the slides has been annotated with notes from the meeting. These additional notes either in blue text or are on new slides that have a yellow background.

## Slide 2: Attendees
Organisation | Attendee
ActEW AGL | Jeff Roberts
ActEW AGL | K Nguyen
AEMO | Anne-Marie McCague
AEMO | Austin Tan
AEMO | Blaine Miner
AEMO | Craig Shelley
AEMO | Emily Brodie
AEMO | Greg Minney
AEMO | Paul Lyttle
AEMO | Simon Tu
AGL | Pieter Wijtzes
Aurora | Paul Willacy
Ausnet | Con Michailides
Citipower | Arif Syarifuddin
Citipower | Clare Yap
Organisation | Attendee
Citipower | Greg Szot
Citipower | Mark Pillkington
Citipower | Ron Dittman
Electranet | Ramesh Khadka
Endeavour | Dino Ou
EnergyAustralia | Jon Ham
EQ | Nicole Bright
EQ | Terry Lodge
Ergon Retail | Ingrid Farah
Essential Energy | Curtis Dora
Essential Energy | Tim Lloyd
Intellihub | Warren van Wyk
Jemena | Rajiv Balasubramanian
Jemena | Matthew Mullen
Metering Dynamics | Cindy Matthews
Organisation | Attendee
Metering Dynamics | Jonathan Briggs
Metering Dynamics | Steve Smith
Mondo | Kam Vessali
Origin | Mario Iogha
Plus ES | Linda Brackenbury
Powercor | Lalitha Shankar
Powermetric | Snehal Jogiya
Red/Lumo | Mark Reid
SAPN | David Woods
Simply | Aakash Sembey
Stanwell | Elizabeth Byrne
TasNetworks | Adrian Honey
United Energy | David Hangar
United Energy | Larry Lara
Vector | Paul Greenwood

## Slide 3: Consolidate meeting actions
Topic | Action | Responsibility | Due date
Changes to AEMO’s Meter Data Validation Framework | TFG to propose valid use cases for the 3 rejection scenarios | TFG | Thu 30 Apr
MTP activities: Clarifications and approaches | AEMO to circulate a draft template relating to the conversion of Dec 2022 meters to the TFG. | AEMO | Thu 30 Apr
 | TFG to provide indicative timing as to when participants intend to send or receive 5-min metering data (assuming 5MS commencement of 1 July 2021) | TFG | Thu 30 Apr
 | AEMO to provide a template to the TFG to support MDPs providing their conversion plans to AEMO | AEMO | Thu 30 Apr
 | AEMO to provide confirmation to TFG on the NCONUML algorithm approval process, taking into consideration how to apply, lead time required for approval and whether there is a template for profiles and algorithms | AEMO | Thu 30 Apr

## Slide 4: Agenda
NO | Time | AGENDA ITEM | Responsible
Preliminary Matters |  |  | 
1 | 10:00 - 10:10 | Welcome and introduction | Greg Minney
2 | 10:10 – 10:25 | Notes/actions from previous meeting | Greg Minney
For noting |  |  | 
3 | 10:25 – 10:30 | Changes to the MTP since the previous meeting | Blaine Miner
4 | 10:30 – 10:45 | Transition of Net datastreams to register level datastreams | Blaine Miner
5 | 10:45 – 10:50 | Accreditation update activities | Craig Shelley
For discussion |  |  | 
6 | 10:50 – 11:00 | Changes to AEMO’s Meter Data Validation Framework | Simon Tu
7 | 11:00 – 11:30 | MTP activities: Clarifying activity intent Clarifying approach | Greg Minney Blaine Miner Paul Lyttle
BREAK 11:30 – 11:40 |  |  | 
8 | 11:40 -12:40 | MTP activities continued | Greg Minney and Blaine Miner
9 | 12:40 – 12:55 | Readiness reporting: How to reflect progress in responses Upcoming activities | Austin Tan
General business |  |  | 
10 | 12:55 – 13:00 | Next steps and general questions | Greg Minney
 | APPENDIX | Refresher on 5MS and GS metering and metering data obligations | 

## Slide 5: Introduction
Greg Minney

## Slide 6: 5MS/GS and Covid-19 implications
Risk was raised at March PCF in relation to the impact Covid-19 may have on Industry’s and AEMO’s 5MS and GS implementation programs
Risk was discussed at Executive Forum in March and the following actions were taken:
  Risk to be monitored through PCF
  Question(s) to be added to the Industry Readiness Questionnaire in relation to the impacts of Covid-19 and the mitigation measures
PCF discussion on industry impact this Thursday, 9 April
This TFG meeting will focus on 5MS/GS implementation given that COVID-19 discussions are currently being managed by the PCF.

## Slide 7: Session objectives and expectations
Increase clarity and understanding of activities in the MTP
Confirm those areas where:
  AEMO support may be required by participants
  Implementation approaches to activities need elaborating
Share plans and approaches across impacted participants
Support ongoing participant work programs
Confirm next steps for TFG

## Slide 8: Notes and actions from previous meeting
Greg Minney

## Slide 9: Actions from TFG #5 (28 Feb 20) – 1/3
Topic | Action | Responsibility | Response
5min data delivery agreements | AEMO to include reference to type 7 metering in the ‘context slide’ | AEMO | Complete
 | Participants to seek Legal advice as required in relation to NER 7.10.5. | Participants | Ongoing - Close
 | Participants to engage other Participants early to discuss the potential delivery of 5-min metering data pre-1 July 2021. | Participants | Ongoing – Close
 | Participants to advise AEMO when they believe they will deliver or receive 5-min metering data. | Participants | 6 responses received: 3 retailers indicated they will start receiving 5-min data from 1 Jul 2021 1 retailer and 1 DNSP indicated they will be able to receive 5-min data from approx. Q1, 2021 1 MDP indicated it will be able to send and receive 5-min data from Nov 2020, and will aggregate to 15-min or 30-min data as required until 1 Jul 2021 or thereafter.
 | AEMO to publish list of participants’ intentions on their timing for delivering or receiving 5-minute metering data. | AEMO | Responses from most TFG members still outstanding
5-min metering data delivery for Type 4/4A… | AEMO and TFG to monitor and consider implications of changes being discussed in the ERCF | AEMO & Participants | Ongoing
Non-contestable unmetered loads | AEMO to confirm number of prospective days a datastream can be created | AEMO | Complete

## Slide 10: Actions from TFG #5 (28 Feb 20) – 2/3
Topic | Action | Responsibility | Response
Tier 1 basic meters | Participants to determine if additional support is required from AEMO to complete these MTP activities | Participants | 5 responses received: 3 advised that no additional support needed 1 retailer needs advanced notice of MC/MP plans for installations/reconfigurations (has system dependencies), but did not indicate the need for additional support from AEMO 1 indicated it would seek assistance at a later time if required
 | Participants to determine if specific CR notification considerations should be applied to these updates | Participants | 5 responses received: No specific CR notification considerations raised
Alignment of meter RegisterIDs and Suffixes | AEMO and Participants to monitor discussions at the ERCF and Standing Data Review which may impact TFG considerations | AEMO & Participants | Ongoing
 | Participants to raise items which need to be considered for this MTP activity | Participants | 6 responses received: Items to be discussed in this TFG

## Slide 11: Actions from TFG #5 (28 Feb 20) – 3/3
Topic | Action | Responsibility | Response
Updates to GLOPOOL | Participants to provide feedback regarding AEMO proposal and engagement with the SWG | Participants | 6 responses received: Items to be discussed in this TFG
Updates to the MTP | AEMO to update Special Sites and VIC TUoS items in the MTP | AEMO | Complete
Next Steps | AEMO to add an ‘approach’ column into the MTP to communicate agreed methodologies/options in delivering a particular activity | AEMO | Complete

## Slide 12: Updates to the MTP
Blaine Miner

## Slide 13: Updates to the MTP since previous meeting
Update | SC / Activity References | Reasoning
Aligned the ‘Transition Start Dates’ relating to the creation of register level datastreams to AEMO being able to receive MDFF (1 Feb 2021) | A36, A40, A45, A51, A57, A63, A69, A75, A81 | The creation of register level CNDS records introduces the requirement for MDPs to provide register level metering data for that meter to AEMO. This cannot occur if AEMO’s MDFF capability is not available.
Subcategory relating to the meter data delivery of ‘Pre-1 Dec 2018/19 Type 4, 4A, VICAMI and SAMPLE meters’ has been removed | SC21 | This meter ‘group’ is not relevant to 5MS Readiness. Should any of these meters be replaced they would then be captured under other existing SCs (SC17-20)
SC relating to the requirement to complete a data cleanse of RegisterIDs and ‘Suffixes’ has been moved to the activity level under each applicable meter type | Removed - SC40 Added - A36a, A40a, A45a, A57a, A63a, A69a, A75a, A81a | By placing this requirement at the activity level, against each applicable meter type, it allows for the application of the appropriate transition end date e.g. Type 1-3, subset of 4 to be cleansed by 31 May 2021 vs Type 4 to be cleansed by 15 Jan 2022
Updated ‘Transition End Dates’ to 30 Nov 2022 for meter types that must deliver 5min metering data by 1 Dec 2022 (includes B2B and B2M related activities) | A54, A56, A60, A62, A66, A68 | To align to the 5MS Rule requirements

## Slide 14: Transition of Net datastreams to register level datastreams
Blaine Miner

## Slide 15: Context
With the introduction of the 5MS & GS Rule requirements, a more granular and global source of reference data is required.
To support this requirement, Net CNDS records will be gradually replaced by Register Level CNDS records.
AEMO will be publishing a clarification document shortly to provide specific guidance on how this transition will occur.
  Current Service Level Procedure: MDP Services requirement (3.7.1):
  (e) aggregate interval metering data for a connection point into a 30-minute interval net Datastream prior to delivery to AEMO as required by the MSATS Procedures, MDM Procedures and NMI Procedures;
  New 5MS Service Level Procedure: MDP Services requirement (2.4.1):
  (v) for Datastream Suffix(s) corresponding to interval metered connection points, update the Datastream Suffix value from ‘N’ to Register level (E1,B1) when:
      (A) a new metering installation is installed at a connection point; or
      (B) a configuration within an existing meter or metering equipment is updated.

## Slide 16: AEMO CNDS & Meter Data Clarifications Overview
This clarification document will include:
  Background
    5MS Rule
    CATS CNDS Table
    Key Metering ‘Go-live’ dates
  CNDS Records
  CNDS DataStreamType Codes
  ADL in CNDS
  CNDS & Meter Data Delivery
  CNDS & Procedures
  Scenarios - Net & Register level CNDS records

## Slide 17: Examples of some of the clarifications
Active Net CNDS records will still exist in some instances post 1 July 2021
Net CNDS record must be deactivated with an end date prior to the effective date of the Register Level CNDS record
Net CNDS records cannot be created from the start of 5MS, currently scheduled for 1 July 2021, with an effective date equal to or greater than 1 July 2021
An Interval Register Level CNDS record cannot be replaced by a Net CNDS record
Interval Register Level CNDS records must reflect a DatastreamType of ‘I’, ‘P’ or ‘N’.
Once an interval Register Level CNDS record has been created, an MDP must send AEMO meter data in MDFF from the date the Register Level CNDS record was created.
AEMO’s preference is for MDPs to transition Net records to Interval Register level CNDS records as soon as possible, after the AEMO MDFF Go-Live (~1/2/21)
AEMO Process | Mandatory CNDS Records (as per NMI Procedures)
NEM Settlements | DatastreamSuffix = ‘E’, ‘B’, ‘A’ & ‘D’
UFE Analysis | DatastreamSuffix = ‘Q’, ‘K’, ‘P’ & ‘J’
VIC TUoS: NEM Settlements | DatastreamSuffix = ‘E’, ‘B’, ‘A’ & ‘D’
VIC TUoS: UFE analysis | DatastreamSuffix = ‘Q’, ‘K’, ‘P’ & ‘J’
VIC TUoS: Billing | DatastreamSuffix = ‘F’, ‘C’, ‘R’ & ‘L’

## Slide 18: Valid 5MS DataStreamSuffix and DataStreamType Code ‘Combinations’
 | First character |  |  |  |  |  |  |  | 2nd character
 | Ave | DatastreamType | Master | DatastreamType | Check | DatastreamType | Net | Datastream Type | Meter numbers or measuring elements are to be 1-9 then A-H, J-N, P-Z
IMPORT kWh | A | I or N for Virtual NMI’s | B | I or N for Virtual NMI’s | C | N | N | I or P | 
EXPORT kWh | D | I or N for Virtual NMI | E | I, P or N for Virtual NMI’s | F | N |  |  | 
IMPORT kvarh | J | N | K | N | L | N | X | N | 
EXPORT kvarh | P | N | Q | N | R | N |  |  | 
KVAh | S | N | T | N | U | N |  |  | 
Power Factor pF |  |  | G | N |  |  |  |  | 
Q Metering Qh |  |  | H | N | Y | N |  |  | 
Par Metering parh |  |  | M | N | W | N |  |  | 
VOLTS (or V2h) or Amps (A2h) |  |  | V | N | Z | N |  |  | 
First Character |  | Second Character | Datastream Type
1 | First Datastream | Meter numbers are to be 1-9 then A-H, J-N, P-Z. | C
2 | Second Datastream |  | 
3 | Third Datastream |  | 
4 | First controlled load Datastream |  | 
5 | Second controlled load Datastream |  | 
6 | Third controlled load Datastream |  | 
7 | First LNSP/ENM defined Datastream |  | 
8 | Second LNSP/ENM defined Datastream |  | 
9 | Third LNSP/ENM defined Datastream |  | 
Net & Register Level CNDS Records
Accumulation CNDS Records
Tables provide the valid ‘combinations’ between DataStreamType codes and the first character of the ‘ElectricityDataStream/Suffix’ value.
With consideration to the physical configuration of an individual meter and/or Metering Installation, DataStreamSuffixes highlighted in GREEN reflect AEMO required ‘combination’s from the AEMO MDFF Go-Live (Feb 2021) and not prior to this date.

## Slide 19: Scenario 8: An interval metered NMI with Master, Check and Logical Meters
 | Physical Meter | CATS_Meter_Register, ‘Suffix’ | CATS_NMI_Data_Stream |  | 
 |  |  | ‘DataStreamSuffix’ | ‘DataStreamType’ | ADL
Current State – Master Meter | Ex Bx Qx Kx | Ex Bx Qx Kx | Nx | I | 500
Current State – Check Meter | Fx Cx Rx Lx | Fx Cx Rx Lx | N/A | N/A | N/A
Current State – Logical Meter | Dx Ax Px Jx | Dx Ax Px Jx | N/A | N/A | N/A
Final State – Master Meter | Ex Bx Qx Kx | Ex Bx Qx Kx | Ex Bx Qx Kx | N N N N | 0 0 0 0
Final State – Check Meter | Fx Cx Rx Lx | Fx Cx Rx Lx | Fx Cx Rx Lx | N N N N | 0 0 0 0
Final State – Logical Meter | Dx Ax Px Jx | Dx Ax Px Jx | Dx Ax Px Jx | I I N N | 15 0 0 0
  Within RM29 reporting, AEMO will identify unexpected combinations across all active CNDS records for a NMI.

## Slide 20: NOTES: CNDS & Meter Data clarification overview
Discussion around Ausnet’s ICF to the ERCF requesting the removal of the procedural requirement to align the RegisterID and the Suffix in MSATS’s CRI table. AEMO stated that the TFG must assume that the requirement remains in place for transition planning purposes. Should the obligation be removed from the procedures as a result of the ERCF process, then the associated MTP activities would be removed.
Ausnet asked why the transition requirement was that RegisterID equals the Suffix needs to be completed by Feb 2022. AEMO responded that that is the effective date of the corresponding procedure.
AEMO noted that this alignment activity has no direct impact on market critical processes and that Participants can decide when to schedule their alignment activities to comply with the procedure.
EnergyQueensland sought confirmation that the date transition window for the required conversion of Net to Register level CDNS records is between MDFF Go Live (1 Feb 2021) and the 31 May 2021. AEMO confirmed that was correct.
Endeavour sought clarification on whether MDPs were expected to change from net to register level for all datastreams associated to a NMI at the same time, or if a ‘mixture’ of levels is permitted. AEMO responded that the expectation is that all datastreams associated with a NMI should be updated at the same time and should be at the same level.
Endeavour asked about MSATS validations for datastream creation. AEMO stated that Participants won’t be able to create net datastreams with an effective date of 1 July 2021 or later. This requirement will be enforced through a combination of system validations and reporting. System logic will stop the creation of new N datastreams and there will be some very basic validations at CR levels “after the fact” to make sure Participants are meeting SLA requirements.
Mondo raised a question regarding the availability of reports for VIC TUOS. AEMO noted that VIC TUOS is an existing AEMO internal process that will be covered by RM11 and RM37 metering data reports, but not in settlement reports. The conversion of VIC TUOS DataStreamType codes will also be monitored through AEMO reporting.

## Slide 21: Accreditation activities
Craig Shelley

## Slide 22: MSP accreditation updates: Observations
Background
5MS/GS MSP accreditation update plan sets out the process and timing for:
  MSPs to assess the need for an accreditation update
  MSPs to apply for an accreditation update where necessary
  AEMO to process accreditation update applications
Progress to date
Most MSPs have returned their accreditation readiness surveys, AEMO following up those who have not
About 1/3 of pre-accreditation meetings have been completed (MTP due date is 30 June 2020)- on track.
AEMO planning for accreditation processing is underway
AEMO encourage MSP’s to review the Qualification Procedure which provides the process to be taken regarding re-accreditation in conjunction with the MSP accreditation update plan.

## Slide 23: Changes to AEMO’s Meter Data Validation Framework
Simon Tu

## Slide 24: Changes to AEMO’s Meter Data Validation Framework
Background
In an early Joint Metering Focus Group meeting (Nov 2018), attendees discussed the potential inefficiencies caused by the delays in updating NMI standing data in MSATS for the delivery of metering data to AEMO and Participants
Although from a Procedural perspective, MDPs are not meant to send metering data until the MSATS standing data is in place, AEMO took an action to consider how AEMO’s 5MS systems may be able to alleviate this issue for Industry in a 5MS environment

## Slide 25: Changes to AEMO’s Meter Data Validation Framework
AEMO’s considerations
In establishing the new validation framework for B2M MTRD, AEMO reviewed the following B2M MDMT rejection rules:
  Rejecting Metering Data for Data Streams not established in CATS NMI Datastream (CNDS).
  Rejecting Metering Data for NMIs not established in CATS NMI Data (CND).
  Rejecting Metering Data sent by a participant not associated to a NMI in CATS NMI Participant Relationships (CNPR)
AEMO’s findings
AEMO will be able to accommodate scenario (a) and (b) and will, instead of rejecting the metering data, accept and create an informational warning in the associated Transaction Acknowledgment.
AEMO unfortunately cannot accommodate scenario (c) and will continue to reject Metering Data sent by a participant not in the CNPR role.

## Slide 26: Notes: Changes to AEMO’s Meter Data Validation Framework
EvoEnergy asked if AEMO will be using existing MDM exception codes to support this process. AEMO confirmed that it will where possible. 5MS Validation matrix can be found at:
    https://www.aemo.com.au/-/media/files/electricity/nem/5ms/systems-workstream/2019/meter-data-validation-matrix.xlsx
Stanwell enquired about the tech spec to which the metering data validation relates, whether it will be updated and what is the impact would be to participants. AEMO responded that upcoming changes will be published soon and the tech spec is called “MSATS technical specification for metering data”.
  https://www.aemo.com.au/-/media/Files/Electricity/NEM/IT-Systems-and-Change/2019/MSATS-Release-Schedule-and-Technical-Specification---5MS---Meter-Data.pdf
Mondo asked, should an MDP fail to retain accreditation, will the metering data delivered by that MDP be rejected by AEMO’s systems? AEMO stated that the system does not enforce accreditation, it ensures that the MDP sending the data is the correct MDP as per the NMI Participant relationships table.
Mondo asked if the failure to retain accreditation is covered by the contingency plan. AEMO confirmed that it was and that if this situation occurred the MC would be responsible for resolving any flow on issues.
Endeavour Energy questioned the validity of the 3 scenarios specified
***ACTION*** TFG to propose valid use cases for the 3 rejection scenarios.
Endeavour Energy questioned the benefit of AEMO sending out informational warnings as Participant systems may not be configured to raise these occurrences for investigation. AEMO only sends informational warnings if there is a problem with the standing data. Participants can choose to use informational warnings to improve their exception processes or can choose to ignore them.

## Slide 27: MTP activities: Clarifications and approaches
Greg Minney and Blaine Miner

## Slide 28: MTP activities: Clarifications and approaches
Objectives
To ensure Participants understand the intent of the activities contained in the MTP
To agree required approaches where applicable
To confirm required support from AEMO

## Slide 29: MP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Identify which meters need replacing or reconfiguring | S01/A1, S02/A6, S03/A11, S04/A16, S05/A22 | Participant discretion | Nothing requested at this stage | 
Assess and apply for data storage exemptions | S01/A2 & A5, S02/A7 & A10, S03/A12 & A15, S04/A18 & A21 | Participant discretion | Process data exemption requests | 
Install or reconfigure meters as required | S01/A4, S02/A9, S03/A14, S04/A20, S05/A24, S06/A25, S07/A26, S08/A27, S09/A28, S10/AA29 | Participant discretion | Nothing requested at this stage | 
Complete RegisterID to ‘Suffix’ data cleanse | S13/A36a, S14/A40a, S15/A45a, S17/A57a, S18/A63a, S19/A69a, S20/A75a | Until the requirement has been removed, we need to plan for an appropriate transition e.g. timing and preferred approach | Dependent on agreed approach | AEMO and Participants to monitor discussions at the ERCF and Standing Data Review
Create Registers in MSATS | S26/A97, S27/A101, S27a/A101c | Updates to occur via CATS CRs | Notification mgt potentially | 
Complete data cleanse of Meter Installation Type codes | S39/A121 | Updates to occur via CATS CRs | Notification mgt potentially | 
Assess and apply for Accreditation Updates | S41/A123&A124&A125 S42/A127&A128&A129 | AEMO accreditation workflow | Assessment and application support | 

## Slide 30: NOTES: MP ‘Responsible’ MTP Activities
AEMO reiterated that the MP activities associated to the identification of which meters needed replacing or reconfiguring should have now been completed, except for ‘unknown’ cross-boundary meters which needs to be identified by 30 June 2020. The approach as to how to identify these meters was left to the MPs, however, AEMO has provided a template for industry use to ensure that relevant and consistent information is being provided, including at risk sites and remediation plans.
AGL sought clarification that if FRMPs (or other parties) wanted to input into an MP’s meter rollout plan that they should approach the relevant MP directly. AEMO confirmed that this was its understanding.
AEMO noted that there is a procedural requirement relating to the completion of a RegisterID to ‘Suffix’ data cleanse. Until such time that the procedure requirement is removed, the TFG will need to determine an appropriate approach for this activity.
Ausnet sought clarification as to whether the approach for MTP A69 (data cleanse) would be addressed by the CNDS clarification document. AEMO noted that the paper focused on the CNDS table and not the CRI table.
Metering Dynamics enquired about whether the expectation was to start aligning RegisterIds, datastreams and MDM contributory suffix now. AEMO noted it was up to individual organisations to decide when and how they would fulfil with obligation.
Metering Dynamics asked whether AEMO was still considering if the ADL would remain at the datastream level in a 5MS environment. AEMO noted that the conversation regarding the application of the ADL has commenced in the ERCF and that the TFG would continue to monitor its progress.
AEMO noted that a complete data cleanse of Meter Installation Type codes was a broad brush activity with emphasis on type 1-3 and 4* meters. AEMO didn’t expect a significant volume of CRs being generated as a result of this activity, however, should industry believe that this will not be the case, then the TFG should consider notification management processes.
Vector enquired about whether AEMO would provide a template for MPs to report meter transition plans for the December 2022 meters. AEMO stated that it will circulate a template for TFG consideration.
**ACTION**: AEMO to circulate a draft template relating to the conversion of Dec 2022 meters to the TFG.

## Slide 31: MDP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Agreement to allow the delivery of 5min metering data pre-1 July 2021 | S13/A32 & A34, S14/A37 & A39, S15/A42 & A44, S16/A47 & A49, S17/A53 & A55, S18/A59 & A61, S19/A65 & A67, S20/A71 & A73, S22/A84 & A85, S23/A88 & A91 | AEMO/Participants to engage other Parties as required Participants to advise AEMO of indicative 5min delivery/reception dates AEMO to publish list of participant timings | AEMO must be a party to any agreement as per the NER | 
5min metering data delivered to Participants (B2B) | S13/A33, S14/A38 S15/A43, S16/A48, S17/A54, S18/A60, S19/A66, S23/A82, S23/A90 | As per Participant project plans | Nothing requested at this stage | 
Register level 5min metering data delivered to AEMO (via MDFF) | S13/A35, S14/A41 S15/A46, S16/A50, S17/A56, S18/A62, S19/A68, S20/A74, S22/A86 S23/A92, S23/A94, S38/A120a | As agreed between an MDP and AEMO | Bi-lateral party | AEMO expected to require 5min metering data from Feb 2021
Create/activate register level CNDS records | S13/A36, S14/A40 S15/A45, S16/A51, S17/A57, S18/A63, S19/A69, S20/A75, S26/A83, S26/A96, S27/A100, S27a/A101b, S36/A117&A118 | Updates to occur via CATS CRs Notification mgt to be determined | Nothing requested except for potential notification mgt support | CNDS clarification document to be published mid-April

## Slide 32: MDP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Provide forward plan to AEMO and industry | S17/A52, S18/A58, S19/A64, S20/A70 | Each MDP Rollout plan is to include: transition window, volumes, ramp rates and overall approach e.g. jurisdictional, distribution area, Retailer. All ‘Required meters’ under the 5MS Rule must be included Application of a common template and the provision of periodic updates | AEMO to consolidate rollout plans and provide information and advice to the TFG | TFG to determine preferred template
NCUL profiles and algorithms | S23/A89 | MDPs to provide NCUL profiles and algorithms for AEMO approval | Approval related support | 
Delivery of tier 1 basic meter metering data (Actuals, Subs and Forward Estimates) to AEMO | S24/A93 | Timing and approach to be determined by the MDPs | Nothing requested at this time | Tier 1 basic meter reads can be provided to AEMO today and must be provided from 1 April 2021
Update (remove/add) new DataStreamType codes as required | S37/A119, S38/A120 | Updates to occur via CATS CRs Notification mgt considerations to be determined | Nothing requested except for potential notification mgt support | CNDS clarification document to be published mid-April
Finalise Accreditation Updates as required | S43/A131-133, S44/A135-137 | AEMO accreditation workflow | Assessment and application support | 

## Slide 33: NOTES: MDP ‘Responsible’ MTP Activities
Discussion regarding industry agreements to allow the delivery of 5-min metering data before 5MS commencement. Origin questioned if Participants are likely to want 5-min metering data early for a subset of meters only e.g. may want early 5-min data for Types 1-3 meters, but 30-min data for all others.
EnergyAustralia sought clarification around whether AEMO needed to be a party to any agreement for early delivery of 5-min metering data associated to NCONUML. AEMO responded that the NER requires the Retailer, DNSP, MDP and AEMO to be party to any agreement for metering data delivery that is in “sub-multiples” of the current Rule’s trading interval.
AEMO noted MDPs are required to provide conversion plans to AEMO and industry for type 4/4A/VIC AMI meters by the end of June. AEMO will provide a template for this activity to ensure information in provided in a consistent manner. At the last TFG it was agreed that the following key elements needed to be included in the plans: transition window, volumes, ramp rates and overall approach. AEMO noted that Industry may need to provide updates to the conversion plans so that AEMO and Industry have up-to-date information to make informed decisions regarding transition activities.
Ausnet enquired about what notifications were expected to be generated as a result of the 5-min MDP conversions. AEMO noted that should the ERCF approve the use of the ReadType field to communicate a meter’s trading interval granularity, that this would likely result in a material volume of CRs being initiated. Ausnet noted its agreement and that for its business, only a Read type code change would impose CATS CRs to be raised.
EnergyQueensland raised a question about the process to receive approval of NCONUML profiles and algorithms. AEMO noted that the process is currently under consideration within AEMO.
**ACTION: TFG to provide indicative timing as to when participants intend to send or receive 5-min metering data
**ACTION: AEMO to provide a template to the TFG to support MDPs providing their conversion plans to AEMO
**ACTION: AEMO to provide confirmation to TFG on the NCONUML algorithm approval process, taking into consideration how to apply, lead time required for approval and whether there is a template for profiles and algorithms.

## Slide 34: MC ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Provide visibility of approach / timeframe for required meter replacement or reconfiguration | S01/A3, S02/A8, S03/A13, S04/A19, S05/A23 | Populate template provided by AEMO Provide periodic updates | Consolidation of information and provision of information to RWG/TFG | Template provided by AEMO Periodic updates required to manage progress and risks/issues (new activities for MTP)
For any registered ‘Special Site’ (as defined in the ‘Special Sites and Technology Related conditions within the National Electricity Market Version 1.2), update and distribute algorithms adjusted for introduction of 5 minute interval length to AEMO, FRMP and LNSP for approval. | S12/A31 | TBD | AEMO part of the approval process | 

## Slide 35: LNSP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Create NMIs: Cross-boundary NCULs SASCALE | S26/A95, S27/A98a & A99 S27a/A101a | NCULs- Wait for new NMI Classification Code to be available and then create required NMIs (eliminates erroneous transfer risks) | Nothing requested at this stage | 
Update NMI Class Codes: NCONUML DWHOLESAL NREG XBOUNDRY GENERATR | S29/A105, S30/A107, S31/A109, S32/A111, S33/A113 | Updates to occur via CATS CRs Notifications are not expected to be supressed | Monitoring of NCC application where possible | Updates are the responsibility of the LNSP and are to be performed using CATS CRs
Determine and engage Metering Coordinator (after Global Settlement market commencement on 6 February 2022) | S04/A17 |  | Nothing requested at this stage | 

## Slide 36: TNSP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Update NMI Class Codes: BULK WHOLESAL | S28/A103, S34/A115 | Updates to occur via CATS CRs Notifications are not expected to be supressed | Monitoring of NCC application where possible | Updates are the responsibility of the TNSP and are to be performed using CATS CRs

## Slide 37: FRMP ‘Responsible’ MTP Activities
Activity | SC & Activity References | Proposed Approach | Support from AEMO | Comments
Ability to receive and process new NMI Classification Codes: BULK NCONUML DWHOLESAL NREG XBOUNDRY GENERATR WHOLESAL | S28/A102, S29/A104, S30/A106, S31/A108, S32/A110, S33/A112, S34/A114 | Updates to occur via CATS CRs Notifications are not expected to be supressed | Nothing requested at this stage | By 30 April 2021

## Slide 38: ‘Other’ MTP Activities
EvoEnergy enquired about which system release will provide industry with the ability to update NMI classification codes. AEMO stated that it was intended to be in the Nov 2020 xml release and the Dec 2020 MDM platform release. However, the MTP will ultimately guide industry as to when the codes should actually be used in production.
AEMO stated that TNSPs will need to update NMI Classification Codes for BULK and WHOLESAL. It noted that “WHOLESAL” is an existing code but that its definition is changing under 5MS.
Endeavour asked why the GENERATR code was not listed under TNSP responsibilities. AEMO responded that the GENERATR code shouldn’t change unless it is to NREG or DWHOLESALE (generation connected to a distribution network). GENERATR is to be used for transmission network connections only.
Mondo sought clarification around whether the “agg flag” will still be set to ‘N’ for Generator and ‘Y’ for Wholesale. AEMO noted that the 5MS NMI Procedure specifies in what instances the “agg flag” should be ‘Y’ as opposed to ‘N’ for all NMI Classification Codes (Appendix E).

## Slide 39: FRMP/LR updates (GLOPOOL)
It is AEMO’s intention to perform bulk updates for:
  LR Participant ID on all Distribution connection points to ‘GLOPOOL’ (excluding Embedded Networks)
  FRMP Participant ID on all Bulk Supply Points (TNIs) and Cross Boundary connection points to ‘GLOPOOL’
Updates to be effective 6 Feb 2022 and run as part of GS go-live process
No notifications to be sent out from MSATS. AEMO proposes to:
  Provide ‘Update logic’ to Participants
  Fast-track in-flight CRs prior to bulk updates being applied (similar process to POC)
  Provide Reconciliation files to FRMPs
    AEMO’s initial view on providing files to other Participant types
MSATS validations will be in place to ensure accurate LR and FRMP maintenance from GS Go-live

## Slide 40: NOTES: FRMP/LR updates (GLOPOOL)
AEMO confirmed that the change to GLOPOOL will become effective on the GS financial go-live date e.g. 6 Feb 2022.
The exact system approach to support the updates is still being considered.
A Participant asked if the bulk update would only apply to the LR updates i.e. FRMP updates would occur via CATS CRs. AEMO stated that it is currently expected that the bulk updates would cover both LR and FRMP GLOPOOL updates.
Energy Queensland sought confirmation that reconciliation files for GLOPOOL updates would be provided to all Participant types i.e. not just FRMPs. AEMO noted that the generation of the reconciliation files is expected to be very manually intensive i.e. would potentially take days if not weeks to accommodate every participant ID. The ability for AEMO to provide files to all Participant types cannot be committed to at this stage.
AEMO stated that it will be the responsibility of each participant to update their FRMP and LR standing data but that AEMO will assist where possible.
Origin enquired about the timing for reconciliation files to be delivered to FRMPs after 6 Feb 2022. AEMO noted that the exact timings are still unknown but it was expected that FRMPs would have updated their systems in accordance with the associated update logic.
EvoEnergy asked when MDPs can stop sending LRs MDFF metering data. AEMO responded that it depends on what date the metering data relates to (prior to 6 Feb 2022 or after). MDPs are required to provide metering data to LRs for dates prior to GS financial go-live.

## Slide 41: Readiness reporting relating to MTP
Austin Tan

## Slide 42: Reflecting progress in your responses
The Metering Transition Plan is monitored through Readiness reporting. Participants are encouraged to provide candid status reporting and raise any issues through the readiness surveys
Participants will provide status reporting on activities relevant to their participant type at a sub-category level. When completing the readiness survey, participants will be asked to choose from the following statuses for each relevant sub-category:
Response | Description | Comments
Complete | All activities associated to the participant type within the sub-category are completed | AEMO will not be validating the self-reported statuses of participants. “Complete” responses will be taken at face value.
On track (started) | All relevant activities are on track for completion by the transition end date, and; Implementation on one or more activities has commenced | -
On track (not started) | All relevant activities are on track for completion by the transition end date, and; Implementation has not yet commenced on any activity | -
At risk | One or more activities within the sub-category are at risk of missing the transition end date | Survey comments to include mitigations and recovery plan
Late | One or more activities within the sub-category are not expected to be completed by the transition end date; or One or more activities within the sub-category is not completed by the transition end date | Survey comments to include recovery plan/activities
n/a | All activities in the sub-category are not applicable to your organisation | Please provide reasoning as to why the activities are not relevant to your organisation

## Slide 43: Reflecting progress in your responses - Example
Example format of MTP monitoring criteria – for Metering Providers (not exhaustive)
For the following sub-categories defined in the MTP, is your organisation on track to complete the associated activities (MP related only) by the defined transition end date?
Category | Sub-Cat ID | Activity ID | Sub-Cat Description | Status
Meter Installation and Reconfiguration | S01 | A1, A2, A4, A5 | BULK/Wholesale Meters | 
 | S02 | A6, A7, A9, A10 | Type 1-3 meters | 
 | S03 | A11, A12, A14, A15 | Subset of type 4 meters - TNI, Market Generator or SGA | 
 | S04 | A16, A17, A19, A20 | Cross Boundary meters (KNOWN) | 
 | S05 | A21, A23 | Cross Boundary meters (UNKNOWN) | 
Response options
Complete
On track (started)
On track (not started)
At risk
Late
n/a
 |  |  | Identify which meters need replacing or reconfiguring | MP
 |  |  | Initial assessment of whether data storage exemptions may be required | MP
 |  |  | Provide visibility of approach / timeframe for required meter replacement or reconfiguration | MC
 |  |  | Install or reconfigure meters as required | MP
Sub Category |  |  |  | 
BULK/Wholesale Meters |  |  | Identify which meters need replacing or reconfiguring | MP
 |  |  | Initial assessment of whether data storage exemptions may be required | MP
 |  |  | Provide visibility of approach / timeframe for required meter replacement or reconfiguration | MC
 |  |  | Install or reconfigure meters as required | MP
Sub Category | Sub-Cat ID | Activity ID | Activity ID | Responsibility
BULK/Wholesale Meters | S01 | A1 | Identify which meters need replacing or reconfiguring | MP
 |  | A2 | Initial assessment of whether data storage exemptions may be required | MP
 |  | A3 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration | MC
 |  | A4 | Install or reconfigure meters as required | MP
 |  | A5 | Apply for data storage exemptions as required | MP
S01
S02
S03

## Slide 44: Metering transition plan past and upcoming activities: Meter installation and reconfiguration
Sub-Category | Activities | Responsible | Transition end date
S01 Bulk/Wholesale meters S02 Type 1-3 S03 Subset of type 4 S04 Cross boundary (known) | Identify which meters need replacing or reconfiguring… Initial assessment of whether data storage exemptions may be required | MP | 31 Mar 2020
 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration [to AEMO] | MC | 31 Mar 2020
S05 Cross boundary (unknown) | Identify which meters need to be installed, replaced or reconfigured | MP | 1 Jul 2020
 | Provide visibility of approach / timeframe for required meter replacement or reconfiguration [to AEMO] | MC | 31 Dec 2020

## Slide 45: Metering transition plan upcoming activities: Metering data delivery
Sub-Category | Activities | Responsible | Transition end date
S17 New and replacement type 4 S18 New and replacement type 4A S19 New and replacement VIC AMI meters S20 New and replacement SAMPLE meters S21 Pre-1 Dec 2018/19 Type 4, 4A, VICAMI and SAMPLE meters | Provide forward plan to AEMO and industry | MDP | 1 Jul 2020

## Slide 46: Metering transition plan past and upcoming activities: MSP accreditation updates
Sub-Category | Activities | Responsible | Transition end date
MP/MDP accreditation (for 1 July 2021) | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation | MP/MDP | 28 Feb 2020
 | Confirm scope/scale of change with AEMO |  | 30 Jun 2020
 | If needed, apply for accreditation update |  | In accordance with Roadmap agreed with AEMO
MP/MDP accreditation (for 1 Dec 2022) | Assess level of change required for people, process and systems to facilitate 5MS/GS implementation | MP/MDP | 31 Mar 2020
 | Confirm scope/scale of change with AEMO |  | 30 Sep 2020
 | If needed, apply for accreditation update |  | In accordance with Roadmap agreed with AEMO

## Slide 47: Readiness reporting - timelines
Readiness reporting | Survey released | Survey responses due | Distribute results | Discuss at RWG | Discuss at PCF | Discuss at EF
Round #1 | 05-Feb-20 | 14-Feb-20 | 2-Mar-20 | 11-Mar-20 | 05-Mar-20 | Proposed 12-Mar-20
Round #2 | 14-Apr-20 | 23-Apr-20 | 07-May-20 | 14-May-20 | 02-Jun-20 | Proposed 11-Jun-20
Round #3 | 07-Jul-20 | 16-Jul-20 | 30-Jul-20 | 13-Aug-20 | 03-Sep-20 | Proposed 07-Sep-20
Round #4 | 01-Sep-20 | 10-Sep-20 | 24-Sep-20 | 08-Oct-20 | 05-Nov-20 | 19-Nov-20
Round #5 | 03-Nov-20 | 12-Nov-20 | 26-Nov-20 | 09-Dec-20 | tbc | tbc
https://aemo.com.au/en/initiatives/major-programs/nem-five-minute-settlement-program-and-global-settlement/readiness-workstream/readiness-reporting
*** TFG reps to support RWG reps in ensuring accurate Survey Responses

## Slide 48: Next steps and general questions
Greg Minney

## Slide 49: Reflection on session objectives
Increase clarity and understanding of activities in the MTP
Confirm those areas where:
  AEMO support may be required by participants
  Implementation approaches to activities need elaborating
Share plans and approaches across impacted participants
Support ongoing participant work programs
Confirm next steps for TFG

## Slide 50: Next steps
Continued implementation of MTP
Meeting outcomes and actions to be circulated to TFG and RWG
Any MTP changes to be presented to the RWG for their consideration
Other?

## Slide 51: General questions

## Slide 52: Thank you for your attendance and participation!

## Slide 53: APPENDIX: Refresher on 5MS and GS metering and metering data obligations

## Slide 54: 5MS Metering installation requirements
Metering Type | Requirement | Date
Types 1, 2, 3 and 7 | Must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 July 2021
Subset of Type 4* | Must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 July 2021
Types 4, 4A and 5 | All new or replacement metering installations (other than type 4A metering installations) installed from 1 December 2018 must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. All new or replacement type 4A metering installations installed from 1 December 2019 must be capable of recording and providing, and configured to record and provide, five-minute trading interval energy data. | By 1 Dec 2022
Note:
AEMO may grant an exemption where 1 type 1, 2, 3 or subset of type 4 meter is not quite capable of storing 35 days of metering data (i.e. 30-34 days) if it is reasonably satisfied that the Metering Provider will be able to otherwise satisfy the requirements of Chapter 7.
* Subset type 4 meters definition:
Type 4 metering installations at a:
  Transmission network connection point; or
  Distribution network connection point where the relevant financially responsible Market Participant is a Market Generator or Small Generation Aggregator

## Slide 55: 5MS/GS metering data delivery to AEMO
Topic | Requirement | Date
File Format | MDFF NEM12 files to be the required file format For all interval metering data being delivered to AEMO MDFF NEM13 files to be supported by AEMO MDMF files for basic meter reads will continue to be supported and accepted | From 1 July 2021
Granularity | NEM12 interval metering data to be: Delivered at the register level (E, B, Q and K) NEM12 200 records must be accurate As per the meter’s trading interval configuration i.e. 5, 15 or 30-minute intervals | From 1 July 2021
Energy | Metering data which must be sent to AEMO: Import and Export Active energy (kWh) (E and B) Import and Export Reactive energy (kVarh) (Q and K), where applicable All other forms of measurement (such as volts and amps) are not required to be delivered to AEMO but will be processed if they are provided. | From 1 July 2021

## Slide 56: 5MS/GS: MSATS datastream standing data
Metering Type | Requirement | Date
Types 1, 2, 3 and 7 | Net datastreams (N1) must be converted to Register level datastreams (E1, B1, etc.) | By 1 July 2021
Subset of Type 4* | Net datastreams (N1) must be converted to Register level datastreams (E1, B1, etc.) | By 1 July 2021
Types 4, 4A and 5 | All new records relating to interval meters must be created at the register level e.g. E and B. Existing net datastream records can remain active post 1 July 2021, until an update to the datastream record is required e.g. meter replacement. Where an update is required to a CNDS record, the net datastream record is to be inactivated and any new active datastreams records are to be created at the register level. Datastreams associated with import and export reactive energy e.g. Q and K must be created in the CNDS table if they exist in the CRI table. Datastreams must be established in a manner that ensures they are not included in market settlements. | From 1 July 2021
Basic Meters | All 1st tier datastreams must be activated and meter reads delivered to AEMO, for UFE purposes | By 1 July 2021

## Slide 57: 5MS/GS: MSATS standing data - general
By 1 July 2021
  Non-contestable unmetered load (NCONUML) NMIs and associated standing data created in MSATS
  NMI Classification Code updates, for affected existing NMIs, to reflect the new code requirements
NMI Classification Code | Description
BULK | Connection point where a transmission network connects to a distribution network - also termed 'Bulk Supply Point’
DWHOLSAL | Distribution network connection point where energy is directly purchased from the spot market by a Market Customer
NCONUML | Non-contestable unmetered load
NREG | Connection point associated with a non-registered embedded generator, i.e. a generating unit that is not classified by a Market Generator, but may be classified by a Small Generation Aggregator as a market generating unit.
WHOLESAL | Transmission network connection point where energy is directly purchased from the spot market by a Market Customer
XBOUNDRY | Connection point where a distribution network connects to another to distribution network