## Field Info (hidden)
Field Type | Description
Ref ID | A unique identifier assigned to the work item (for example, the Quality Centre reference number.
Priority | The priority of the work item. - Add a category of not yet assessed.
Ref ID | The QC Reference Number
Priority | Internal Scoring (To Be Agreed)
Title | A one sentence statement of the issue.
Originator Name | Person who has raised the initial issue.
Originator Company | Company that the person represents within the respective forum.
Register Date | Date it has been raised
Energy Type | Gas or Electricity.- All forums of a retail nature.
Resp. Forum | The responsible forum.
Juristiction | VIC/SA/QLD/ACT/NSW/TAS/NEM
Problem Statement | A very high level category assigned to the item for reference in the RMLF.
Issue Detail | A summary of information relating to this issue.
Target Release | An indication of when this item should be deployed.
Current Stage | Current stage of the applicable change management process.
Stage Open Date | The date the “Current Stage” is opened.
Stage Close Date | The date the “Current Stage” is due for closure.
Change Type | This section looks to identify what is impacted by the change.
-Procedure | A change to procedural documentation.
-System | A system change either at AEMO only/Participant Only or both.
-Schema | A change that will affect AseXML schema.
Additional Comments | Any relevant and useful information to communicate to stakeholders the progress and next steps of this item. This field may also be used to provide barriers to success and areas of overlap with other items. *Decisions made in the CURRENT stage*
Magnitude | Size of change for the industry.

## GAS - In Progress
RETAIL MARKET ISSUE & CHANGE REGISTER
Last Updated: | 2020-09-10
MARKET | CHANGE ID INnnn/yy | TITLE / TOPIC | SHORT DESCRIPTION | PROPONENT (COMPANY & CONTACT) | DATE RAISED | CONSULTATIVE FORUM RESPONSIBLE | JURISDICTION | SYSTEM IMPACT | CURRENT STATUS | PROGRESS COMMENTS
Retail Gas - WA | IN003/20W |  | Add the CustomerDetailsNotification (CDN) to the WA gas retail market systems | ATCO | 2019-11-29 | GRCF | WA | Procedure and system impacts | IIR | Sep 2020 update - The IIR was issued on 17 August and feedback closed 10 September 2020. AEMO will look to issue its Notice of ERA Recommendation in late October. Aug 2020 update - The PCR feedback closed on 24 July. AEMO received submissions from AGL, Alinta Energy, Origin Energy, Simply Energy, and Synergy. All participants supported the initiative, contingent on its being paired with the other schema change initiatives under consideration by the GRCF. This change wil require WA partcipants to move to r38 of the aseXML schema. The IIR is likely to be issued on 13 Aug. June 2020 update: Feedback from the GRCF on privacy matters and the proposal itself has been received. A paper will be presented to the GRCF at the June meeting that will put a recommendation how this proposal should proceed May 2020 update - GMI included in meeting pack Apr 2020 update - As noted at the Feb 2020 release meeting, WA participants expressed that, if a WA schema uplift is to be pursued, then this initiative be considered. Jan 2020 update - Yet to be prioritied
Retail Gas | IN026/15 | Job Enquiry codes review: OTH, UMS, DSD, AML, | During the NARGP process flow workshops it was identified that certain JECs need to be reviewed and process clarified. A harmonised business process to be developed for all jurisdictions, including NSW-ACT: OTH– is being used in VIC, QLD, SA jurisdictions for change of regulator – should ideally have a new JEC as volumes are 250 per month in VIC and NSW-ACT. UMS (Upgrade Meter Size) should also include downgrade meter size or a new JEC is needed. DSD and AML: should not be raised by a Distributor. AML – this should be used only in the case of debt if that is correct should have a new Job Enquiry Code for DBs to use. | GRCF | 2015-06-16 | GRCF | All | Procedure and system impacts | PPC / PCR | Sep 2020 update - The PPC for this initiative was issued on 18 August 2020 and feedback closed on 4 September 2020. AEMO received responses from AGL, AGN, Alinta, ATCO, Jemena, MGN, Origin, Red/Lumo, Simply, and Synergy. AEMO will look to issue its IIR in late Sept. Aug 2020 update: A workshop was held on 30 July to discuss this initiative. Additional requirements were proposed at the workshop which included adding parent/child type structure to the exist JEC field. Also spare JEC was also an addition to the scope. The overall outcome from the workshop was that the GRCF thought this initiative if buddled with GLS changes has merit and formal consultation processes should commence. AEMO is targeting to issue the PPC on 17 Aug. June 2020 update: On the 28th May, AEMO sent an e-mail to the GRCF that contained a questionnaire for IN026/15. This feedback closed 18 June 2020. AEMO is currently reviewing feedback and if the feedback contains sufficient advice that the proposal is excepted to deliver overall net benefit, then AEMO will progress this initiative to the PPC stage. May 2020 update - GMI included in May meeting pack Apr 2020 update - At the Feb 2020 release workshop, it was noted the GRCF agreed to do further investigation. A volunteer is needed to write a GMI 28 Apr 2016 GRCF Prioritisation session - EC Review noted and GRCF stakeholders indicated that this item would require a system change. Moved to On Hold tab because GRCF stakeholders agreed items requiring system changes would not be immediately progressed. Apr 2016 Update - Updates to be made at prioritisation session. Aug 2015 Update - Yet to be prioritised.
Retail Gas - WA | IN002/15W | Service Order Job Enquiry Code (JEC) for Disconnecting / Reconnecting a Delivery Point | ATCO proposes an alternate disconnection method (New Disconnect Method) which will involve the use of a blanking disc together with a security shroud. The New Disconnect Method will not require the removal of the pressure regulator as the disc and lockable shroud will be fitted on the outlet side of the meter to prevent gas from being delivered to the delivery point. | ATCO | 2015-10-18 | GRCF | WA | Procedure and system impacts | PPC / PCR | Sep 2020 update - Jointly issued with IN026/15, as per that initiative. Aug 2020 update: A workshop was held on 30 July to discuss this initiative. Additional requirements were proposed which included adding parent / child level for some existing JEC such as AML. Further work on the Spec Pack changes is needed. AEMO has set a deadline of 10 Aug for these to be completed. June 2020 update: Since the May GRCF meeting, ATCO and AEMO have discussed the idea of updating ATCO original GMI to largely reflect the same requirements contained in IN026/15. ATCO supported this concepted. A revised GMI is now with ATCO for review. May 2020 update: Same status as Apr 2020 update Arp 2020 update - Awaiting to recieve a response from ATCO on action item 132.18.1W whihc involves to provide to AEMO a list of fields and transactions fields that are optional in WA gas retail market but have been made mandatory in later schema versions. Also as noted at the Feb 2020 release meeting, WA participants expressed that, if a WA schema uplift is to be pursued, then this initiative be considered. Feb 2020 update - The updated GMI was submitted to the GRCF for feedback. The feedback closed on 10 Feb 2020. Jan 2020 update - AEMO has provided its feedback to the GMI. This proposal will require schema change. ATCO have been requested to identify any impact related to migrating to current version of the schema. Nov 2019 update – AEMO received GMI from ATCO on 20 Nov 2019. The timetable for this consultation has yet to be determined. Further details to be issued in early in Q3 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020. April 2019 update - Joe Sanchez (ATCO Gas) advised that this can be moved to “pending”. Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. June 2018 update - Reminder sent to ATCO about their input to the issue for consideration at the June 2018 PCC meeting Feb 2018 Update: Reminder sent to ATCO about their input to the issue for consideration at the Feb 2018 PCC meeting. Dec 2017 Update: Received advice from Joe Sanches that ATCO was aiming to have an update by 1 Dec. Oct 2017 Update: There was no further update during the PCC meeting Aug 2017 Update: Joe Sanches (ATCO) advised that new devices have been sourced and new processes are being implemented. ATCO are looking at 120 target sites to perform these activities in relation to disconnecting a delivery point. ATCO will update respective retailers once devices have arrived which is expected in September. Draft program of work was presented to the PCC. Jun 2017 Update: ATCO will continue with trial and sample an additional 100 disconnection service orders. ATCO may propose changes to B2B SO codes. D McGowan advised that ATCO need to allow at least 4 months lead time in order for PCC and ERA to complete respective changes / consultation process before implementing. Dec 2016 Update - Joe Sanches (ATCO) advised that there is no update. Oct 2016 Update - No Update Aug 16 Update - ATCO’s trial is continuing steadily. ATCO is still trying to source alternate materials July 2016 Update - ATCO’s trial is continuing and results will be provided at completion. Recycling of 100 units is still underway. ATCO confirmed that this trial would be post transition. June 2016 Update - ATCO’s trial is continuing and results will be provided at completion. 70 of 100 sites have been successfully tested at the end of May 2016, with 5 damaged. Apr 2016 Update - ATCO to trial another 100 sites. The Specification Pack may need to be updated pending completion of the trial. March 2016 Update - ATCO drafted a GMI on this issue, and REMCo circulated the GMI for agreement by circular resolution. The RCC asked several clarification questions, and agreed to ATCO running a trial of the New Disconnect Method after receiving responses from ATCO to the questions. ATCO is to keep the RCC up to date on outcomes for the trial, and pending results from the trial, will propose changes to the Specification Pack.
Retail Gas - WA | IN009/19W | MIRN Status in MIRN Discovery Response | The meter status is not provided in MIRN discovery response | AGL |  |  |  |  | PPC / PCR | Sep 2020 update - The PPC for this initiative was issued on 18 August 2020 and feedback closed on 4 September 2020. AEMO is review the feedback with the idea of issuing IIR shortly. Aug 2020 update: A workshop was held on 30 July to discuss this initiative. Additional requirements were proposed which included adding new meter status values to the existing enumeration list. Whether meter status should be or is include in the MIRN standing data was also discussed. Further work the Spec Pack changes is needed. AEMO has set a deadline of 10 Aug for these to be completed. June 2020 update: AEMO has issued an e-mail to the GRCF on 11 June that puts forward an AEMO recommendation on how this initiative needs to progress. This will be a topic for discussion on 25 June. May 2020 update: AEMO is evaluating the GMI submitted by AGL. Apr 2020 update - The timetable for the formal consultation has yet to be determined. Also as noted at the Feb 2020 release meeting, WA participants expressed that, if a WA schema uplift is to be pursued, then this initiative be considered. Feb 2020 update - Same status as Jan 2020 Jan 2020 update - Same status as Nov 2019 update Nov 2019 update - Consultation targeted to commence mid Feb 2020 Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020. Jan 2019 Prioritisation session update – GRCF supported AEMO proposal to flag this a pending issue on the register
Retail Gas - WA | IN010/20W | MIRN Status in MIRN Discovery Response | Add new Meter Status for WA | AGL | 2020-07-31 | GRCF | WA | Procedure and system impacts | PPC / PCR | Sep 2020 update - Jointly issued with IN009/19W, as per that initiative Aug 2020 update: A workshop was held on 30 July. Adding additional meter statuses emerged as a important requirement that adds potential value to the MIRN Discovery process. Work is underway to develop the technical protocol documentation changes for this initiative. This need to be completed by 10th Aug to ensure it will be considered as part of the bundled release package.
Retail Gas - WA | IN002/20W |  | WA to move to the same aseXML schema format as east coast | AEMO | 2019-09-17 | GRCF | WA | Procedure and system impacts | IIR | Aug 2020 update - See IN003/20W June 2020 update: Same status as Nov 2019 update May 2020 update: Same status as Nov 2018 update Apr 2020 update - same status as Nov 2019 update Feb 2020 update - same status as Nov 2019 update Jan 2020 update - Same status as Nov 2019 update. Nov 2019 update - Consulation is targeted to commence early May 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas | IN001/20 |  | Move VIC, QLD and NSW/ACT weather related information into the Register of Weather Related Information guide that SA adopted (documentation changes only). | AEMO | 2019-09-17 | GRCF | Vic, QLD and NSW/ACT | Procedure-only | IIR | Sept 2020 update. IIR issued on 26 Aug. Feedback due 18 Sept. Aug 2020 update: - PPC was issued on 14 July. Feedback closes on 7 Aug. Issuing of the IIR is targeted for late Aug June 2020 update: The PPC on these changes is likely to be issued in the week commencing 22 June with feedback due mid July. Apr 2020 update - Targeting late Apr to issue a PPC with feedback due late May Feb 2020 update - Because of other priorities such has new initatives that have IT changes, AEMO will need to review the timing. AEMO will provide an update in early March. Jan 2020 update - AEMO remains on track to commence a consultation on this change by mid Feb 2020 Nov 2019 update - Consultation is targeted to commence mid Feb 2020 Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas | IN004/17 | Meter Management | Add a Downgrade Process to the procedures. This initative is one of several east coast miscellaneous / harmonising RMP and TP (documentation changes only). See also tab titled IN004-17 - East coast package. | AGL | 2017-04-18 | GRCF | VIC, QLD and SA | TBA | Discussion only | Sept 2020 update – An initial scoping exercise is underway. This work maybe split into two categories (non-controversially and complex) with the non-controversially consultation package kicking off in mid-October. Aug 2020 update: AEMO is looking at having a covering paper/GMI to the GRCF in late August. Formal consultation would kick off in late Sept. June 2020 update: AEMO is looking at having a covering paper/GMI to the GRCF in early August. Formal consultation would kick off in late August. May 2020 update: Same status as Jan 2020 update Apr 2020 update - Same status as Jan 2020 update Feb 2020 update - Same status as Jan 2020 update Jan 2020 update - AEMO is planning to commence work on this initative in the 2nd half of 2020. Nov 2019 update - Consultation is targeted to commence mid Apr 2020 Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020. Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” Apr 2017 Update - Yet to be prioritised.
Retail Gas | IN012/15 |  | During the NARGP consultation it was revealed that the NGR prescribe the obligation for the NWO to provide a listing of all DPI. The new RMP include a obligation for the NWO to provide such a listing. Similar obligation in other jurisdictional RMP contain the same obligations. Have the obligation reside in the NGR is superfluous and can be delated. AEMO support the idea to request a change to the NGR and when that done remove the definition DPI full listing. (See IIR consolidated Response document ref # 41). | to be determined | 2015-02-17 | GRCF | All except WA | TBA | Discussion only | Sept 2020 update – AEMO is seeking legal advice on whether NGR rule 138AC can be non-controversially removed. That advice will be provided at the October GRCF meeting June 2020 update: Same status as Jan 2020 May 2020 update: Same status as Jan 2020 update Apr 2020 update - Same status as Jan 2020 update Feb 2020 update - Same status as Jan 2020 update Jan 2020 update - AEMO is planning to commence work on this initative in the 2nd half of 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN004/20 |  | Base Load (BL) and Temperature Sensitivity Factor (TSF) changes in NSW/ACT | JGN | 2019-09-17 | GRCF | NSW/ACT | Procedure and system impacts | Discussion only | Sept 2020 update - JGN provided the following update on 20 Aug. JGN plan to submit a GMI toward the end of Sept 2020. The proposal is likely to involve adding sub-characterisations for Volume Boundary meters and MD/HR MIRNs with 2 meters (one gas and one hot water). Changes to NSW/ACT RMP maybe required. They pertain the attachments - Gas Meter E2 Estimation & Substitution Methodology – BL and TSF. JGN has proposed the following timeline: Consultation – Q4 2020 / Q1 2021, RMP changes - Q2 2021, Deployment – May/June 2021 (subject to IT change, build and test). June 2020 update: Earlier this month AEMO contacted Jemena seeking an update regarding time. Jemena advised that they are aiming to submit a proposal to AEMO in late July. May 2020 update: Same status as Nov 2019 update Feb 2020 update -Same status as Nov 2019 update Feb 2020 update - Same status as Jan 2019 update Jan 2020 update - Same status as Nov 2019 update. Nov 2019 update – The timetable for this consultation has yet to be determined. Further details to be issued in early in Q3 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas | IN005/18 |  | Estimated Consumption after meter removal | OE | 2018-06-18 | GRCF | All except WA | TBA | GMI | Sept 2020 update - AGL sent e-mail to DBs on 2nd Sept inviting DBs to send through to AGL and OE 5 or 6 process steps by the 11th Sept. A workshop (before the end of Sept) has been proposed that would be used to work through the process and agree a simple process July 2020 update - Same status as Jan 2019 update June 2020 update: Same status as Jan 2019 May 2020 update: Same status as Jan 2019 update Apr 2020 update - Same as Jan 2020 update Feb 2020 update - Same as Jan 2020 update Jan 2020 update - OE and AGL had further developed the process but still had a number of scenarios that needed to be fully worked through. OE and AGL aiming to have a draft PPC to AEMO by the January GRCF meeting. Nov 2019 update - A workshop was held on the 15 Oct. Mario (OE) sent an updated GMI containing updated flow chart on 20 Nov 2019. Feedback on the updated GMI is required before 28th Nov. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020. Jan 2019 Prioritisation seesion - The GRCF agreed that a workshop was required to further explore whether this initiative was worth adding to the GRCF 2019 program of work. Aug 2018 update. - Feedback from particpants closed 13th July. AEMO received feedback from Jemena, OE, AGL, AusNet and Multinet. Feedback suggested the proposal wasn’t an immediate priority therefore AEMO proposes that this initiative be “parked” for the time being and flagged as a potential item to progress in 2019. June 2018 update - Issued as a late paper for June 2018 GRCF meeting
Retail Gas - WA | IN001/20W |  | Bundled WA Explicit Informed Consent (EIC) process review | AEMO | 2019-09-17 | GRCF | WA | Procedure-only | Discussion only | Sept 2020 update - AEMO has commenced analysis work on this initiative and will propose solution options to GRCF June 2020 update: Same status as Nov 2019 update May 2020 update: Same Status as Nov 2019 update Apr 2020 update - Same status as Nov 2019 update Feb 2020 update - Same status as Nov 2019 update Jan 2020 update - Same status as Nov 2019 update. Nov 2019 update – The timetable for this consultation has yet to be determined. Further details to be issued in early in Q3 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas - WA | IN001/18W | Clause 325 | Minor RMP change. Matters referred to AEMO under clause 325 | Alinta | 2018-01-05 | GRCF | WA | Procedure-only | GMI | Sept 2020 update - AEMO has allocated resource to progress this initiative Aug 20202 update: Same as Jan 2020 June 2020 update: Same as Jan 2020 May 2020 update: Same as Jan 2020 Apr 2020 update - Same as Jan 2020 Feb 2020 update - Same as Jan 2020 Jan 2020 update - Awaiting availability of resource to progress this initiative Nov 2019 update - As per the request from the proponent, a meeting was held between AEMO, AGL, Alinta and Kleenheat to discuss the proposed changes to clause 325. An outcome of the meeting was for AGL to prepare a provide a paper of the breach reporting requirements based on the Compendium of gas customer licence obligations and national energy retail law. This has been done. AEMO is working on mapping out breach reporting obligations from the RMP. Sep 2019 update - The proponents advised that they intend to withdraw the initiative. AEMO has communicated to the proponents that it intends to continue with the proposal to fix the issue of no provision for self-reporting of breaches in the RMP Jul 2019 update - AEMO feedback on GMI provided for participant response April 2019 update - Further update from AEMO review and participant feedback received for discussion at Apr 2019 GRCF Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Feb 2019 Update - GMI updated with further participant feedback and inclusion of self-reporting of breaches and released for participant feedback. Aug 2018 update - AEMO advised PCC members that this change was not required as reporting of breaches under clause 325 although a good practice was not mandatory particularly where corrective action was taken immediately. Whether a breach is reported or not, the participant is still responsible to identify corrective actions and implement them. In view of this AEMO recommended that this initiative be withdrawn. Kleenheat have advised that they will provide further details about changes to RMP in relation to Self reporting of breaches. June 2018 update - GMI tabled for discuss at June meeting Feb 2018 Update - To be discussed a Feb PCC meeting
Retail Gas | IN003/20 |  | Adoption of the two B2B LS transactions including adopting a version of the aseXML schema that contains these LS transactions | AEMO | 2019-09-17 | GRCF | All except WA | Procedure and system impacts | Implementation | Aug 2020 update - On the 23 June 2020 AEMO published it deicsion to approve this changes. The date on which these changes will take effect will be published in a separate notice (Notice of Effective Date). AEMO proposes to issue that notice by the end of March 2021. The target effective date for these changes is Q4 (Oct-Dec) 2021..... June 2020 update: IIR response closed 1 June. AEMO’s preliminary assessment has revealed that AEMO positions on recommending the changes to proceed is unlikely to change. An AEMO decision is on track to be published before 30 June 2020. May 2020 update: IIR issued 4 May with a recommendation to proceed with the changes. Responses due 1 June. Apr 2020 update - Notice of Time Limit Extension issued 5 March 2020. Supplementary survey issued 5 March 2020. Responses closed 31 March 2020. AEMO on track to issue IIR by mid-May. Feb 2020 update - PPC consultation closed 14 Feb 2020. IIR due to be issued 10 Mar 2020. Jan 2020 update - PPC is on track to be issued mid Jan 2020. Nov 2019 update - Consultation targeted to commence mid Jan 2020 Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas | IN011/20 |  | Adding the CustomerDetailsRequest (CDR) to gas retail market systems and amend the existing CustomerDetailsNotification (CDN) | AGL | 2019-11-29 | GRCF | VIC | Procedure and system impacts | Implementation | Sept 2020 update - On the 28 Aug 2020 AEMO published it decision to approve this changes. The date on which these changes will take effect will be published in a separate notice (Notice of Effective Date). AEMO proposes to issue that notice by the end of March 2021. The target effective date for these changes is Q4 (Oct-Dec) 2021 Aug 2020 update - The IIR feedback closed on 31 July. AEMO received feedback from AGIG, EA, MGN, OE, Red and Lumo Energy, and Simply Energy. A Notice of Decsion is likely to be issued before the end of the month. June 2020 update: On the 25 May AEMO issued a PPC. Response closed on 12 June. AEMO is currently reviewing feedback and is on track to issue a IIR on 26th June. May 2020 update - Feedback on GMI closed 8 May. Apr 2020 update - At the Feb 2020 release workshop, it was noted the GRCF expressed a strong desire for this initative to be bundled with IN003/20 in terms of schema releases. Jan 2020 update - Yet to be prioritied

## IN004-17 - East coast package
MARKET | CHANGE ID INnnn/yy | TITLE / TOPIC | SHORT DESCRIPTION | PROPONENT (COMPANY & CONTACT) | DATE RAISED | CONSULTATIVE FORUM RESPONSIBLE | JURISDICTION | SYSTEM IMPACT | CURRENT STATUS | PROGRESS COMMENTS
Retail Gas | IN009/17 | Harmonise RMPs | Add a cause 4.2A (Re-energisation of Distribution Supply Points) to align with Qld and Vic. See Vic clause 2.9.5A | AEMO | 2017-06-23 | GRCF | NSW/ACT | Procedure-only | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” July 2017 Update - Yet to be prioritised.
Retail Gas | IN002/18 | AEMO lodging a transfer on behalf of SCUs | Add a provision to the RMPs similar to SA that describes that AEMO can lodge a transfer on behalf of a SCU (This was raised as part of the SA RMP hamonisation effort) | AEMO | 2018-02-28 | GRCF | VIC, QLD, and NSW/ACT | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Mar 2018 update - Yet to be prioritised
Retail Gas | IN011/18 |  | It seems there is highlighted text throughout the document that opens with quotations, Red and Lumo propose to AEMO that this is removed and simply highlighted without the quotations. There is inconsistency throughout the PBPs where quotations are and are not used in reference to the highlighted text. (The blue highlighted text are all NSW/ACT differences highlighted throughout the PBP, however, do not require quotations) | Red/Lumo | 2018-12-31 | GRCF | NSW/ACT | Procedure-only | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Dec 2018 update - Yet to be prioritied
Retail Gas | IN004/19 |  | There is an inconsistency in the jurisdictional RMP how timeline periods are applied. Vic, QLD and SA seem to use number of hours “from the start of the gas day” however NSW/ACT uses a specific time that at 6:00am. The NSW/ACT RMP should be updated to reference number of hours “from the start of the gas day” like the other the jurisdiction. This idea was raised during the GDH IIR consultation and was published in NoD (see item #14) | AGL | 2019-02-19 | GRCF | NSW/ACT | TBA | Discussion Only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Mar 2019 update - Yet to be prioritied
Retail Gas | IN005/19 |  | Remove redundant tranistional provision in Chapt 12. This idea was raised during the GDH IIR consultation and was published in NoD (see item #16) | AGL | 2019-02-19 | GRCF | NSW/ACT | TBA | Discussion Only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Mar 2019 update - Yet to be prioritied
Retail Gas | IN007/19 |  | Cls 410 (a) do not have a clear time for the cancelled or accelerated transfer actions to occur whereas the other jurisdictions do. This idea was raised during the GDH IIR consultation and was published in NoD (see item #25) | AGL | 2019-02-19 | GRCF | SA | TBA | Discussion Only | Sept 2019 (Sept 2020 Prioritisation session) – See IN004/17. Mar 2019 update - Yet to be prioritied
Retail Gas | IN005/15 |  | Feedback received during the NARGP IIR phase revealed that the use of the term "Reasonable endeavours" is potentially being used inconsistently throughout the new NSW/ACT RMPs and may not be consistent with the rules and law. Because the NSW/ACT RMP leveraged of the VIC and QLD RMP it is likely that use of the Reasonable endeavours terms may also be potentially used inconsistently. A review of all RMPs is proposed to remedy any potential inconsistencies. (See IIR consolidated Response document ref # 1,6,44,45,48) | to be determined | 2015-02-11 | GRCF | All | TBA | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) – See IN004/17. June 2016 Prioritisation session update - GRCFconsidered this to be a low priority and should remain 'on hold'. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN007/15 |  | A proposal put forward during the NARGP was to include in the RMPs hierarchy of market participation. RMPs use a variety of terms – Participant, User, Retailer, FRO. Proposal is to clarity of what each term covers. Requires careful consideration as different terms are used to convey particular activities or relationship. AEMO considers this is a broader issue for all jurisdiction RMPs (See IIR consolidated Response document ref # 10, 33) | AEMO | 2015-02-17 | GRCF | All | TBA | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) – See IN004/17. June 2016 Prioritisation session update - GRCFconsidered this to be a low priority and should remain 'on hold'. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN009/15 |  | A proposal put forward during the NARGP consultation to include defined terms for NERL and NERR. AEMO considers this is a broader issue for all jurisdiction RMPs. (See IIR consolidated Response document ref # 30) | to be determined | 2015-02-17 | GRCF | All | TBA | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN010/15 |  | The inclusion of a definition of “day” or “calendar day” was canvassed during the NARGP consultation to improve the readability. These terms are used in most RMPs. AEMO considers this is a broader issue for all jurisdiction RMPs therefore a harmonisation approach should be considered (See IIR consolidated Response document ref # 37 and 77) | to be determined | 2015-02-17 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN011/15 |  | During the NARGP consultation, AEMO simplified the defined term actual meter reading to simply say - The figures or other information shown on a meter or instrument as actually read. Other jurisdictions included the various method to record/retrieve a read in the definition of actual meter read which for the RMP isn’t warranted. AEMO considers this is a broader issue for all jurisdiction RMPs therefore a harmonisation approach should be considered (See IIR consolidated Response document ref # 40) | to be determined | 2015-02-17 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN013/15 |  | During the NARGP consultation, AEMO introduced the defined term Prospective FRO. This is a term not used other jurisdictions. For consistency AEMO proposed to also add this definition in VIC and QLD. (See IIR consolidated Response document ref # 42) | to be determined | 2015-02-17 | GRCF | VIC and QLD and SA | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN014/15 |  | During the NARGP consultation, AEMO Clause 2.6.2 (d) in Vic states where, pursuant to clause 2.1.5, the Distributor has provided, (i) to the FRO for a distribution supply point any of the information referred to in clause 2.6.2(a); or (ii) to AEMO any of the information referred to in clause 2.6.2(b), the Distributor will have satisfied its obligations under clause 2.6.2(a) or 2.6.2(b) (as applicable) with respect to the information provided under clause 2.1.5. NSW/ACT has now has an equivalent clause 3.6.5 (c). A doubt was raised during the NARGP consultation whether this is an acceptable practice. (See IIR consolidated Response document ref # 114) | to be determined | 2015-02-26 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN015/15 |  | During the NARGP consultation it was identified that metering chapter have deenergisation clauses they don’t have energisation clauses. The same applies in VIC and QLD. A proposal was put forward consider adding a energisation clause. (See IIR consolidated Response document ref # 119) | to be determined | 2015-02-26 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN017/15 |  | During the NARGP consultation feedback received indicated that the meter data delivery (3.5.1) was a little unclear. Introducing better drafting entails changing the structure of multiple provisions, which are currently broadly consistent with Vic and Qld. This was beyond the current scope and should be a proposal for future improvement across all jurisdictions. (See IIR consolidated Response document ref # 98) | to be determined | 2015-02-26 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN008/18 |  | All jurisdiction RMPs state that AEMO can submit a MIRN discovery request however the method and format isn’t specified in any technical protocol. AEMO will raise this a new issue on the Retail Market Issue/Change register for the GRCF to consider | AEMO | 2018-09-17 | GRCF | All | TBA | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) – See IN004/17. Sept 2018 update - Yet to be prioritied
Retail Gas | IN006/15 |  | Feedback received during the NARGP IIR consultations phase revealed that the use of the term MIRN rather than "distribution supply point / delivery point” would improve the readability of the RMP. An example is VIC RMP Each Distributor must use its reasonable endeavours to provide each User who is the FRO for a MIRN distribution supply point which is located in the distribution region of a Distributor with details of any changes to any site access information …… A review of all RMPs is proposed to improve the clarity. (See IIR consolidated Response document ref # 38) | AEMO | 2015-02-11 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) – See IN004/17. June 2016 Prioritisation session update - GRCFconsidered this to be a low priority and should remain 'on hold'. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation

## GAS - Pending
MARKET | CHANGE ID INnnn/yy ICFnnnn | TITLE | SHORT DESCRIPTION | PROPONENT (COMPANY & CONTACT) | DATE RAISED | CONSULTATIVE FORUM | JURISDICTION | SYSTEM IMPACT | CURRENT STATUS | PROGRESS COMMENTS
Retail Gas | IN012/14 | Retrospective Transfers | Consider adding the VIC and QLD RetrospectiveTransfer functionality for the SA and NSW/ACT jurisdiction. | GRCF | 2014-06-02 | GRCF | NSW/ACT & SA | Procedure and system impacts | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) - Given AEMC trasfer rule change GRCF supported AEMO proposal park this till we better understand the landscape of electricity Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted the AEMC's rule change and this needs to be monitored by all GRCF stakeholders and AEMO. Apr 2016 Update - Updates to be made at prioritisation session. Higher focus 12 March 2015 Update: There was support from the GRCF Retailers for this item to remain on the pending tab as open.
Retail Gas | IN005/16 | Differences in VIC and NSW transfer completion windows | During NARGP project it was identified that in VIC the transfer completion for the data provision period is not aligned NSW. For example a Transfer in NSW will not complete if it is outside the data provision period. NSW process seems to be more in sync with the intent of the RMP wording. VIC process needs to be reviewed. | AEMO (at this point) | 2016-02-18 | GRCF | NSW/ACT,VIC | Procedure and system impacts | Discussion only | Sept 2019 update - Sept 2020 Prioritisation session) – See IN012/14 Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this was a low priority and agreed to be reviewed Q4. Apr 2016 Updates to be made at prioritisation session. Yet to be prioritised. Raised during the NARGP consultationApr 2016 Update - Updates to be made at prioritisation session. Aug 2015 Update - Yet to be prioritised.Apr 2016 Update - Updates to be made at prioritisation session. Feb 2016 Update - Yet to be prioritised.
Retail Gas | IN008/16 | Meter Reads for Incomplete MFX Service Order | This relates to the issue of the requirement to provide ‘New/Basic Meter/Next scheduled read date’ and ‘New/Basic Meter/Scheduled reading day number’ details for Meter Fix (MFX) type service order response sent by the Distributor where they were unable to complete the meter fix request | Kelly Murray (Multinet) | 2016-03-03 | GRCF | All | TBA | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. May 2018 Update - Multinet provided advice on 20 Apr that this is still required. Multinet Gas is now sending these service order responses without the fields that are specified in the build pack as mandatory for MFX orders and are not experiencing any issues with the retailer receiving these responses. Mutinet do still believe that Participant Build Pack 3 section 4.2.2.2 ServiceOrderResponse is wrong and the transaction Data elements section should be amended to define that these values(Next scheduled read date & Scheduled reading day number) are NOT mandatory for MFX orders that are not completed successfully ( meter installed) Apr 2016 update - Some participants provided feedback on potential system and process impact. This item is on Apr 2016 GRCF for discussion and prioritisation. If prioritised the proponent to raise a GMI. Feb 2016 Update - Yet to be prioritised.
Retail Gas | IN032/16 | MaterDataResponse | Network operator to send a MeterDataResponse transaction (T31B) for Customer Own Reads. | AGL | 2016-09-08 | GRCF | NSW/ACT | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” Oct 2016 Update - Yet to be prioritised.
Retail Gas | IN001/17 | RoLR | Review List of Known Consequences - Retailer of Last Resort, in light of QLD RoLR being implemented. Also need to also review in light of NARGP change | AEMO | 2017-01-10 | GRCF | QLD and NSW/ACT | Procedure-only | Discussion only | Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” Jan 2017 Update - Yet to be prioritised.
Retail Gas | IN008/17 | Include SA RoLR Process Flows | Include SA RoLR process flows that were developed during the implementation of SA RoLR scheme but not added to the technical protocol documentation | AEMO | 2017-06-23 | GRCF | SA | Procedure-only | Discussion only | Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “pending” July 2017 Update - Yet to be prioritised.
Retail Gas | IN035/12 |  | Decommissioned sites with actual reads. Provide further data on the materiality on decommissioned sites with actual reads. Analysis undertaken by AEMO in 2013 on basic meter data has identified that DB’s are provided AEMO with actual basic meter readings MIRNs that have a status of decommissioned. The effect of this discrepancy is that MIRNs are excluded from Net System Load (NSL) calculations and therefore means that the gas is not being allocated to the associated non-host retailers in the wholesale market, but rather to the host retailer. Possible causes are (i) DB Processes – such as meter exchange that doesn’t replug a plugged meter , (ii) Meter Re-Fix completed without a transfer or without a MIRN Status Update or (iii) fraud. | To be determined | 2012-11-22 | GRCF | VIC, QLD | Procedure-only | Discussion only | Sept 2019 - Prioritisation session - GRCF supported AEMO proposal to leave this as pending. Feb 2018 Prioritisation session update - GRCF considered this initiative was less of a priority therefore agreed it should be moved to a status of “pending” Feb 2018 update - Awaiting prioritisation session outcome Nov 2017 update - GRCF rejected AEMO proposal to close this issue. A further paper on the next steps will be tabled at the Nov meeting. Sept 17 update - Paper to be tabled at Sept GRCF July 2017 update - Data sent to DBs on 12 May. 1st Tier RBs where set a rpt 2 June. Update May 2017 - As per the agreed GRCF Work Program, AEMO is still on track to issue spreadheets Mid May. DB's to provide transaction early Aug. Jan 2017 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2017 therefore agreed to move this item to the in progress tab. 28 Apr 2016 GRCF prioritisation session - AEMO to re-run report. Apr 2016 Update - Updates to be made at prioritisation session. May 2015 Update – Updated information sent to Vic RBs and Vic DBs that confirms that the issues is still present. Vic DBs have been request to provide a MIRNStatusUpdate transaction to AEMO before COB Friday 29 May 2015. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this is a medium priority that should remain open confirmation is provided that it has been resolved. The GRCF agreed AEMO should generate the relevant report in April to see if the issue is still present.
Retail Gas | IN003/15 | Validation of the complete customer listing | The RMPs are not prescriptive enough regarding AEMO validation steps pertaining to the complete customer listing provided by retailers. This is a cross-jurisdictional issue raised at the NARGP IIR consultation. See item #140 on consolidated list | to be determined | 2015-01-22 | GRCF | VIC, QLD, SA and NSW/ACT | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. Feb 2018 Prioritisation session update - GRCF considered this initiative was less of a priority therefore agreed it should be moved to a status of “pending” Feb 2018 update - Awaiting prioritisation session outcome Jan 2017 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2017 therefore agreed to move this item to the in progress tab. June 2016 Prioritisation session update - GRCF considered this to be a low priority and should remain 'on hold'. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation.
Retail Gas | IN006/18 |  | Improving Customer transfers in the Gas Retail Markets (Customer Own-Reads) | Red/Lumo | 2018-06-18 | GRCF | All | TBA | GMI | March 2019 Workshop - GRCF ageed that this issue is not a high priority and will not be address until 2020 at the earliest. Jan 2019 Prioritisation seesion - The GRCF agreed that a workshop was required to further explore whether this initiative was worth adding to the GRCF 2019 program of work. Aug 2018 update. - Feedback from particpants closed 13th July. AEMO received feedback from OE,Multinet and AusNet. Feedback suggested the proposal wasn’t an immediate priority therefore AEMO proposes that this initiative be “parked” for the time being and flagged as a potential item to progress in 2019. June 2018 update - Issued as a late paper for June 2018 GRCF meeting
Retail Gas - WA | IN006/19W | Reduce regulatory costs (negative assurance audits) | Rule 350 requires a user to conduct a negative assurance audit for each calendar year. This audit is in relation to a customer’s explicit informed consent. It is proposed this period should be extended where it is reasonable to do so.Industry Benefit: Reduction in cost | Synergy | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. Jan 2019 Prioritisation session update – GRCF supported AEMO proposal to flag this a pending issue on the register
Retail Gas - WA | IN007/19W | Notification by posts | Rule 12(1) deems that communication sent by mail is deemed to have been received on the second business day. This time frame is not realistic. It is proposed that this rule is reviewed and amended to align with Australia Posts revised delivery time frames. Australia Posts current delivery time frames (for the same state) is 3 business days for metro and 4 business days for country. | Synergy | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. Jan 2019 Prioritisation session update – GRCF supported AEMO proposal to flag this a pending issue on the register
Retail Gas - WA | IN008/19W | Bulk MIRN Discovery | Improve the efficiency of MIRN discovery. Synergy propose that there should be arrangements similar to electricity for a bulk MIRN discovery. Including where applicable for users to use a “robot” for the transactions.Industry Benefit: Saving cost for retailer and network operator | Synergy | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. Jan 2019 Prioritisation session update – GRCF supported AEMO proposal to flag this a pending issue on the register
Retail Gas - WA | IN001/17W | Add clarity to Clause 184 and 189 | Add further clarity to the words used in clause 184 and 189 | Kleenheat | 2017-02-01 | GRCF | WA | Procedure-only | GMI | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as pending. June 2018 update - Reminder sent to Kleenheat and Synergy about their input to the issue for consideration at the June 2018 PCC meeting. AEMO suggested the the GMI needed updating. No further feedback was received. Feb 2018 Update: Reminder sent to Synergy about their input to the issue for consideration at the Feb 2018 PCC meeting. Dec 2017 Update: On 28 Nov, AEMO e-mailed Synergy and Kleenheat seeking an update on this issue. On 1 Dec Alex Penter advised that Kleenheats comments on amendments were sent to Synergy. Kleenheat support the proposed amendments that have been created in collaboration between Kleenheat, AGL and Synergy. Awaiting further information from Synergy. Oct 2017 Update: There was no further update during the PCC meeting. Aug 2017 Update: Alex Penter noted that Kleenheat are satisfied with the basis for the 10%. Synergy and Alinta are having to manage the 10% variable frequently and a new approach needs to ensure that the process takes into account agreements between pipeline operators and the need to supply sufficient gas. Synergy and Kleenheat to work together on updating the GMI IN001/17W to include a more efficient approach and present at a future PCC meeting. PCC raised concern in recent 255 notice that a participant may have replied to the issuing email instead of the email in attached notice. AEMO to investigate if correct process was followed in issuing the notice on 18 Aug. Jun 2017 update - Hans Niklasson (Kleenheat) provided a summary regarding a GMI prepared by Kleenheat. This GMI proposed minor wording changes to improve the clarity of clause 189. AEMO and CGI had no issues with the proposed changes. Further discussion revealed that it was Kleenheats intention that the 10% can change if confirmation has been provided by the pipeline operator. The PCC agreed to place this GMI on hold and that AEMO will look into the basis for the 10% “A” variable and work with PCC to understand the implications of varying the 10%.
Retail Gas | IN008/19 | Customer own reads | Leave the current timeframes for COR provision as the minimum requirement but include an additional clause in these obligations that allows the information to be shared by at an agreed frequency (eg 1 read / month). See the IIR for IN006-17 (SA RMP harmonisation) – Attachment D ref #9. | Mark Riley (AGL) | 2019-04-08 | GRCF | QLD, NSW-ACT, VIC and SA | Procedure-only | GMI | April 2019 - GMI submitted, GRCF happy to add to prioritisation calendar
Retail Gas | IN005/20 |  | A WA change proposal (IN003/18W) to rule 14 (5) was amended and approved by ERA which meant that the process is now different in the east coast RMPs. A review of the East Coast process needs to be undertaken to determine if the WA change needs to be applied. | Mark Riley (AGL) | 2019-10-10 | GRCF | QLD, NSW-ACT, VIC and SA | Procedure-only | Discussion only | Jan 2020 update - The GRCF agreed at the Nov meeting to add this initative to the East Coast RMP and TP harmonisation changes (IN004/17) Oct 2019 update - Yet to be prioritied
Retail Gas | IN006/20 |  | AEMO has identified that the definition of a Customer could be improved for all east coast jurisdiction to include exempt customers for other purposes under the procedures in the event an exempt seller is registered either as a Retailer or an SCU. For example for SA RMP the definition could be improved by inserting the words "(or, where relevant, an ‘exempt customer’ as defined in section 109 of the NERL) after the word "NERL". See the IIR for IN006-17 (SA RMP harmonisation) – Attachment D ref #8. | AEMO | 2019-11-13 | GRCF | QLD, NSW-ACT, VIC and SA | Procedure-only | Discussion only | Oct 2019 update - Yet to be prioritied
Retail Gas | IN007/20 |  | AGL suggests that for consistency that the obligation to provide data fields noted in Appendix E (Non Automated Electronic Files) of the AEMO Spec Pack doc - FRC B2B System Interface Definitions is made consistent with the WA drafting. See the IIR for IN006-17 (SA RMP harmonisation) – Attachment D ref #42. | AGL | 2019-11-13 | GRCF | QLD, NSW-ACT, VIC and SA | TBA | Discussion only | Oct 2019 update - Yet to be prioritied
Retail Gas | IN008/20 |  | AEMO has identified and issues with section 2.1.17 of the ICD. A prelim assessment highlighted the uncertainty around the circumstances / concept of a participant GBO-ID becoming “suspended”. There is a possibility that the GBO-ID status of suspended isn’t required. The system impact of removing this GBO-ID state is unknown and would require further investigation. See the IIR for IN006-17 (SA RMP harmonisation) – Attachment D ref #38. | AEMO | 2019-11-13 | GRCF | SA | TBA | Discussion only | Oct 2019 update - Yet to be prioritied
Retail Gas | IN009/20 |  | Residual SA Harmonisation change. AEMO overlook a further documentation change when the Connectivity Testing and Technical Certification document became a WA only artefact. It is to do with the Low Volume Interface (LVI). Appendix D (The Low Volume Interface) of the FRC B2M-B2B Hub System Specifications need to be amended to say “Appendix D (The Low Volume Interface – WA only). | AEMO | 2019-11-29 | GRCF | SA | TBA | Discussion only | Jan 2020 update - Yet to be prioritied
Retail Gas | IN004/20W | WA harmonisation | Harmonise the RMP (WA) with the east coast procedures in terms of structure and format | Mark Riley (AGL) and Joe Castellano (Origin Energy) | 2019-11-22 | GRCF | WA | Procedure only | Discussion only | Jan 2020 update - raised as part of IN003/19W (Holistic tidy up of WA RMP), a number of changes in the Register of Category 2 or 3 Changes served only to harmonise the RMP (WA) with east coast procedures, which was out of scope for IN003/19W, so the GRCF agreed to incorporate a broader harmonisation initiative on the Change Register for future consideration.
Retail Gas | IN005/20W | Requirements for a valid transfer request | Per clause 83 sub-clauses (g), (h) and (i) a valid transfer request can only be valid for a small gas customer, not a large gas customer. AGL wants investigation as to whether this is correct. | Mark Riley (AGL) | 2019-11-12 | GRCF | WA | Procedure and system impacts | Discussion only | Jan 2020 update - This issue was raised as a non-system change during IN003/19W (Holistic tidy up of WA RMP). AEMO noted that there is a likelihood that systems have been built in accordance with the procedures. If it is found that these validation provisions are incorrect, system modification will be required. On that basis, this issue was excluded from IN003/19W and placed on this register.
Retail Gas | IN006/20W | Clause 115 clarity | AGL seeks further clarity from AEMO and the operator around the practical aspects of how this clause operates. AGL would expect that if the network operator has lodged a disconnection notice, then that MIRN is physically disconnected. Therefore AGL suggests that AEMO should not cancel the disconnection notice, but rather continue to seek the meter data or put a substituted meter reading into the system until the Operator provides the data. Alternatively, the network operator should not be able to submit a notice without submitting a meter read of some sort. | Mark Riley (AGL) | 2019-11-12 | GRCF | WA | Procedure and system impacts | Discussion only | Jan 2020 update - this issue was raised as part of IN003/19W (Holistic tidy up of WA RMP)
Retail Gas WA | IN007/20W | Hierachy of meter data | AGL believes there is not a clear place to describe the hierarchy of meter data. The NEM Electricity Metrology Procedures clearly define the hierarchy for electricity. Given that Customer Own reads are now being included in the WA gas amrket, AGL suggests that a generic hierarchy be established for all markets (east and west coast) to standardise the hierarchy in all markets. | Mark Riley (AGL) | 2019-11-12 | GRCF | WA | Procedure and system impacts | Discussion only | Jan 2020 update - this issue was raised as part of IN003/19W (Holistic tidy up of WA RMP)
Retail Gas | IN012/20 |  | Changes to address street types. Need to determine if we add AV and CR, or replace AVE to AV and CRES to CR. | AEMO | 2020-01-06 | GRCF | All | Procedure and system impacts | Discussion only | Jan 2020 update - Yet to be prioritied
Retail Gas | IN013/20 |  | Add gender netural person title value "Mx" | AEMO | 2020-01-06 | GRCF | All | Procedure and system impacts | Discussion only | Jan 2020 update - Yet to be prioritied
Retail Gas | IN008/20W | Additional Service Charge | Determine whether the definition additional services charge in clause 2 and the details about additional service charge described in clause 362A are still warranted or should be amended. (Note – This initiative was one of the residual items from the IN003/19W (Holistic tidy up of RMP) consultation whereby a consensus position as unable to be reached that the workshop because further research and information is required.) | AEMO | 2020-01-21 | GRCF | WA |  | Discussion only
Retail Gas | IN014/20 |  | Clause 2.9.7 (Metered supply points) of the RMP requests that distributor must calculate the total number of metered supply points and send that information to AEMO. The use of the term “metered” needs further clarity in terms of whether “metered” includes counting supply points where the meter is connected to an upstand, however the inlet that allows gas to flow from the meter to the fitting lines in plugged hence the gas doesn’t flow. The total number of metered supply points supports AEMO cost allocation process. | AEMO | 2020-03-04 | GRCF | Vic and Qld | Procedure and system impacts | Discussion only | Apr 2020 update - Yet to be prioritied
Retail Gas | IN009/20W |  | There is a possible typographical error in appendix 4 (Auditor’s deed of undertaking) clause 9. Reference to clause 359 should be clause 358. | AEMO | 2020-04-14 | GRCF | WA |  | Discussion only | Apr 2020 update - Yet to be prioritied
Retail Gas | IN016/20 | Corrections to SA RMP clause 8.6 | The old version of the SA RMP clauses 220(2), 221, 222 and 223 (1) contained formulas however in the effort to harmonise the SA RMP, these formulas didn’t find there way into clauses 8.6.2(b) Pipeline Injections , 8.6.3 Total Corrected Injections , 8.6.4 User interval-metered withdrawals and 8.6.5(a) Net system load. | AEMO | 2020-06-01 | GRCF | SA | TBA | Discussion only | Yet to be prioritiesed
Retail Gas | IN018/20 |  | "Residual changes that relate to the bundle release program of work targeted for Q4 2021. These changes are: - delete the T71 (Amend Customer Details Six Monthly Refresh) transaction. This relates to PPC feedback received for IN011/20. - The code for Life Support contact name in PBP 1 Table of transaction (element tab) should be “N” and the the code for Life Support equipment in PBP 1 Table of transaction (element tab) should be “Y”. This relates to PPC feedback received for IN011/20. - the event codes for CND mentioned in PBP 3 (section 4.6.2.1) are superfluous. These same events are mentioned in other technical protocols. AEMO proposes to adding the corresponding electricity codes 1970 and 1939 as mentioned in the electricity B2B procedures. This relates to PPC feedback received for IN011/20." - The descriptions for the allowable values under CDN/CDR "Reason" still contain electricity terminology (e.g. LNSP/MC/MBP instead of "Distributor") - has been changed in WA to the correct terminology but not in other jurisdictions - The referance numbering in in Figure 4-63 in PBP3 interface definations is incorrect. The numbering need to match that contained in PBP 1 Process Flow Diagrams document for the Customer Details Notification diagram 4.1. (This relates to the IIR feedback on IN011/20 - See ref #17) - The Figure 4-65 in PBP3 Interface Definations doc needs to be updated. (This relates to the IIR feedback received for IN011/20 - see ref #28) - A diagram for the Customer Details Request need to be included in the PBP1 Process Flow Diagram. (See IIR feedback for IN011/20 ref # 33) - In relation to SA/WA Spec pack FRC B2B System Interface Defination (4.6.2.1 & 4.6.3) the event codes need to be reviewed. See IIR feedback for IN011/20 ref #38 | AEMO | 2020-07-13 | GRCF | All | TBA | Discussion only | Yet to be prioritiesed
Retail Gas | IN019/20 |  | A PwC found that the calculation process relies on the completion of the Aggregate pipeline allocation (INT772) report, which is automatically produced by AEMO. The INT772 report for August 2019 was prepared on 20 September 2019, resulting in a one (1) business day delay in the production and delivery of the monthly NAF file, which took place on 23 September 2019. Clause 8.11.15 of the NSW/ACT Retail Market Procedures requires AEMO to perform monthly distribution system allocation (DSA) calculations for final settlement by the 15th business day after the end of a month. Initial anlysis suggest that NSW/ACT Retail Market Procedures to better align NAF delivery timelines requirements to the National Gas Rules (469) and STTM Procedure (7.2.4(c)). | AEMO | 2020-06-22 | GRCF | NSW/ACT | TBA | Discussion only | Yet to be prioritiesed

## GAS - On Hold
MARKET | CHANGE ID INnnn/yy ICFnnnn | TITLE | SHORT DESCRIPTION | PROPONENT (COMPANY & CONTACT) | DATE RAISED | CONSULTATIVE FORUM | JURISDICTION | SYSTEM IMPACT | CURRENT STATUS | PROGRESS COMMENTS
Retail Gas | IN014/12 |  | As per the recommendation in the “Discussion Paper on the results of the DUAFG Wash Up Options Evaluation and Global Settlements in Victoria" (IN002/09), amend the existing “Wholesale market distribution UAFG procedures (Vic)” to reflect the principles set out in Option A of the discussion paper | AEMO | 2012-03-27 | GRCF | VIC | Procedure and system impacts | Discussion only | Sept 2019 uppdate (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. June Prioritisation session - GRCF requested the Options Paper be re-circulated and considered at a subsequent GRCF meeting. Considered to be a medium priority. Apr 2016 Update - Updates to be made at prioritisation session. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this issue should remain on hold. Mid Jan 2014 update - No Change. Work still progressing internal but low priority.
Retail Gas | IN019/13 | Metering Obligations in the RMP | Obligation in Procedures cannot be a conduct provision. The drafting for the Non DTS (Chap 8) just incorporate the requirements of the specified rules (by reference) into a separate framework for non-DTS systems which doesn’t expand the scope of the NGR. The NGR conduct provision will still be limited to declared transmission and distribution systems. (see also IN002/11) | AEMO | 2013-10-01 | GRCF | VIC | Procedure-only | Discussion only | June 2016 Prioritisation session update - AEMO to review to determine whether it is a material regulatory gap. Considered to be a low priority. Apr 2016 Update - Updates to be made at prioritisation session. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this the status of this items should be changed to on hold.
Retail Gas | IN012/15 |  | During the NARGP consultation it was revealed that the NGR prescribe the obligation for the NWO to provide a listing of all DPI. The new RMP include a obligation for the NWO to provide such a listing. Similar obligation in other jurisdictional RMP contain the same obligations. Have the obligation reside in the NGR is superfluous and can be delated. AEMO support the idea to request a change to the NGR and when that done remove the definition DPI full listing. (See IIR consolidated Response document ref # 41). | to be determined | 2015-02-17 | GRCF | All | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Oct 2015 Update – AEMO analysis determined that this proposal required either AEMO legal review and/or has NSW/ACT links. At the Aug GRCF meeting the GRCF supported AEMO recommendation to place this proposed change on hold till 6 months post NARGP implementation which is targeted for 2nd May 2016 Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN031/15 | Retail Reports | This intiative seeks reports to standardise the information and incorporate all markets to allow for comparisons | AGL | 2015-08-18 | GRCF | All | TBA | GMI | Sept 2019 update (Sept 2020 Prioritisation session) - Same as previous years, best left with the proponent (AGL) to argue the need to progress otherwise propose that this GMI be withdrawn Feb 2018 Update - Prioritisation session update - GRCF agreed to leave this as “on-hold” Oct 2015 Update - Discussed at GRCF Aug 2015 meeting and agreed good idea but also noted industry resource constraints at the moment would be difficult to progress. Agreed to put in the on hold category.
Retail Gas | IN002/15 | Energise meter via Customer Transfer (Deemed Transfer) | Currently the SA procedures, systems and processes facilitate a mechanism to energise a meter via a Transfer should the Transfer be a “move in” and the meter currently disconnected. This process removes the need for a Retailer to raise a Meter Turn-on (MTN) service order request. The NARGP decided not to include this facility for NSW/ACT but rather consider a broader implementation that includes VIC and QLD. | AEMO | 2015-01-22 | GRCF | VIC, QLD and NSW/ACT | Procedure and system impacts | Discussion only | Sept 2019 update - At the 2020 GRCF proiritisation session, AEMO proposed that this should be a candidate for 2020. The GRCF did not support this proposal. 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this would need system changes for Retailers and DBs.Moved to On Hold tab because GRCF stakeholders agreed items requiring system changes would not be immediately progressed. Item supported by APA. Apr 2016 Updates to be made at prioritisation session. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN030/15 |  | Additional estimation_substitution_reason_codes to be discussed in the GRCF for a cross-jurisdictional harmonised approach. The addition of extra Substitution_Reason_Code in the MDN. Code 19 – Access to Meter Unsafe – This is equivalent to the current “Unsafe” code (can’t read code 08) which is reported to retailers. Code 20 – Can’t Locate Address – Required in order to distinguish from 04 Can’t Locate Meter (address found but not the meter). Code 21 – MDL Issue – Required to match the CRC 13 we currently send to retailer. These initiatives have been put forward by NARGP | GRCF | 2015-08-04 | GRCF | All | Procedure and system impacts | Discussion only | Sept 2019 (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to require system changes for Retailers and DBs and agreed to move this to the On Hold tab. Apr 2016 Update - Updates to be made at prioritisation session. Aug 2015 Update - Yet to be prioritised.
Retail Gas | IN006/16 | Cross jurisdictional harmonised approach for safety related DB initiated disconnections | During NARGP project it was identified that there seems to be ambiguity on which SO could be used for safety related disconnections. APA uses DB initiated SDR-MRM and it seems that these DB initiated SOs did not cause any issues in Retailer systems and were processed appropriately. The SOs were not rejected/ NACK’d and the meter reads processed correctly. Jemena has also agreed to use MRM-SDR, similar to APA in NSW-ACT. Couple of issues were raised: 1. One retailer raised an issue in terms of charging their customers for these SOs may be an issue. 2. Another retailer noted that they were able to process DB initiated MRM but not a SDR. It was agreed that it may be prudent to refer this to the GRCF for a cross jurisdictional harmonised approach for safety related disconnections. | To be determined | 2016-02-18 | GRCF | All | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is a low priority and likely to need system changes for Retailers and DBs it was agreed this could be move to On Hold tab. Apr 2016 Updates to be made at prioritisation session. Yet to be prioritised. Raised during the NARGP consultationApr 2016 Update - Updates to be made at prioritisation session. Apr 2016 Update - Updates to be made at prioritisation session. Feb 2016 Update - Yet to be prioritised.
Retail Gas | IN009/16 | PBP5 clarification item - Total Gas Injected report update | Amend the TotalGasInjectedRpt for NSW-ACT as per issues identified during the NARGP project. The context of the naming of the fields depending on the outcome may need to change. GasDay in the current report actually refers to the date the data was updated/received, vs GasDayHistorical which is actually the gas date the data applies to. If adding a timestamp, it may make sense to rename GasDayHistorical to GasDay and rename GasDay to LastModifiedDateTime | AEMO | 2016-03-03 | GRCF | NSW-ACT | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this was a low priority and on hold. Mar 2016 Update - Yet to be prioritised.
Retail Gas | IN011/13 | 1.Non-DTS Metering | RMP only changes for Non DTS interval metering to remove regulatory gap | AEMO | 2013-07-01 | GRCF | VIC | Procedure-only | GMI | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. 28 Apr 2016 GRCF prioritisation session - GRCF participants agreed this item may need a rule change,was a low priority and is to be moved to the On Hold tab. Apr 2016 update - the Adjunct letter Agreement commenced 1 July 2015 for an 18 month term (1 Jan 2017), and will automatically renew for rolling 6 month periods unless terminated by agreement of the parties. 12 March 2015 Update: GRCF agreed that the proponent should AEMO instead of AusNet Services. To align with other agreements P.Ellis (AusNet Service) proposed end of December 2015 as the target release which was not opposed by the GRCF.
Retail Gas | IN016/16 | PBP5 Daily MDN Index Value amendment | Evaluate the issue with Jemena/AAD provision of ‘Current_Index_value’ in transaction 2115 (MeterDatNotificaiton for Daily meters to Retailers from the Distributor) which is noted as ‘Mandatory’ in the PBP5. In certain scenarios the index values may not align with the energy values. GRCF to evaluate whether daily MDN index values can be noted as being ‘optional’ in the PBP5. | Jemena | 2016-04-04 | GRCF | NSW-ACT | Procedure and system impacts | Discussion only | Mar 2018 update - Jemena advised that this is still an issue and believe the retailers are still actioning the workaround of disregarding the misalignment of index value to energy value. If the retailers continue with this practice of disregarding the information as published, then Jemena will agree to remove this item from the GRCF register. They need assurance that we will not have a flood of rejections or disputes. Apr 2016 Update - Updates to be made at prioritisation session.
Retail Gas | IN018/16 | NSW-ACT WWT clarification item: Move-in transfers and deemed Service Orders | Resolve disconnect between APA WWT implementation, based on their SA system, and adoption of move-in transfer objection period of 5 days as per wider NSW-ACT. Issue arises when prospective transfer date is within the 5 day objection window, leading to APA not raising the deemed SRT or MTN as required - as it is contingent on a PEN notification from AEMO straight after the REQ notification. GRCF to investigate whether a change is required to RMPs and PBP6 where no Objection period is applicable for move-ins in WWT and as such a PEN is sent earlier to APA. Noting the volumes of move-ins are about 130 per year, with none of them requiring reconnections. APA has a workaround in place currently till a permanent fix is implemented. | To be determined | 2016-04-08 | GRCF | NSW-ACT | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Apr 2016 Update - Updates to be made at prioritisation session.
Retail Gas | IN023/16 | PBP5 conformance- Jemena/AAD network bills | After the NARGP market trials AEMO was notified that Jemena is not conforming to the PBP5 requirements in regards to network bills. Jemena to ensure inclusion of an adjustment indicator of ‘C’ instead of ‘N’ to generate the cancellation of a previously provided Excluded service item. PBP3 (and by extension PBP5) state that ‘C’ is to be utilised for Cancellation of previous transactions in the excluded services. | To be determined | 2016-04-21 | GRCF | NSW-ACT | Procedure and system impacts | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Apr 2016 Update - Updates to be made at prioritisation session.
Retail Gas - WA | IN010/19W | Clause 211 – AEMO Intra Day Reporting | Confirm with the participants if the intraday reports specified in clause 211 of the WA RMP are still valid (i.e. if participants use the reports and find the data in the report useful). If the reports are no longer valid then remove the reporting requirements from the WA RMP.This will require AEMO IT system changes. Industry Benefit : Reduces the time, effort and costs associated in producing reports that are not be used in the market. | AEMO | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Feb 2019 Prioritisation session update – GRCF supported this idea to leave on hold.
Retail Gas - WA | IN011/19W | Report Timing | There are number of reports which AEMO must provide within 5 hours after the end of a gas day. Review the timing and requirement of these reports, e.g. can the time be extended; can it be on a reasonable endeavours/as soon as practical basis instead of ‘must’?The reports are specified in the following clauses of the WA RMP:228(3), 246(1), 248(1), 286, 287(1), 288(1), 296(1),299(1), 300(1), 300(2)(a)-(f), 300(3), 302(3).This will require AEMO IT system changes. | AEMO | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Feb 2019 Prioritisation session update – GRCF supported this idea to leave on hold.
Retail Gas - WA | IN012/19W | Users permitted to object to a transfer | It is proposed that the rules be changed (similar to the NEM) to permit users to object to a transfer where a customer has an outstanding debt. | Synergy | [5 empty] | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Feb 2019 Prioritisation session update – GRCF supported this idea to leave on hold.
Retail Gas - WA | IN001/09W | Emergency Provisions in the Procedures | Consider: • the ROLR provisions in the Procedures; and • inclusion of the EMD arrangements (or similar) that applied in SA for WA Procedures (formally part 5.12B – Gas Emergencies). | AEMO | 2009-11-18 | GRCF | WA | TBA | Discussion only | Sept 2019 update (Sept 2020 Prioritisation session) - GRCF supported AEMO proposal to leave this as on hold. Arp 2016 Update: (tracking no longer required): The RCC will need to consider emergency provisions in the Procedures when the Public Utilities Office and/or ERA raise emergency management in the energy sector – likely to occur as part of the Electricity Market Review.
Retail Gas - WA | IN002/19W | EIC | Reduce regulatory administration in WA by removing some references to explicit informed consent. - Rule 72 requires a user to obtain explicit informed consent before making a request for a MIRN discovery. It is proposed that (similar to the Electricity Customer Transfer Code) the requirement for explicit informed consent is removed. Removing this requirement reduces costs and administrative burden and improves the efficiency of the quotation process. This change will not affect the interests and rights of customers. The rules require a user to obtain explicit informed consent before making a request for historical data in order to respond to a customer’s request for a supply quotation. It is proposed the requirement for explicit informed consent is removed and replaced instead with substantiation that the request was made subject to a customer’s request for a supply quote. This change will not affect the interests and rights of customers. | Synergy | 2019-02-19 | GRCF | WA |  | Discussion only | Sep 2019 update - Synergy (proponent) requested to move this initiative to 'On hold' area. Jul 2019 update - AEMO followed up with Synergy on progress on draft GMI early July. Synergy advised at the draft GMI would not be available for the July meeting. April 2019 update - AEMO internal review Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. New issue raised

## GAS - Completed or Withdrawn
MARKET | CHANGE ID INnnn/yy ICFnnnn | TITLE | SHORT DESCRIPTION | PROPONENT (COMPANY & CONTACT) | DATE RAISED | CONSULTATIVE FORUM | JURISDICTION | SYSTEM IMPACT | CURRENT STATUS | PROGRESS COMMENTS
Retail Gas | IN020/09 |  | GRCF N&A to consider the STTM requirement for backwards reconciliation and the replacement of current balancing mechanisms for the NSWWilton network section. | GRCF-N&A | 2009-04-14 | GRCF | NSW | Changes to the GRMBS and changes to aseXML schema | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009.
Retail Gas | IN021/09 |  | GRCF N&A to consider the STTM requirement that ‘user allocation’ data for the NSW Wilton network section be made available to the STTM systems by no later than 1100h on the day following the end of a gas day. | GRCF-N&A | 2009-04-14 | GRCF | NSW | Changes to the GRMBS and changes to aseXML schema | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009.
Retail Gas | IN022/09 |  | GRCF - N&A to consider the STTM requirement that the STTM systems provide Total Daily Quantity (TDQ) data for the NSWWilton network section to the Data Estimation Entity (DEE) at the end of each month for STTM settlement purposes. This data will replace the ‘provisional’ TDQ data that is provided by the network operator on ‘day + 1’. | GRCF-N&A | 2009-04-29 | GRCF | NSW | Changes to the GRMBS and changes to aseXML schema | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009.
Retail Gas | IN024/09 |  | GRCF- N&A to consider the proposed approach to allocating Change in Linepack (CLP) and Unaccounted for Gas (UAG) amounts to users for the NSWWilton network section. | GRCF-N&A | 2009-05-27 | GRCF | NSW | Changes to the GRMBS and changes to aseXML schema | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009.
Retail Gas | IN025/09 |  | The STTM Project Office, with Jemena Gas Networks (JGN) and the Market Operator have developed a mechanism that will enable the exclusion of gas quantities (known as 'matched allocations') from STTM settlement in certain and limited circumstances. The GRCF N& A is requested to consider the proposed approach and provide feedback on whether the proposed AEMO Procedure and GRMBS changes would achieve the STTM requirement. | GRCF-N&A | 2009-06-16 | GRCF | NSW |  | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009.
Retail Gas | IN026/09 |  | Under Change Request 116 (CR116), the sum of the ‘user allocation’ amounts sent to the STTM systems will not match the aggregate pipeline allocations. This is because agreement has not been reached on how the difference between actual and estimated non‑daily meter readings (the ‘reconciliation amount’) will be allocated by the GRMBS. Three options have been proposed to allocate reconciliation amounts and the GRCF - N&A has been requested to consider the advantages and disadvantages of each of these options. | GRCF-N&A | 2009-07-14 | GRCF | NSW | Changes to the GRMBS and changes to aseXML schema | IMP | Consolidated as part of IN044/09. PPC to be raised on 13 October 2009. Issues relating to monitoring of adjustment amount to be developed further in a paper presented to the GRCF - NSW & ACT at its 19 September 2009 meeting.
Retail Gas | IN023/09 |  | GRCF N&A to consider issues associated with the transition from existing balancing and reconciliation processes to the STTM processes for the NSW Wilton network section. This includes consideration of residual imbalance and reconciliation account balances. | GRCF-N&A | 2009-05-27 | GRCF | NSW | Changes to the GRMBS | IMP | For discussion at GRCF-N&A. - Date to implement 1 Sept 2010
Retail Gas | IN027/09 |  | Clarification of Clause 9.2 of the Procedures, the B2B process and the circumstances in which a “creation of delivery point transaction” should be initiated by a user | GRCF-N&A |  | GRCF | NSW | N/A | IMP | AEMO decision to be made no later than 19 July 2010 - Date to implement 1 Sept 2010
Retail Gas | IN044/09 |  | Changes to the Retail Market Procedures (NSW and ACT) required to support the STTM. Consolidation of issues IN020/09, IN021/09, IN022/09, IN024/09, IN025/09, and IN026/09 | GRCF-N&A | 2009-10-07 | GRCF | NSW | Changes to the GRMBS | IMP | AEMO decision published February 2010 - Date to implement 1 Sept 2010
Retail Gas | IN016/09 |  | Revise RMR clause 7.8 to prevent revision settlements overlapping a final settlement | GRCF-Q | 2009-02-01 | GRCF | QLD |  | IMP | I&IR posted on AEMO website on 4/9. Consultation closes 25/9.
Retail Gas | IN017/09 |  | Change to Host Retail Definition in Retail Gas Market Procedures (Queensland) | GRCF-Q | 2009-04-01 | GRCF | QLD |  | IMP | I&IR posted on AEMO website on 4/9. Consultation closes 25/9.
Retail Gas | IN019/09 |  | Change the date on which the FRC Monthly report is produced report to be 10 days after the end of the last business day of the month | GRCF-Q | 2008-09-03 | GRCF | QLD | Report change | IMP | This report change was implemented for the August 2009. See email from L. Doerre on 7/9/09
Retail Gas | IN030/09 |  | Publish Envestra and ATP All Gas Meter Measurement Schemes on AEMO website | GRCF-Q | 2009-08-19 | GRCF | QLD |  | IMP | R. Abbott and J. Jamieson have provided schemes. Details e-mailed to GRCF-Q reps on 28/8/09
Retail Gas | IN032/09 |  | Add Metering SME to Qld B2B contact list for DB, RB and AEMO. | GRCF-Q | 2009-09-02 | GRCF | QLD |  | IMP | This was agreed at Sept 09 QGTPWG meeting.
Retail Gas | IN038/09 |  | Meter Fix - MIBB Report (Queensland) | GRCF-Q | 2009-09-14 | GRCF | QLD |  | IMP | IMPLEMENTED IN MARCH 2010
Retail Gas | IN011/10 |  | Update on the current balance of the Participant Compensation Fund (PCF). Also a reminder to Retailers about the mechanism to limit their imbalance position on exceedance charges | GRCF-Q | 2010-02-25 | GRCF | QLD |  | WD | Discussion at GRCF-Q on 28th April. Noted. Origin advised that a trade will be done soon.
Retail Gas | IN014/09 |  | Review the need for a Customer Details six monthly refresh transaction. This transaction is used in Vic and is currently in the QLD GIP. This transaction has not been tested for QLD. Consider this issue as part of the Post Implementation Review | GRCF-Q | 2007-06-20 | GRCF | QLD |  | WD | This was agreed to be withdrawn as all Retailers are providing the Customer Details in Qld - even without the process being tested in the implementation of FRC in Qld.
Retail Gas | IN003/10 |  | Amendments to be made to Qld Retail Market documentation to update references to parent regulatory instruments changed as a result of the creation of the new gas framework and the start of AEMO (see IN011/09) | GRCF-Q | 2010-02-24 | GRCF | QLD |  | IMP | Target implementation is July 2010. AEMO has updated documentation. PPC to be raised 1 April 2010. See IN011/09 for more information
Retail Gas | IN015/09 |  | INT549 not displaying rolling 31 days | ITDF | 2008-09-01 | GRCF | QLD |  | WD | To be raised at Q-ITDF
Retail Gas | IN005/10 |  | Clause 1.6.1 states that AEMO must commence a review before 1 July 2010. This review looks at chapter 5 (interval metering), the exclusive preparation of profile data (Attachment 4) and the methodologies in Attachment 1,2 and 3 | GRCF-Q | 2010-02-25 | GRCF | QLD |  | IMP | Consultation Complete.
Retail Gas | IN023/10 |  | Incorrect MIRN Registration |  | 2010-09-21 | GRCF | QLD | n/a | IMP | This item is completed.
Retail Gas | IN025/10 |  | Proposed change to gas day definition to align with STTM | GRCF-Q | 2010-09-23 | GRCF | QLD |  | WD | 8.00am gas day start time retained - no changes to RMP-Q required
Retail Gas | IN029/10 |  | STTM – Treatment of Sandy Creek and Brightview | GRCF-Q | 2010-10-19 | GRCF | QLD | configuration changes | WD | Discussed at GRCF-Q meeting on 27 Oct 2010. Agreed that two areas would remain outside of STTM. Refer to IN041/10.
Retail Gas | IN031/10 |  | STTM - Reporting | GRCF-Q | 2010-10-19 | GRCF | QLD |  | WD | Final reporting requirements agreed at GRCF-Q meeting on 17 Nov 2010. No changes required.
Retail Gas | IN035/10 |  | Change to Substitution and Estimation Methodologies in RMP Q | GRCF-Q | 2010-11-04 | GRCF | QLD |  | WD | Joint GMI (with AEMO) prepared for 8 Dec GRCF-Q meeting. See IN044/10.
Retail Gas | IN041/10 |  | Treatment of differences between CTM and Interval meters at Sandy Creek and Brightview | GRCF-Q | 2010-11-09 | GRCF | QLD |  | WD | Discussed at GRCF-Q meeting on 17 Nov 2010. Options 1 & 4 agreed. No PPC required.
Retail Gas | IN035/09 |  | Version 5.0 of the AEMO/REMCo Specification Pack | GRCF-S | 2009-09-08 | GRCF | SA |  | IMP | Decision approving new Spec Pack published on 30/09/10
Retail Gas | IN041/09 |  | New version of the GBOid table need to be published to include new e-mail contacts for AEMO and some other minor coorections. | GRCF-S | 2009-09-22 | GRCF | SA |  | IMP | GBO id released on 22/11/09
Retail Gas | IN046/09 |  | Possible abnormality between the SA Retail Market Procedures and the SA Distribution Code | GRCF-S | 2009-11-11 | GRCF | SA |  | WD | Action for AGL and Envestra to discuss offline
Retail Gas | IN040/09 |  | The term "gate point estimation recalculation threshold value" and swing sevice recalculation threshold value is referred to in clause 301B and 301C, howeever the term in not defined in clause 2. | GRCF-S | 2009-09-17 | GRCF | SA |  | WD | For discussion at GRCF-S
Retail Gas | IN029/09 |  | STTM changes to Parts 5.4 and 5.6 of the SA Retail Market Procedures | GRCF-S | 2009-08-20 | GRCF | SA |  | IMP | Approved on 1/02/10
Retail Gas | IN033/09 |  | SA Transitional Provisions (post STTM) | GRCF-S | 2009-09-08 | GRCF | SA |  | IMP | Approved on 26/05/10
Retail Gas | IN034/09 |  | Secondary STTM changes (apart from Parts 5.4 and 5.6) for the SA Retail Market Procedures. | GRCF-S | 2009-08-20 | GRCF | SA |  | IMP | Approved on 19/03/10
Retail Gas | IN047/09 |  | STTM daylight savings changes for the GRMS | GRCF-S | 2009-11-11 | GRCF | SA |  | IMP | Approved on 19/03/10
Retail Gas | IN001/10 |  | APA data file processing for the SA market | GRCF-S | 2010-01-07 | GRCF | SA |  | IMP | Approved on 6/05/10
Retail Gas | IN005/09 |  | CATS transfers and the linking of Special Read Request (AGL's Q3&4) | GRCF-V | 2009-05-12 | GRCF | VIC |  | WD | Currently with AGL (GTPWG rep) to further define issue and present marked up procedure changes
Retail Gas | IN008/09 |  | Meter Fix - MIBB Report (Victoria) |  | 2008-09-15 | GRCF | VIC |  | IMP | IMPLEMENTED IN MARCH 2010
Retail Gas | IN013/09 |  | Interoperability. Participants have identified that they expect to be able to reduce their costs if the Gas and Electricity B2B hubs (and Electricity) interoperated, thereby allowing them to use one hub for all their B2B transactions. This would allow each participant to use the B2B protocol and data network that they believe best meets their business drivers. The intention is to allow participants to choose protocol(s) they consider appropriate. |  | 2006-06-06 | GRCF | VIC | IT systems | WD | GRCF-V AGREED TO WITHDRAW AND LEAVE FOR DISCUSSION AT THE ENERGY MARKET IT STEERING COMMITTEE MEETING.
Retail Gas | IN010/09 |  | Develop agreed work arounds for the List of RoLR Known Issues and Consequences including Retrospective Transfers to the RoLR Date (assuming RoLR event has occurred) should not be allowed as RoLR reads were estimated. | GRCF-V | 2009-06-25 | GRCF | VIC |  | IMP | GRCF-V have reviewed. AEMO to updated with one further known consequence before publishing on the website.
Retail Gas | IN003/09 |  | Minor GIP change for RoLR - Process Flow Diagrams not consistent with Rules or Build Pack with respect to RoLR data delivery | GRCF-V | 2009-06-25 | GRCF | VIC |  | IMP | This change was rolled into IN011/09 - implemented - effective 1 July 2010
Retail Gas | IN039/09 |  | 2nd MFX raised on Decommissioned sites (ie Meter had previously been removed) with inconsistent processes resulting in FRO mismatches between Market Operator, Distributor and Retailer. | GRCF-V | 2009-09-14 | GRCF | VIC |  | WD | Envestra requested that this GMI be withdrawn.
Retail Gas | IN012/10 |  | Undertake a review of the non declared transmission systems arrangements | GRCF-V | 2010-05-05 | GRCF | VIC |  | IMP | Review complete
Retail Gas | IN012/09 |  | Additional no read codes | GRCF-V | 2006-04-04 | GRCF | VIC | Schema Change | WD | GTPWG have recommended that CR83 be deferred until there is clarity regarding a process for updating enumerated lists without the requirement for a schema release
Retail Gas | IN011/09 |  | Amendments to be made to Vic Retail Market documentation to update references to parent regulatory instruments changed as a result of the creation of the new gas framework and the start of AEMO | GRCF-V | 2009-06-02 | GRCF | VIC & QLD |  | IMP | IIR went out for consultation. Comments due back on 3 June. No comments were received and approved by CEO 7 June. Implementation date is 1 July 2010.
Retail Gas | IN017/10 |  | Removal of redundant clauses in the RMP (Qld) to do with the replacement of basics meters to interval meters prior to 1 July 2009. This has been implemented and is no longer relevant. | GRCF-Q | 2010-08-17 | GRCF | QLD |  | IMP | Implemented on 1 February 2011.
Retail Gas | IN018/10 |  | Add the Type 4 "Approved Estimation" and "Approved Substitution" methodologies to the RMP(Q). Support DB's in the co-ordination of the removal of the methodologies from the MMS. | GRCF-Q | 2010-08-17 | GRCF | QLD |  | IMP | Implemented on 1 February 2011.
Retail Gas | IN024/10 |  | Correction for 6.5.1 of the RMP | GRCF-Q | 2010-09-22 | GRCF | QLD | n/a | IMP | Implemented on 1 February 2011.
Retail Gas | IN033/10 |  | Reinsert the balancing parameters that were lost in the transition process (rules to procedures) | GRCF-Q | 2010-10-28 | GRCF | QLD |  | IMP | Implemented on 1 February 2011.
Retail Gas | IN045/09 |  | Provision of UAFG data on a daily basis to UAFG Supplier | GRCF-Q | 2009-10-07 | GRCF | QLD |  | WD | No change to UAFG data provision
Retail Gas | IN051/09 |  | Origin Energy GRMS data reports | GRCF-S | 2009-11-19 | GRCF | SA |  | IMP | Approved on 6/05/10 - Implementation date TBA
Retail Gas | IN002/10 |  | AGL request for new gas settelment reports | GRCF-S | 2010-02-15 | GRCF | SA |  | IMP | Approved on 30/08/10 - Implementation date TBA
Retail Gas | IN036/09 |  | Gas B2B Service Order Back-up Plan. This is a process failure work around. | GRCF-S | 2009-09-08 | GRCF | SA |  | IMP | For discussion at the GRCF-S. To be consolidated with Vic and Qld.
Retail Gas | IN043/09 |  | A cost-benefit analysis of upgrading the GRMS for both WA and SA to make it more auditable in each of WA and SA, with cooperation between AEMO and REMCo. (Links to WA Issue # 122 for RCC) | GRCF-S | 2009-10-16 | GRCF | SA |  | WD | For discussion at GRCF-S
Retail Gas | IN007/09 |  | Customer Requests To Obtain Current FRO (for MRM and SDR Service Order Types) | GRCF-V | 2008-06-01 | GRCF | VIC |  | IMP | AEMO has published information on the pilot program on the AEMO website (VIC Participant Only Section).
Retail Gas | IN009/09 |  | Gas B2B Service Order Outage Plan (Vic). This is a process failure work around. | GRCF-V | 2008-08-21 | GRCF | VIC |  | IMP | This has been implemented. Outage Plan is published on the industry only section of the website
Retail Gas | IN018/09 |  | Gas B2B Service Order Outage Plan (Qld). This is a process failure work around. | GRCF-Q | 2008-08-21 | GRCF | QLD |  | IMP | This has been implemented. Outage Plan is published on the industry only section of the website
Retail Gas | IN028/09 |  | Origin would like GRCF - NSW & ACT to consider extending the provision of user allocation data to all NSW networks registered in GRMBS (currently agreed under CR116 for STTM networks). | GRCF-N&A |  | GRCF | NSW | Changes to the GRMBS | IMP | AEMO decision published March 2010 - implementation on 18 Jan 2011
Retail Gas | IN048/09 |  | Dispense with daylight savings for non NSW-Wilton network sections. | GRCF-N&A | 2009-11-19 | GRCF | NSW | N/A | IMP | AEMO decision published, with implementation on 1 October 2010.
Retail Gas | IN050/09 |  | AGL and Origin Energy data reports | GRCF-N&A | 2009-11-19 | GRCF | NSW | Changes to the GRMBS | IMP | AEMO decision published June 2010 - implementation on 18 Jan 2011
Retail Gas | IN004/10 |  | Market design issues related to cumulative imbalances in no OBA network sections | GRCF-N&A | 2010-02-25 | GRCF | NSW |  | WD | On 14/09/2010 the GRCF agreed that an audit of users’ aggregate CI positions under the clause 30.8 process should be performed six months after the second CI recalculation for the ACT-Canberra and NSW-Wilton network sections had been completed. After that the GRCF will assess whether the next clause 30.8 CI audit should be performed on a six monthly basis or on a 12 monthly basis
Retail Gas | IN006/10 |  | Negative STTM distribution system allocations caused by negative CLP | GRCF-N&A | 2010-03-23 | GRCF | NSW |  | IMP | To be implemented on 16 Feb 2011
Retail Gas | IN014/10 |  | Cumulative Imbalance (CI)/Reconciliation Account Balance (RAB) Cash Settlement Process Non Material Amendments | GRCF-N&A | 2010-07-20 | GRCF | NSW | Minimal | IMP | Implemented on 18 January 2011
Retail Gas | IN049/09 |  | Amendments to change of user transactions for daily metered sites | GRCF-N&A | 2009-11-19 | GRCF | NSW | Changes to the GRMBS | IMP | AEMO decision published on 3 November 2010- implementation on 02 Mar 2011
Retail Gas | IN019/10 |  | Review and update AEMO Consumed Energy Scenario (Queensland) | GRCF-Q | 2010-08-18 | GRCF | QLD | n/a | IMP | AEMO approved changes 24/2/11. Changes became effective on 21/3/11
Retail Gas | IN036/10 |  | Update to Procedure : Queensland gas Retail Market - Procedure to Validate Aggregated Injections received from Retailers | GRCF-Q | 2010-11-04 | GRCF | QLD |  | IMP | AEMO approved changes 24/2/11. Changes became effective on 21/3/11
Retail Gas | IN001/11 |  | Update to Queensland Gas Interface Protocol | GRCF-Q | 2011-01-06 | GRCF | QLD |  | IMP | AEMO approved changes 24/2/11. Changes became effective on 21/3/11
Retail Gas | IN001/09 |  | Review and update AEMO Consumed Energy Scenario (Victoria) | GRCF-Q | 2006-08-23 | GRCF | VIC | No | IMP | AEMO approved changes 24/2/11. Changes became effective on 21/3/11
Retail Gas | IN037/09 |  | Review chapter 7 of the Retail Market Procedures (Victoria) to see how it would apply to PTS and non-PTS in light of the NGL/NGR framework. | GRCF-V | 2009-09-08 | GRCF | VIC |  | WD | Withdrawn. Will be captured under IN002/09
Retail Gas | IN005/11 |  | New AEMO MIBB guide to replace all other MIBB user guides (eg Master MIBB Report List, Participant guide to the MIBB and QLD Interim Master MIBB) | GRCF-Q | 2011-02-01 | GRCF | Vic & QLD |  | IMP | Implemented on 4 April
Retail Gas | IN031/09 |  | Proposal to change the state wide average daily flow weighted heating value used in the basic meter energy calculation to the daily flow weighted zonal heating value | GRCF-V | 2009-08-24 | GRCF | VIC |  | WD | Withdrawn by R.Abbott at GRCF-V meeting held 13th Apr 11.
Retail Gas | IN042/09 |  | A cost-benefit analysis for providing after-hours helpdesk support in WA and SA, with cooperation between AEMO and REMCo. (Links to WA Issue # 121 for RCC). | GRCF-S | 2009-10-16 | GRCF | SA |  | WD | For discussion at GRCF-S
Retail Gas | IN015/10 |  | Verification of shipper on sub-network | GRCF-S | 2010-08-11 | GRCF | SA |  | IMP | Approved by AEMO on X. Became effective on 19/05/11
Retail Gas | IN032/10 |  | Change management provisions for the Specification Pack and FRC Hub Conditions | GRCF-S | 2010-10-21 | GRCF | SA |  | IMP | Approved by AEMO on X. Became effective on 19/05/11
Retail Gas | IN047/10 |  | Settlement run identifier | GRCF-S | 2010-12-10 | GRCF | SA |  | IMP | Approved by AEMO on X. Became effective on 19/05/11
Retail Gas | IN007/10 |  | Changes to the calculation DI and UDW | GRCF-S | 2010-03-25 | GRCF | SA |  | IMP | Approved by AEMO on X. Became effective on 19/05/11
Retail Gas | IN008/11 |  | Establishment of the RBPWG | GRCF-V GRCF-Q GRCF-S | 2011-04-05 | GRCF | VIC & QLD & SA |  | IMP | Approved by AEMO on 13/05/11. Became effective on 13/05/11
Retail Gas | IN009/11 |  | FRC HUB Communication Protocol | GRCF-V GRCF-Q GRCF-S | 2011-04-05 | GRCF | VIC QLD SA |  | WD | Withdrawn by AEMO as it will be included on the B2B Contact List.
Retail Gas | IN045/10 |  | Removal of Gas Balancing Arrangements in QLD Non-STTM Withdrawal Zones | GRCF-Q | 2010-12-01 | GRCF | QLD |  | IMP | No comments received on IIR. AEMO approved changes 25 May. Implementation of $0 exceedance charge is 1 July. Then 9 months of revisions to be processed before PCF is redistributed.
Retail Gas | IN013/10 |  | Crossed Meters | GRCF-N&A |  | GRCF | NSW |  | WD | To be included in the B2B project
Retail Gas | IN034/10 |  | QLD MIRN Reconciliation | GRCF-Q | 2010-11-04 | GRCF | QLD |  | IMP | AUG 2011 Update - MIRN reconciliation complete.
Retail Gas | IN042/10 |  | Changes to the FRC B2M-B2B Hub System Specifications | GRCF-S | 2010-11-11 | GRCF | SA |  | IMP | Approved by AEMO on 11/07/11; effective date 1/08/11.
Retail Gas | IN010/11 |  | Specification Pack Usage Guideline v5.2 | GRCF-S | 2011-05-13 | GRCF | SA |  | IMP | Approved by AEMO on 11/07/11; effective date 1/08/11.
Retail Gas | IN025/11 |  | Rationalise the GRCF's that operate in Vic, Qld and SA | GRCF-V GRCF-Q GRCF-S | 2011-09-20 | GRCF | VIC & QLD & SA |  | IMP | For discussion at October GRCF meeting
Retail Gas | IN014/11 |  | non-DTS Transfers: system change for validation of contractual access to transfer customers in non-DTS | GRCF-V | 2011-06-01 | GRCF | VIC | System Changes | IMP | SEP 2011 Update - IIR closed on 7 Sept
Retail Gas | IN003/11 |  | non-DTS UAFG: change to provide the UAFG rate to AEMO in order to complete UAFG in non-DTS areas | GRCF-V | 2011-02-01 | GRCF | VIC | Nil | IMP | SEP 2011 Update - IIR closed on 7 Sept
Retail Gas | IN021/10 |  | Objection Process Failure – transportation agreements | GRCF - N&A | 2010-08-24 | GRCF | NSW | Potentially changes to the GRMBS | WD | To be included in the B2B project
Retail Gas | IN046/10 |  | Amendments to COU move-in provisions in the Procedures | GRCF - N&A | 2010-12-14 | GRCF | NSW |  | IMP | Included in version 6 of the Procedures, with an effective date of 16.6.2011
Retail Gas | IN004/11 |  | Introducing Self Contracting Users in QLD | GRCF-Q | 2011-02-16 | GRCF | QLD |  | IMP | Approved by AEMO on 16/06/11; awaiting implementation 3 Nov 2011 (v5.0 of RMP-Q).
Retail Gas | IN017/11 |  | Removal of cumulative imbalance monitoring process for non-STTM wthdrawal zones | GRCF-Q | 2011-07-13 | GRCF | QLD |  | IMP | Awaiting implementation on 3 Nov 2011 (v5.0 of RMP-Q)
Retail Gas | IN018/11 |  | Amements to the RMP-Q for the redistribution of the PCF | GRCF-Q | 2011-07-13 | GRCF | QLD |  | IMP | Awaiting implementation on 3 Nov 2011 (v5.0 of RMP-Q)
Retail Gas | IN027/10 |  | Provision of STTM distribution system allocation (DSA) - QLD | GRCF-Q | 2010-09-24 | GRCF | QLD |  | IMP | Updated paper circulated to GRCF-Q on 9 Nov. GRCF-Q deemed agreement on 19 Nov (i.e. no objections). IIR raised 22 Mar - refer to IN048/10
Retail Gas | IN030/10 |  | STTM – Balancing under STTM | GRCF-Q | 2010-10-19 | GRCF | QLD |  | IMP | Discussed at GRCF-Q meeting on 27 Oct 2010. IIR raised 22 Mar - refer to IN048/10.
Retail Gas | IN043/10 |  | Provision of update extracts for interval meters | GRCF-Q | 2010-11-29 | GRCF | QLD |  | IMP | To be raised at GRCF-Q meeting on 8 December 2010. IIR raised 22 Mar - see IN048/10.
Retail Gas | IN044/10 |  | Estimation methodology for interval meters | GRCF-Q | 2010-11-29 | GRCF | QLD |  | IMP | GRCF-Q agreed to proceed with Option 2 at meeting on 19 January 2011. IIR raised 22 Mar - see IN048/10
Retail Gas | IN048/10 |  | Consolidated STTM changes - QLD. Incorporates IN026/10, IN027/10, IN030/10, IN043/10 and IN044/10. | GRCF-Q | 2010-12-29 | GRCF | QLD |  | IMP | AEMO approved changes 11 May. Awaiting implementation on 1 Dec.
Retail Gas | IN026/10 |  | Timing of data provision under STTM-Q | GRCF-Q | 2010-09-24 | GRCF | QLD |  | IMP | Timelines agreed at 27 Oct meeting. IIR raised 22 Mar - refer to IN048/10.
Retail Gas | IN023/11 |  | Cumulative imbalance adjustment for the October 2010 Revision Settlement |  | 2011-09-15 | GRCF | QLD | Documentation only | IMP | Changes approved by the GRCF-Q via circular resolution
Retail Gas | IN028/11 |  | B2B Contact List | GRCF-V GRCF-Q GRCF-S GRCF-N&A | 2011-11-18 | GRCF | VIC QLD SA NSW/ACT | N/A | IMP | Approved and implemented
Retail Gas | IN015/11 |  | Inclusion of postcodes in the “discovery address” | GRCF-N&A | 2011-06-14 | GRCF | NSW/ACT | N/A | IMP | included in Version 7 of the Procedures, with an effective date of 26 September 2011
Retail Gas | IN002/12 |  | Investigate solution for RAB issues in the ACT-Canberra network section |  | 2012-01-01 | GRCF | NSW/ACT |  | WD | Closed as already covered under IN020/10 paper
Retail Gas | IN029/11 |  | Crossed Meters | GRCF - N&A | 2011-12-13 | GRCF | NSW/ACT |  | WD | Discussed in 14 Feb 2012 workshop after GRCF and issues were found to be not linked to crossed meters.
Retail Gas | IN030/11 |  | Error Correction Transaction | GRCF - N&A | 2011-12-13 | GRCF | NSW/ACT |  | WD | Discussed at 14 Feb 2012 GRCF and issues were found to be immaterial.
Retail Gas | IN003/12 |  | NECF – provision of customer privacy information to Distribution businesses | GRCF | 2012-01-09 | GRCF | VIC QLD SA |  | WD | MAR 2012 Update - Discussed at the March GRCF. Rick Abott advised that this now a background issue that Envestra were looking into and requested that this issue be withdrawn. FEB 2012 Update - On agenda for discussion at GRCF in Feb 2012
Retail Gas | IN001/12 |  | Delivery of DPI full Listings | GRCF - N&A | 2012-01-01 | GRCF | NSW/ACT | N/A | IMP | Included in ver 8 of the RMP-N&A, to be effective 28 March 2012
Retail Gas | IN010/12 |  | Update the introduction section of the RMP (SA) so that SCU are removed from the Spec Pack obligation currently place on a “prescribed person”. This will make the RMP consistent with Vic and Qld for SCUs | GRCF | 2012-02-27 | GRCF | SA |  | WD | APR 2012 Update - Duplicated with IN012/12 therefore GRCF agreed to withdraw this GMI MAR 12 Update - Discussed at GRCF. Similar to a NSW issue with a formal GMI to follow.
Retail Gas | IN019/11 |  | Transfer Validation | RBPWG | 2011-08-11 | GRCF | VIC QLD | CATS System Change | IMP | Mid MAR 2012 - Effective date published as 17th Apr 12 MAR 2012 Update - Publication of effective date expected in mid-March. DEC 2011 Update - IIR closed. AEMO approved for a Build 30 implementation date as the effective date
Retail Gas | IN016/10 |  | COC Change to 8 Digits | GRCF-V | 2010-08-04 | GRCF | VIC | Schema Change. Moderate systems changes for DBs, RB and AEMO. | IMP | AEMO approved change. Implementation date: 30 July 2012
Retail Gas | IN007/11 |  | Further ESV-related GIP Changes PLN | GRCF-V | 2011-02-22 | GRCF | VIC | Schema Change. Moderate systems changes for DBs, RB and AEMO. | IMP | AEMO approved change. Implementation date: 30 July 2012
Retail Gas | IN027/11 |  | Customer Classification | RBPWG | 2011-10-18 | GRCF | VIC QLD SA | Schema Change. Moderate systems changes for DBs, RB and AEMO. | IMP | AEMO approved change. Implementation date: 30 July 2012
Retail Gas | IN011/12 |  | NECF - Residual changes to align systems / schema with documentation | GRCF | 2012-02-29 | GRCF | VIC QLD SA | Nil | IMP | AEMO approved change.
Retail Gas | IN013/12 |  | Add the words "all retailers" to relevant sections of RMP (Chapter 7) and the Wholesale market distribution UAFG procedures (Vic) as per the section 4 (Recommendation) of the DUAFG wash up paper. | GRCF | 2012-03-27 | GRCF | VIC | Nil | IMP | ARP 2012 - First raised for discussion. May 2012 Update - AEMO to undertake work internally on this to develop a GMI. End of May- PPC raised and presented to GRCF on 5 Jun. Target effective date 1 Aug 2012. IIR closed 13 July 2012 JUL 2012 Update - this is awaiting AEMO approval
Retail Gas | IN020/11 |  | Retail Gas Market Systems Consolidation Plan workshops | All | 2011-09-01 | GRCF | VIC QLD SA NSW/ACT |  | IMP | MAR 2012 Update - to be progressed through the RBPWG. May 2012 Update - Prioritised by RBPWG. On the agenda for Q3 2012.
Retail Gas | IN021/11 |  | Net Industry Value | All | 2011-09-01 | GRCF | VIC QLD SA NSW/ACT |  | IMP | For discussion at September GRCF meetings
Retail Gas | IN010/10 |  | Proposed Process to rectify incorrect current user details in the delivery point registry | GRCF-N&A | 2010-03-16 | GRCF | NSW/ACT |  | WD | Covered by DPI Reconciliation IN028/12
Retail Gas | IN022/10 |  | COU Reconciliation Issues | GRCF - N&A |  | GRCF | NSW/ACT |  | WD | Covered by DPI Reconciliation IN028/12
Retail Gas | IN024/11 |  | Meter Reads for Disconnected Delivery Points | GRCF- N&A | 2011-09-13 | GRCF | NSW/ACT |  | WD | Moved to B2B Project
Retail Gas | IN025/11 |  | Alternative to estimated read if special read is requested and there is no access | GRCF- N&A | 2011-10-05 | GRCF | NSW/ACT |  | WD | Moved to B2B Project
Retail Gas | IN012/12 |  | Market Communications - Provide ability for AEMO to exempt Self Contracting Users, from communication with AEMO systems, in unique situations where it is deemed not practicle for SCUs to implement significant IT changes | GRCF - N&A | 2012-03-01 | GRCF | NSW/ACT |  | IMP | AEMO decision for 3 September release.
Retail Gas | IN020/12 |  | Consolidation of version 8 and version 9 of Procedures to allow for separate implementation of NECF in NSW and ACT | GRCF-NA | 2012-06-19 | GRCF | NSW/ACT | Nil | IMP | AEMO decision for 3 September release.
Retail Gas | IN021/12 |  | Changes to the ICD to reflect NECF related changes as well as updates to include the objection codes. Alignment of the operation of the ICD clause to match Vic and Qld Procedures. | GRCF-NA | 2012-06-19 | GRCF | NSW/ACT | Possible system testing for participants using these transactions | IMP | AEMO decision for 3 September release.
Retail Gas | IN019/12 |  | Obligation for AEMO to publish the Heating Zone / postcode mapping table | GRCF | 2012-06-29 | GRCF | QLD | Nil | IMP | Implemented in June 2012
Retail Gas | IN009/12 |  | Update the Mapping of heating value zone to custody transfer meter in the QLD Retail gas market table to remove Hvid 106 and 110. This change is targeted for 2nd Apr 2012 | GRCF | 2012-02-27 | GRCF | QLD | Likely system impacts for RBs, DBs and AEMO | IMP | AUG 2012 Update - Qld RBs revised the implementation date 30 Sept 2012. SEPT 2012 Update - AGL have advised that they have completed. Awaiting APG and Origin confirmation 15 OCT 2012 Update - All retailers have removed dependancies on zones, APA have ceased providing values on these zones.
Retail Gas | IN004/09 |  | Inconsistencies in Special Read Process regarding no access and when to send an estimated meter read (AGL's Q1&2) | GRCF-V | 2009-05-12 | GRCF | VIC | Possible system impacts for DBs | WD | FEB 2012 Update - On priority list, to be progressed further in coming months by RBPWG JUL 2012 Update - Prioritised by RBPWG. On the AUG 2012 Agenda. OCT 2012 - AGL is proposing to withdraw this GMI. Awaining AGL formal advice to withdraw this GMI then circulate to GRCF for endoresment OCT 2012 - circulated AGL withdrawal proposal with no objections received from industry
Retail Gas | IN008/10 |  | Crossed Meter Process | RBPWG | 2010-03-31 | GRCF | SA | Nil | IMP | AEMO approved change.
Retail Gas | IN040/10 |  | Changes to the Retail Market Procedures (SA) in light of National Energy Customer Framework | GRCF-S | 2010-11-08 | GRCF | SA |  | IMP | AEMO approved change.
Retail Gas | IN011/11 |  | Correct to MIRN check-sum in Appendix 3 | GRCF-S | 2011-05-13 | GRCF | SA | Nil | IMP | AEMO approved change.
Retail Gas | IN013/11 |  | non-DTS Grampians: change to allow Grampians data into the AEMO MR | GRCF-V | 2011-06-01 | GRCF | VIC | New networkID for AEMO system | IMP | AEMO approved change. Implementation date: 1 Feb 2013
Retail Gas | IN006/12 |  | South Australian RoLR Procedures | GRCF | 2012-01-31 | GRCF | SA | Manual work arounds | IMP | AEMO approved change.The provision to the T900 files will be delivered as a part of Build 31 (Oct 2012).
Retail Gas | IN008/12 |  | Spec pack references Victoria incorrectly with respect to Tariff D network Duos billing file format | GRCF | 2012-02-16 | GRCF | SA | Nil | IMP | AEMO approved change.
Retail Gas | IN018/12 |  | Prospective CATS transfer review | GRCF | 2012-06-29 | GRCF | VIC & QLD | Nil | IMP | AUG 2012 Update - RBPWG agreed to raise as a PPC. SEPT 2012 Update - Awaiting AEMO decision. OCT 2012 update - AEMO decision 1 feb 2013 implementation
Retail Gas | IN033/12 |  | Grampians Net System Load Methodology Procedure | GRCF | 2012-10-31 | GRCF | VIC | AEMO has IT system impacts but coverred under maintenance rather than IT release | IMP | PPC to be raised at the GRCF meeting on 13 November 2012 IIR raised on 20/12/2012 - close on 9/01/13 Procedure published on 17/01/13
Retail Gas | IN036/12 |  | Reconciliation of meter reading frequency for large sites in GRMBS | GRCF-NA | 2012-12-11 | GRCF | NSW/ACT |  | WD | Completed. Superceded by activations workshop and IN001/13
Retail Gas | IN029/12 |  | Prescribe Pilot program BAU process into the GIP | RBPWG | 2012-07-19 | GRCF | VIC |  | IMP | AEMO has approved this change, commencement date: 1 March 2013
Retail Gas | IN034/12 |  | Relaxation of DSA Delivery Requirements | GRCF-NA | 2012-12-11 | GRCF | NSW/ACT | Nil | IMP | IIR closed on 11 Feb. Approved by AEMO. Implemented on 25 March with version 11 RMP.
Retail Gas | IN016/11 |  | Next Scheduled Read Date | GRCF-NA | 2011-07-12 | GRCF | NSW/ACT | Small systems change for NWO | IMP | Approved by AEMO board. Pending agreement on implementation dates. GRCF-NA support a later implementation for Envestra. Implemented with version 11 of the RMP on 25 March.
Retail Gas | IN028/10 |  | Harmonisation of NSW ACT B2B | GRCF-NA |  | GRCF | NSW/ACT | Users system, network operators systems, B2B Hub and GRMBS | WD | AEMO provided a board communique noting that was advising that AEMO cease work on this project in the absence of a clear et benefit or policy directive.
Retail Gas | IN027/12 |  | Gas Leaks and Emergency Protocol | GRCF | 2012-07-19 | GRCF | VIC QLD SA | Nil | WD | FEB 2013 - PPC is out for consultation, closed on 13 March 2013. IIR Release date extended to 3 June to consult on NERR obligations MAY 2013 -After request from SP AusNet on 30/05/13, AEMO has withdrawn this consultation 31/05/2013
Retail Gas | IN002/13 |  | Consolidating the Gas Retail Consultative Forums | GRCF GRCF-NA | 2013-03-05 | GRCF | VIC QLD SA NSW/ACT | N/A | IMP | MAY 2013 - Final ToRs released. Inaugural consolidated GRCF to occur on 2 July 2013
Retail Gas | IN038/10 |  | Changes to the Retail Market Procedures (NSW/ACT) in light of National Energy Customer Framework | GRCF | 2010-11-08 | GRCF | NSW/ACT |  | IMP | AEMO approved change. AEMO has released a verion 11.1 of the RMP to be effective on 1 July 2013.
Retail Gas | IN015/12 |  | Provide ability for AEMO to exempt Self Contracting Users, from communication with AEMO systems, in unique situations where it is deemed not practicle for SCUs to implement significant IT changes | GRCF | 2012-04-16 | GRCF | SA | Nil | WD | AUG 2013 - AEMO will be removing this item from the change register at it is of the opinion that the proposal will not provide any value in its current form
Retail Gas | IN008/13 |  | Standardise Connectivity Testing and System Certification process across all jurisdictions and include a requirement for 10 working days. Issue arising from WA new entrant. |  | 2013-05-01 | GRCF | SA, WA |  | IMP | AUG 2013 - IIR released on 12 Aug with proposed implementation date of 1 October
Retail Gas | IN013/13 |  | Amended RMPs for the delivery timeframe for UETW file current defined as 4hr should be 5hr as per the SLA |  | 2013-07-08 | GRCF | SA |  | IMP | AUG 2013 - This is a typographical error that will be fixed with the release of the SA RMP on 1 October. AEMO will attach a memorandum explaining the change in more detail when the Procedures are published.
Retail Gas | IN006/11 |  | Updates to FRC Hub Operational Terms and Conditions |  | 2011-05-13 | GRCF | VIC, QLD, SA |  | IMP | AUG 2013 - IIR has closed and AEMO will make decision before end of Aug with a proposed implementation date of 1 October 2013.
Retail Gas | IN004/13 |  | Automatic population of MDA and RoLR fields in GRMBS |  | 2012-12-11 | GRCF | NSW/ACT |  | IMP | Mid OCT - CR174 implemented on 30 Aug 2013 AUG 2013 - The work associated with the change request raised is due to be completed by CGI by the end of August 2013
Retail Gas | IN015/13 |  | Residual RMP and Spec Pack changes (eg: new event code) for SA RoLR |  | 2013-07-08 | GRCF | SA | Yes | IMP | Mid Dec 2013 - AEMO approved RMP changes on 27 Nov. Awaiting implemention on 1 Jan 2014 Early Nov 2013 - IIR response close 14 Nov. Mid OCT 2013 - IIR issued 15 Oct. Responses close 14 Nov OCT 2013 - PPC released on 10 Sept and responses due on 4 Oct AUG 2013 - GMI released on 30 July. Consultation close 6 Sept. Proposed effective date of 1 January 2014
Retail Gas | IN026/12 |  | SA RoLR (system automation) |  | 2012-07-25 | GRCF | SA | Yes | IMP | Mid Dec 2013 - Awaiting implemention on 1 Jan 2014 Early Nov 2013 update - Awaiting implamention on 1 Jan 2014. FEB 2013 - PPC is out for consultation, closing on 4 April 2013. APR 2013 - Notice of extension sent 8/04; PPC Revised, subs close 26 April 2013 MAY2013 - IIR Released 13/05, subs close 12/06 JUL 2013 - AEMO approved 9/07 changes to take effect 1/01/14
Retail Gas | IN003/13 |  | Interface Control Document Changes for SA RoLR |  |  | GRCF | SA | Yes | IMP | Mid Dec 2013 - Awaiting implemention on 1 Jan 2014 Early Nov 2013 update - Awaiting implamention on 1 Jan 2014. Straight to PPC stage, released 19 March 2013, subs close 4 Apr 2013. IIR release to align with IN026-12 APR 2013 - Notice of extension sent 8/04; PPC Revised, subs close 26 Apr 2013 MAY2013 - IIR Released 13/05, subs close 12/06 JUL 2013 - AEMO approved 9/7 and changes to take effect 1/1/14
Retail Gas | IN012/13 |  | Remove UDW files from RMP and Spec Pack as data no longer required in SA since start of STTM (Oct 2010). |  | 2013-07-08 | GRCF | SA |  | IMP | Mid Dec 2013 - AEMO approved RMP changes on 6 Dec. Awaiting implemention on 1 Jan 2014 Early Nov 2013 - IIR issued on 8 Nov and submission close 29 Nov. Mid OCT 2013 - PPC issued 10 Oct. Responses close 25 Oct Oct 2013 - GMI released on 24 Sept. Responses are due on 1 Oct. PPC is planned to be release on 7 Oct. AUG 2013 - To be incorporated in consultation to remove Redundant Provisions (IN004/12)
Retail Gas | IN014/13 |  | Remove the monthly estimated reconciliation report provided to Users from RMP as data is already generated on a daily basis and sent to the Users superceding the need for the monthly report. |  | 2013-07-08 | GRCF | NSW/ACT |  | IMP | See Status comments for IN012/13 AUG 2013 - To be incorporated in consultation to remove Redundant Provisions (IN004/12)
Retail Gas | IN016/13 |  | For the Vic RMPs there is no equivalent SA clause 412 (a) for the Distributor to update their database when AEMO notifies them of the MIRNs that AEMO has updated in its database as a result of a RoLR. |  | 2013-07-08 | GRCF | VIC |  | IMP | See Status comments for IN012/13 AUG 2013 Update - Candidate to include a Procedure Change pack similar to Redundant Provisions
Retail Gas | IN018/13 |  | Amendment of monthly meter data agent (MDA) report |  | 2013-07-23 | GRCF | NSW/ACT |  | IMP | See Status comments for IN012/13 AUG 2013 - AEMO released a GMI on this issue that will be consulted upon with the same timelines as the Redundant provision consultation
Retail Gas | IN004/12 |  | Redundant Provisions |  | 2012-01-20 | GRCF | VIC, QLD, SA, NSW/ACT |  | IMP | See Status comments for IN012/13 MAY 2013 - AEMO has provided a paper with outcomes from the workshop in Feb and will begin work on a detailed GMI
Retail Gas | IN023/13 |  | The Declared Host definition in the NGR has been removed. The definition therefore need to be add to the RMP |  | 2013-10-11 | GRCF | VIC |  | IMP | Early Nov 2013 - GRCF agreed to include this proposed RMP change in work package 2. Oct 2013 - AEMO identifed the missing defination in Oct
Retail Gas | IN022/11 |  | There are inconsistencies in the GIP and Spec Pack in terms of defining the aseXML transaction priority. One example is PBP3 System Spec section 2.6.3 (page 14) list the certain transactions as low, yet PBP3 Interface Definitions lists them as medium |  | 2011-09-01 | GRCF | VIC, QLD, SA |  | IMP | See Status comments for IN012/13 AUG 2013 Update - Candidate to include a Procedure Change pack similar to Redundant Provisions MAR 2012 Update - to be progressed through the RBPWG. MAY 2012 Update - Prioritised by RBPWG. On the agenda for Q3 2012.
Retail Gas | IN031/12 |  | RMP Changes (Package #1 - 1st April 2014) |  | 2012-06-12 | GRCF | VIC, QLD | Yes | IMP | Early Mar 2014 update: Implementation on track for 1 Apr 2014 Mid Jan 2014 update - AEMO has approved change. Awaiting implemention on 1 Apr 2014. Mid Dec 2013 Update – This issue was included in the minor GIP Changes that were include with the RMP change (Package 2) (IN004/12 – Redundant Provision) that has an effective date 1 Jan 2014. AEMO approved the changes on 6 Dec 2013. Consultation revealed that this wasn’t a minor GIP for some Participants. AEMO decided to make the effective date for this change 1 Apr 2014 instead. Early Nov 2013 - This was a item raised at the June 2012 RBPWG. AEMO to review whether this remains an issue and will update the GRCF in Dec 2013.
Retail Gas | IN002/14 |  | The Specification Pack (FRC B2B System Interface Definitions – Appendix F section 1 (Customer and Site Details (Monthly update) (T900)) doesn’t stipulate that the T900 must be in CSV format, yet the other files mention CSV. This oversight is minor procedure change and could be considered with other procedure changes that are targeted for implementation in July 2014. | AEMO | 2014-02-12 | GRCF | SA | Spec Pack | IMP | June 2014 update: AEMO decision published 6th June. Change to take effect 1 July 2014 May 2014 update: IIR published on 2 May, submissions to IIR close on 23 May. Proposed effective date of 1 July 2014 remains unchanged. Early Mar 2014 update: Part of RMP Changes Package #2 2014. Draft PPC due to be issued for GRCF review in mid March
Retail Gas | IN003/14 |  | Collation of NSW/ACT process flows and steps developed, as part of GRMBS Transactions Review, in a NSW/ACT Gas Interface Protocol document | AEMO | 2014-02-12 | GRCF | NSW/ACT |  | IMP | See Status comments for IN002/14.
Retail Gas | IN004/14 |  | Participant Build Pack 2 – Usage Guide (section 3.1 – UML Activity Digrams) prescribes the Process Flow diagram standard that is to apply for PBP2 Interface Definition document and the PBP3 B2B Interface Definition document. The diagram standard that is currently used is UML Activity Diagram which is part of the Enterprise Architect software. Now that industry has adopted a new diagram stencil, the UML Activity Diagram standard referenced in section 3.1 should be deleted. | AGL | 2014-02-12 | GRCF | VIC/QLD | GIP - PBP2 Usage Guide | IMP | See Status comments for IN002/14.
Retail Gas | IN005/14 |  | Proposed changes to Retail Market Procedures VIC documentation to rectify a incorrect reference. Currently, the definition to Customer Characterisation makes reference to the Department of Infrastructure which doesn’t exist. The current department is Department of Transport, Planning and Local Infrastructure. The RMP proposal is to simply replace one with the other. |  | 2014-02-20 | GRCF | VIC |  | IMP | See Status comments for IN002/14.
Retail Gas | IN008/14 |  | Rectify typographical error in Retail Market Procedures NSW & ACT clause 11.5(3), where 'relevant network operator' is to be replaced with 'objecting participant' to be consistent with the clause intent. |  | 2014-03-07 | GRCF | NSW/ACT |  | IMP | See Status comments for IN002/14.
Retail Gas | IN017/13 |  | Amended relevant Service Order sections of the GIP, Specification Pack and Information Pack consistent with the outcomes of the Service Order Road Map review. | Danny McGowan | 2013-04-06 | GRCF | VIC,QLD and SA |  | IMP | See Status comments for IN002/14.
Retail Gas | IN039/12 |  | There is no industry agreed process for managing MHAs/MRTs. | Steve Clinch | 2012-11-26 | GRCF | VIC, QLD, SA | N/A | IMP | See Status comments for IN002/14.
Retail Gas | IN010/14 |  | Implementation of an automated process to deliver the monthly bulk delivery point information to the NSW-ACT Retail Gas Market participants via FTP. Potential Compliance breaches are mitigated by implementation. | GRCF | 2014-05-20 | GRCF | NSW/ACT | Yes - GRMBS | IMP | July 2014 : Implementation completed and DPR Extracts provided through FTP folders on July 1. June 2014: Implementation on track for June 26. CGI working with particpants' IT contacts to conduct testing. No regulatory changes required, only needs a technological change to enable delivery of DPR Extracts using FTP rather than the current method of emails.
Retail Gas | IN001/13 |  | Obligation to raise deactivation and change of standing data transaction in GRMBS | GRCF | 2013-01-15 | GRCF | NSW/ACT | Yes | WD | Aug 2014 update: GRCF has determined that this issue can be withdrawn as this functionality would be superseded by NARGP outcomes. Jul 2014 update: On hold pending outcomes of NARGP CBA. For discussion at 19 Aug GRCF, post AEMO Board decision. Oct 2013: AEMO has developed a GMI that suggests creating a Procedural obligation to raise these transactions.
Retail Gas | IN005/13 |  | Review of Error Codes and Objection Process for Activations and Deactivations | GRCF | 2013-03-21 | GRCF | NSW/ACT | TBC | WD | Aug 2014 update: GRCF has determined that this issue can be withdrawn as this functionality would be superseded by NARGP outcomes. Jul 2014 update: On hold pending outcomes of NARGP CBA. For discussion at 19 Aug GRCF, post AEMO Board decision. Oct 2013: AEMO has developed draft process flows and a GMI to review the objection window for these transactions.
Retail Gas | IN019/14 |  | AEMO operational efficiency initiative: Introduction of a latest meter read report for NSW/ACT Network Operators to achieve a reduction in large number of dovetal errors. This new report would assist in - Reduction in delays/rejections in processing transfer requests - Reduction in delay/rejections in processing requests for deactivation. | GRCF | 2014-08-19 | GRCF | NSW/ACT | Yes | IMP | Sept 2014: Report implemented for NSW/ACT Network Operators on Sept 1.. Aug 2014: Added to issues/change register. Impelementation expected in early September 2014.
Retail Gas | IN022/13 |  | In the Service Order Response transaction that the Distributor sends to the Retailer include "MIRN Status" and "Meter Status" fields in the transaction. | RBPWG | 2013-10-11 | GRCF | VIC and SA | Possible system impacts for RBs and DBs | WD | Sep 2014 update - RBPWG agreed these changes are no longer required and should be withdrawn. A new GMI is to be created to conduct a mapping exercise to determine whether any are worth pursing. Aug 2014 - RBPWG workshop GMI on 28th July. Awaiting feedback on GMI and from proponents who proposed some of the changes which is due 15th Aug. Oct 2013 - This issue was first raised at the 11 Oct 2013 Service Order review workshop and is yet to be prioritised by the GRCF.
Retail Gas | IN024/13 |  | a). Partcipant systems are currently configured to accept the following Job Enquiry Codes (JEC) - MBO (Meter Pre-Pay Broken), MFXA (Meter Fix – Fault Rectification) and MRG (Meter refix and re-light). These codes are not used in VIC, QLD and SA. The RMPs reflect that these codes not used. Retailers are to reconfigure their systems so they cannot generate these codes and Distributors to reconfigure their systems so they reject these codes should they receive such transaction with the said codes from a Retailer. b). In VIC the MAP( Meter Alter Position), MCH (Meter Change), UMS (Upgrade Meter Size Request) Service Order needs need to a the ability for the Retailer to enter a COC number and for this information to be received by the Distributor. Partcipants systems are not currently configured to accomendate Certificate of Compliance (CoCs) and Plumbers License Number (PLN). Work arounds are currently in place. c ) Add Meter number to Service Order Request transaction and for AML's the meter number is required. d). A new JECs Service Order specifically for (i) Crossed Meter investigations to be developed. Proposed code could be CMI, and (ii) Pressure Correction Factor changes - Proposed code PCH. | RBPWG | 2013-10-11 | GRCF | VIC,QLD and SA |  | WD | See status comments for IN022/13 Oct 2013 - This issue was first raised at the 11 Oct 2013 Service Order review workshop and is yet to be prioritised by the GRCF.
Retail Gas | IN030/12 |  | Review of Error Correction Process | GRCF | 2012-08-14 | GRCF | NSW/ACT |  | WD | Oct 2014 update: PRWG disucssed this matter in 10 Oct workshop. Moving to Completed-Withdrawn tab as this will be completed through NARGP program of work. Sept 2014 update: To be discussed in PRWG in September workshops. Aug 2014 update: GRCF has determined that this issue can be transfered to NARGP PRWG as this functionality would be required for NARGP outcomes. Jul 2014 update: On hold pending outcomes of NARGP CBA. For discussion at 19 Aug GRCF, post AEMO Board decision. Oct 2013: AEMO developed a paper that identifies possible faults with the error correction process that should be amended as a result of the transaction review
Retail Gas | IN026/13 |  | NSW Gas error correction pilot program procedure changes | GRCF | 2013-11-06 | GRCF | NSW/ACT |  | WD | Oct 2014 update: PRWG disucssed this matter in 10 Oct workshop. Moving to Completed-Withdrawn tab as this will be completed through NARGP program of work. Sept 2014 update: To be discussed in PRWG in September workshops. Aug 2014 update: GRCF has determined that this issue can be transfered to NARGP PRWG as this functionality would be required for NARGP outcomes. Jul 2014 update: On hold pending outcomes of NARGP CBA. For discussion at 19 Aug GRCF, post AEMO Board decision. Nov 2013 - Lumo presented this issue at the GRCF on 6/11/13. GRCF agreed to extend the pilot program till such a time that Procedure changes can be drafted for consultation.
Retail Gas | IN001/14 |  | Proposed changes to Retail Market Procedures NSW-ACT documentation to rectify flaw in drafting of error correction procedure. | GRCF | 2014-01-21 | GRCF | NSW/ACT |  | WD | Oct 2014 update: PRWG disucssed this matter in 10 Oct workshop. Moving to Completed-Withdrawn tab as this will be completed through NARGP program of work. Sept 2014 update: To be discussed in PRWG in September workshops. Aug 2014 update: GRCF has determined that this issue can be transfered to NARGP PRWG as this functionality would be required for NARGP outcomes. Jul 2014 update: On hold pending outcomes of NARGP CBA. For discussion at 19 Aug GRCF, post AEMO Board decision. Mar 2014 update - Discussed in Feb 2014 GRCF. Participant comments required for GMI. Jan 2014 update - Added to issues/change register and yet to be prioritised.
Retail Gas | IN025/13 | Removal of Obligation to Publish SA Profiling Guideline | According to clause 209 in the RMP-S, AEMO must publish a guideline that set out the principles on which the profiles referred to in clause 209(1) are based. The GRCF needs to decide whether guideline this required and if a change to this clause is required. | AEMO | 2013-11-12 | GRCF |  | Clause 209 | IMP | Sep 2014 update - IIR published on 29 August 2014, submissions close on 19 September 2014. Aug 2014 update - IIR to be issued by 29 August 2014. Jul 2014 update - AEMO to present final drafting changes and response to particpant questions at July GRCF meeting. June 2014 update - see status update for IN028/13. May 2014 update: Notice of Time Extension published on 5 May. AEMO is targeting to publish the IIR by 29 August 2014. Early Mar 2014 update: Part of RMP Changes Package #2 2014. Draft PPC due to be issued for GRCF review in mid March.
Retail Gas | IN009/14 | SA Disconnection by User | Proposal to remove the Retailer disconnections provision from the RMP (SA) | Envestra | 2014-03-18 | GRCF |  | Clause 111 | IMP | Sep 2014 update - IIR published on 29 August 2014, submissions close on 19 September 2014. Aug 2014 update - IIR to be issued by 29 August 2014.Aug 2014 Jul 2014 update - AEMO to present final drafting changes and response to particpant questions at July GRCF meeting. June 2014 update - see status update for IN028/13. May 2014 update: Notice of Time Extension published on 5 May. AEMO is targeting to publish the IIR by 29 August 2014. Early Mar 2014 update: Part of RMP Changes Package #2 2014. Draft PPC due to be issued for GRCF review in mid March.
Retail Gas | IN028/13 | Harmonisation of Audit Provisions | The proposed market audit changes proposed in IN004/12 required further AEMO internally and was removed from that consultation. These market audit changes will be included as a seperate program of work in 2014. | AEMO | 2013-11-23 | GRCF | All |  | IMP | Sep 2014 update - IIR published on 29 August 2014, submissions close on 19 September 2014. Aug 2014 update - IIR to be issued by 29 August 2014. Jul 2014 update - AEMO to present final drafting changes and response to particpant questions at July GRCF meeting. Jun 2014 update - notice of time extension for IIR publish on 6th May. Now expected by 29th Aug. AEMO to provide update at June meeting. May 2014 update: Notice of Time Extension published on 5 May. AEMO is targeting to publish the IIR by 29 August 2014. Early Mar 2014 update: Draft PPC due to be issued for GRCF review in mid March.
Retail Gas | IN011/14 | NSW/ACT Procedures audit related updates and other minor amendments | Align clause 33.15(2) with the intent of the STTM 9 month revision business process. Additionally correct minor typographical errors in the Procedures. | AEMO | 2014-05-28 | GRCF | NSW/ACT |  | IMP | Sept 2014: IIR published 12 Aug. Responses received by Sept 1. Effective date to coincide with IN028/13, likely ito be 3 November. Aug 2014: PPC response due on 5 aug. IIR to be published. Jul 2014: PPC to be published on 15 Jul. Jun 2014: GMI disucssed in June GRCF.
Retail Gas | IN009/13 | Review of GRMBS Transactions | Review of GRMBS Transactions: development of GRMBS process flows and steps for high volume transactions | AEMO | 2013-05-21 | GRCF | NSW/ACT | No | WD | Feb 2015 update - The GRCF agreed at the Jan prioritisation session that this issue had been superseded by the NARGP and can be withdrawn. Jan 2015 update: AEMO to conduct a final review and publish finalised process flows and steps dependent on resource availability. Dec 2014 update: to be discussed at GRCF prioritisation session in Jan. Jul 2014 update - Provide to RBPWG for 28 July meeting for review. Mar 2014 Update: Next workshop 18 Mar - Error Corrections, Change of Standing Data and Objections.
Retail Gas | IN018/14 | QLD Audit finding | A recent QLD audit identified a incorrect RMP clause referred to in the AEMO Consumed Energy Scenario (QLD). This is a documentation only change | AEMO | 2014-08-11 | GRCF | QLD | TBA | IMP | Feb 2015 update: The GRCF agreed this issue can be withdrawn at the prioritisation session in Jan. Jan 2015 update: AEMO decision published on 23 Dec 2014. Changes effective from 19 Jan 2015. Dec 2014: submissions to IIR closed on 27/11/14. No objections received. AEMO decision to be published on 10/12/14. Sept 2014: AEMO is proposing to issue a GMI this month that targets a 1 Jan 2015 implmentation date. Move to the "in progress" tab Added to issues/change register and yet to be prioritised.
Retail Gas | IN006/13 |  | Harmonisation of full DPI listing format | Malcolm Hempel | 2013-03-21 | GRCF | NSW/ACT | TBC | WD | Jan 2015 Update -At the GRCF Prioritisation Session held 20th Jan, The GRCF agreed that this issue had been superseded by the NARGP and can be withdrawn Early Mar 2014: To be discussed for prioritisation in March GRCF meeting. Mid Jan 2014 - No change since early Nov 2013. Because to the requirement to consider Service Order technology changes, workshop to commence early Feb 2014 Mid Dec 2013 - No change since early Nov 2013. Because to the requirement to consider Service Order technology changes, workshop to commence early Feb 2014 Early Nov 2013 - The GRCF agreed that the GMI is in sufficentl detail to progress to the assessment phase. Agreed to bundle with other MIRN Discovery technology changes once the workshops have been completed. OCT 2013 - This issue is to be included in Gas Road Map (MIRN Discovery) AUG 2013 - Origin Energy to raise GMI incorporating industry feedback at September GRCF
Retail Gas | IN031/13 |  | RMP-NA Clause 16 silent on whether DPR Extracts for ‘deactivated’ DPIs are required to be sent to ‘inactive’ Users. Procedure change required to fix this discrepancy | AEMO | 2013-12-31 | GRCF | NSW/ACT | No | WD | Jan 2015 Update -At the GRCF Prioritisation Session held 20th Jan, The GRCF agreed that this can be withdrawn Early Mar 2014 update: Part of RMP Changes Package #2 2014. Draft PPC due to be issued for GRCF review in mid March
Retail Gas | IN010/13 |  | Review of NSW/ACT RoLR process | Aleks Smits | 2013-06-21 | GRCF | NSW/ACT | Nil | WD | Jan 2015 Update -At the GRCF Prioritisation Session held 20th Jan, The GRCF agreed that this issue had been superseded by the NARGP and can be withdrawn See IN024/12 Update. Mid Dec 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package Early Nov 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package OCT 2013 Update - GRCF recommend to group all RoLR issues / changes into the one Program of Work package AUG 2013 - Initial review of RoLR process has completed. Further end-to-end review and enhancement of processes may be required depending on industry requirements
Retail Gas | IN016/12 |  | Develop and implement a protocol for RoLR monthly customer information delivery in NSW/ACT based upon the MIBB T900 transaction | Aleks Smits |  | GRCF | NSW/ACT | Manual work arounds | WD | Jan 2015 Update -At the GRCF Prioritisation Session held 20th Jan, The GRCF agreed that this issue had been superseded by the NARGP and can be withdrawn See IN024/12 Update. Mid Dec 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package Early Nov 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package OCT 2013 Update - GRCF recommend to group all RoLR issues / changes into the one Program of Work package AUG 2013 - To be reviewed as a part of the end-to-end RoLR review in NSW-ACT (IN010/13) depending on industry requirements.
Retail Gas | IN028/12 |  | DPI Reconciliation |  | 2012-08-14 | GRCF | NSW/ACT | TBC | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, The GRCF noted this issue had been superseded by the NARGP and can be withdrawn. This issue is to be referred to NARGP-CF for consideration. Add to NARGP issue registers as item #38 Early Mar 2014 Update: No change since June 2013 - program of work on hold until at least May 2014 due to industry resource constraints. JUN 2013 - Snapshots issued to Participants and program of work on hold until at least May 2014 due to industry resource constraints.
Retail Gas | IN037/12 |  | Versioning consistency within aseXML | Andrew Screen | 2012-12-04 | GRCF | VIC, QLD, SA | Yes | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, The GRCF noted this issue can be withdrawn. Early March 2014: No further progress. Mid Dec 2013 update - The ITDF completed the reviewing the GMI. A consolidated list of responses was presented to the ITDF late April. The ITDF noted that none of the responses opposed optional and default versioning on schema and on that basis the ITDF endoresed the proposal. AEMO is following up with the ITDF and ASWG chairs in terms of what are the impacts of this outcome. Early Nov 2013 update - The ITDF completed the reviewing the GMI. A consolidated list of responses was presented to the ITDF late April. The ITDF noted that none of the responses opposed optional and default versioning on schema and on that basis the ITDF endoresed the proposal. AEMO is following up with the ITDF and ASWG chairs in terms of what are the impacts of this outcome. FEB 2013 - ITDF currently reviewing the GMI and providing a response regarding the impact of the change. Responses are due 28 March 2013. [note: this is also being progressed at the BMRG for electricity response]
Retail Gas | IN017/12 |  | Review the Crossed Meter Process with a view to establishing a process between Retailers and Network Operators that deals with the resolution of crossed meters more effectively. | Hillary Nguyen | 2012-05-15 | GRCF | NSW/ACT | TBC | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, The GRCF noted this issue had been superseded by the NARGP and can be withdrawn Early Mar 2014 Update - No change since Aug 2013. Other priorities have meant no further progress. AUG 2013 - Outcomes from August 2013 workshop will need to be reviewed and a GMI reraised depending on industry priority. Progressing through the GRCF.
Retail Gas | IN002/11 |  | DTS Interval Metering provisions in Victoria are currently reside in the NGR (part 19). The proposal is to move these to the RMPs. (see also IN019/13) |  | 2011-02-01 | GRCF | VIC | Nil | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this items can be withdrawn and merged with IN011/13 Early Mar 2014 - On Hold since Aug 2013. No longer a priority given IN0011/13 in progress. AUG 2013 - The Rule change will not be progressed and in its place AEMO will progress a RMP change to mitigate the regulator gap (see IN011/13)
Retail Gas | IN020/13 |  | Enhancements to existing MIBB reports INT 549 and IN554 regarding the timing of the reports | Dat Vuong | 2013-10-01 | GRCF | VIC QLD | Yes | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this items can be withdrawn Early Mar 2014 update - No changes since Oct 2013. Yet to be prioritised by the GRCF. Issue first raised in Oct 2013 GRCF.
Retail Gas | IN021/13 |  | Changes resulting from the National Occupational Licensing Scheme (NOLS) reform may have business and system implactions on Service Order B2B transactions should the current format of the Plumbers License Number (PLN) used in Victoria changed. | GRCF | 2013-10-01 | GRCF | VIC | Yes | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this items can be withdrawn Early Mar 2014 update - No changes since Oct 2013. Yet to be prioritised by the GRCF. Issue first raised in Oct 2013 GRCF.
Retail Gas | IN027/13 |  | Discussions at a Gas Road Map Service Order workshop revealed that the diagram 112 included a inter-process link to Meter Data Delivery. The scope of the Gas Road Map Service Order didn’t include a review other process flows. The group agreed not review of the Meter Data Delivery process but requested that when a program of work is undertake to look at Meter Data Delivery process, the scope of such a review included revisiting diagram 112 to ensure it depicts the process, particularly if any changes to the Meter Data Delivery emerge | Gas Road Map - Service Order working group | 2013-11-15 | GRCF |  |  | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this items can be withdrawn Early March 2014: On hold until a review of Meter Data Delivery process flow is undertaken which is yet to be planned. Mid Jan 2014 update - No changes since Nov 2013. Yet to be prioritised by the GRCF. Mid Dec 2013 update - Added to issues/change register on 12/11/13 and yet to be prioritised. Early Nov 2013 - Added to issues/change register on 12/11/13 and yet to be prioritised.
Retail Gas | IN007/14 | Site/Customer Data work program | DHS/Centerlink addressing standards to be considered as part of the Site/Customer Data scoping phase. |  | 2014-03-06 | GRCF | All |  | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, Lumo (the proponent) indicated that this issue can be withdrawn. Added to issues/change register and yet to be prioritised.
Retail Gas | IN020/14 | VIC Gas Meter Serial Numbers - MIBB report | Introduction of a new MIBB report for DBs to notify participants about the new meter serial number ranges as they become available. | EA | 2014-08-26 | GRCF | VIC | Yes | WD | Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, The GRCF noted this issue had been superseded by the NARGP and can be withdrawn Added to issues/change register and yet to be prioritised.
Retail Gas | IN029/13 | Unique Gas Meter Serial Numbers | According to some DBs the assigned number ranges for Gas Meter Numbers will run out in the near furture. |  | 2013-12-18 | GRCF | All |  | IMP | March 2015 Update - GRCF request the the RP group arrange testing of 7 number serial meters. Feb 2015 - Following impact assessment by participants, it was decided no further action required. The DB's will start using new number range when they exhaust existing numbers. Jan 2015 update: AEMO to discuss updated paper and next steps at GRCF meeting on 20 Jan 2015. Jun 2014 - Responsible Persons group proposal circulated to GRCF on 1 Jul. Discuss in 22 Jul GRCF. May 2014 - No update. Identified as priority project at Mar 2014 meeting. Early Mar 2014 update: Responsible Persons group met on Mar 4. Multinet to provide a proposal to AEMO by March end, which would then be tabled in Aprl GRCF meeting. Mid Jan 2014 update - Added to issues/change register on 18/12/13. Briefing paper prepared by Multinet was circulated to VIC DBs and AEMO. Feedback received from SP AusNet. Multinet and AEMO agreed that further analysis on the options is required and that the Responsible Persons (RP) working group are the SMEs best placed to develop options and a recommendation paper for GRCF endorsement. AEMO will convene the RP working group on 14th Feb with an aim of having a recomendation paper to the GRCF before the end of March 2014.
Retail Gas | IN025/14 | Update to MIRN Structure document (Qld) | Updates to the MIRN Structure (Qld) document to remove referances that the Distributor must assign separate MIRN ranges for internal meters and basic meters. | AEMO | 2014-11-28 | GRCF | Qld | No | IMP | Apr 2015 Update - Update doc published on AEMO website Mar 2015 Update - The GRCF agreed this wasnt duplicated as noted in the Jan 2015 update. AEMO will issue marked up changes to the document for considertion on 13th Mar. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF ran out of time to discuss this item. The GRCF noted this issue is a duplicate of IN007/13 and it can be withdrawn. Added to issues/change register and yet to be prioritised.
Retail Gas | IN022/14 | SCU Exception from maintaining connectivity with the GRMBS | Delta Electricity has proposed that SCU's in NSW/ACT are excempt from maintaining connectivity with the GRMBS | Frank Xing | 2014-10-13 | GRCF | NSW/ACT | No | WD | Apr 2015 Update - Delta has deregistered from the NSW.ACT retail market there GMI withdrawn Feb 2015 update: PPC to published in early Mar 2015. Jan 2015 update: PPC expected to be published end of Jan 2015. Dec 2014 update: revised GMI raised by Delta for discussion at Dec GRCF meeting. Revised GMI sent to GWCF for reference. Oct 2014 update: GMI raised by Delta for discussion at Oct GRCF meeting.
Retail Gas | IN023/14 | FRC HUB Upgrade Project | Documentation changes for the FRC Hub upgrade. The documents impacted are: FRC Hub Operational T&Cs; PBP3: FRC B2B System Archietecture; PBP3: FRC B2B System Specifications; Spec Pack Usage Guidelines. | AEMO | 2014-10-20 | GRCF | VIC, QLD, SA | Yes | IMP | May 2015 Update - On the 8th May advice sent to GRCF reps that the system implementation would be move to 24th May. Feb 2015 update: AEMO decision published on 27 Feb with an effective date date of 17 May 2015. Jan 2015 update: IIR published on 9 Jan 2015. Submissions close on 3 Feb. Dec 2014 update: submissions to the PPC close on 11/12/14. AEMO is targeting to publish the IIR on 5/01/15.
Retail Gas | IN039/10 | QLD NECF | Changes to the Retail Market Procedures (Qld) in light of National Energy Customer Framework |  | 2010-11-08 | GRCF | QLD |  | IMP | Jul 2014 Update - Moved from pending to "in prgress" as a result of Jurisdiction announcement of NECF go live 1 July 2015. Mid Jan 2014 update - RMP changes approved. Awaiting QLD to adopt NECF before implementing. Pre 2014 update - AEMO approved change.
Retail Gas | IN005/12 | QLD NECF | This change seeks to introduce changes that support anagement of a RoLR event under the National Energy Retail Law (NERL) or under Part 5 of Queensland's Gas Supply Act. The change is focussed on Retailers providing AEMO with customer details, to be used where a RoLR event occurs. These changes detail how customer data is managed and are harmonised with the arrangements that apply in other jurisdictions. This change requires system changes for Retailers and AEMO. |  | 2012-01-31 | GRCF | QLD | Yes | IMP | Jul 2014 Update - Moved from pending to "in prgress" as a result of Jurisdiction announcement of NECF go live 1 Jul 2015. AEMO approved change. The provision to the T900 files will be delivered as a part of Build 31 (Oct 2012).
Retail Gas | IN025/12 | QLD NECF | Queensland RoLR implementation |  | 2012-07-25 | GRCF | QLD | Yes | IMP | June 2015 Update -Notice of AEMO decision due to be published on 10 Jun 2015 with effective date of 1 Jul 2015 May 2015 Update - IIR issues 20 Apr with submission closing 13 May. AEMO targetting decision notice on 3 June Apr 2015 update - PPC closed on 16 Mar 2015. IIR to be issued shortly Feb 2015 update: PPC published, responses required by 16 Mar 2015 Jan 2015 update: GMI to be discussed at GRCF meeting on 20 Jan 2015. Jul 2014 Update - Moved from pending to "in prgress" as a result of Jurisdiction announcement of NECF go live 1 July 2015. Mid Dec 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package Early Nov 2013 update - No change since Oct 2013.GRCF recommend to group all RoLR issues / changes into the one Program of Work package OCT 2013 Update - GRCF recommend to group all RoLR issues / changes into the one Program of Work package To be raised pending notification of implementation dates
Retail Gas | IN017/14 | VIC Emegency contact number | Contact telephone number for emergencies | AEMO | 2014-07-31 | GRCF | VIC | TBA | IMP | Jun 2015 Update - It was noted that the VIC Emergency contact number would be shutting down at the end of the month. Participants noted that they have the required changes in hand for this issue, and as a result this issue would be closed. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan,The GRCF agreed that this issue should be moved to the ‘In Progress’ tab for discussion at the February 2015 GRCF meeting Added to issues/change register and yet to be prioritised.
Retail Gas | IN030/13 |  | UAFG Large to Small (vice versa) directive | Energy Aust | 2013-12-18 | GRCF | VIC |  | WD | Aug 2015 Update - EA have reconsidered the issue and consider it is no longer a priority and can be closed Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this is a low-medium priority. EnergyAustralia to develop a GMI for and nominate a target release date Early March 2014: No further update.Other priorities have meant no further progress. Mid Jan 2014 update - Added to issues/change register on 18/12/13 and yet to be prioritised.
Retail Gas | IN006/09 | Technology Changes (Sevice Orders) | Job Completion Code (JCC) Descriptions (Option 18 - Combination of Option 3 (Introduce Validation on JCC combinations allowed.(SA process) and Option 5 (Changes to the content of Service Order Response transaction to use the existing additional comment field -– limited use)) and 5 | Hillary Nguyen | 2009-07-20 | GRCF | VIC,QLD and SA | Possible system impacts for RBs and DBs | IMP | Oct 2015 Updated - Implemented on 14 Sept 2015 as planned. Aug 2015 update - AEMO to publish effective date of 14 Sep 2015 May 2015 Update - There was not fully support for an alternate effective date therefore 14 Sept 2015 which is inside the Q3 2015 period will be the effective date for this change. April 2015 Update: - AEMO decision published 16th March. Jan 2015 update: IIR expected to be published on 16 Jan 2015. Submissions close on 9 Feb 2015. Dec 2014 update: Effective date decision agreed by circular resolution on 11th Nov. PPC issued on 28th Nov. Partcipants requested to provide feedback by 19th Dec. Sep 2014 update - RBPWG endorsed changes in GMI. GRCF to advise preferred timing for the effective date of changes. Aug 2014 update - IIR to be issued by 29 August 2014.Aug 2014 - RBPWG workshop GMI on 28th July. Awaiting feedback on GMI and JCC combination codes from Participants which is due 15th Aug. Jul 2014 - GRCF requested that the Service Order technology changes be referred to the RBPWG for assessment. May 2014 - No update. Identified as priority project at Mar 2014 meeting. Mid Jan 2014 – RBPWG reps were reminded to provide any High level requirements for Service Order technology changes at the Gas Road Map Service Order workshop held on 18 Dec. Responses close on 31 Dec. All requests that were received have been added to the relevant issues and the register updated accordingly. Mid Dec 2013 - No change this month. GRCF noted that this is a technology change and should be group with other service order technology changes (IN022/13 and IN024/13) and prioritised accordingly in the new year Early Nov 2013 - GRCF noted that this is a technology change and should be group with other service order technology changes (IN022/13 and IN024/13) and prioritised accordingly in the new year OCT 2013 - AEMO to create a GMI based on option 18 however awaiting AEMO resource allocation. AUG 2013 - Update on DB trail due August RBPWG meeting. VAT results will be presented to the RBPWG with the forum to decide on the appropriate course of action to progress this issue.
Retail Gas | IN012/11 | Identify previous FRO | Process to identify the previous FRO in order to correct erroneous transfers | Allicia Volvricht | 2011-06-01 | GRCF | VIC, QLD, SA | Yes - AEMO and RBs | AI | Oct 2015 Updated - Implemented on 14 Sept 2015 as planned. Aug 2015 Update - AEMO software changes were successfully implemented in production with an effective date of 14 Sep 2015 May 2015 Update - There was not fully support for an alternate effective date therefore 14 Sept 2015 which is inside the Q3 2015 period will be the effective date for this change. April 2015 Update - AEMO decsion published 23rd March Jan 2015 update: IIR to be published on 16 Jan 2015. Submissions close on 9 Feb 2015. Dec 2014 update: Feedback from RBPWG/GRCF on GMI closed 31st Oct. PPC issued on 28th Nov. Partcipants requested to provide feedback by 19th Dec. Jul 2014 update - Targeting RBPWG meeting in Aug/Sep 2014. May 2014 - No update. Identified as priority project at Mar 2014 meeting. Early Mar 2014: To be discussed for prioritisation in March GRCF meeting. Mid Jan 2014 - No change since early Nov 2013. Because to the requirement to consider Service Order technology changes, workshop to commence Apr 2014 Mid Dec 2013 - No change since early Nov 2013. Because to the requirement to consider Service Order technology changes, workshop to commence early Feb 2014 OCT 2013 - This issue is to be included in Gas Road Map (Customer Transfer) AUG 2013 - Results of pilot program presented to participants. RBPWG to decide on options to progress the issue given the failure of the pilot program.
Retail Gas | IN008/15* |  | During the NARGP consultation, a comparision of the definition “meter” between jurisdictions revealed inconsistency. In QLD the term state a meter direct measure the energy. This is incorrect and should be corrected. (See IIR consolidated Response document ref # 22 and 23) | AEMO | 2015-02-17 | GRCF | QLD | TBC | Discussion Only | Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN006/14 | NSW/ACT B2B | Harmonisation of NSW ACT B2B. | AEMO | 2014-02-25 | NARGP | NSW / ACT | Yes | Implementation Phase | Apr 2016 update - NARGP going live on 2 May 2016 On Track Feb 2015 update - RMPs approved on 27th Feb
Retail Gas | IN004/15 | NSW/ACT RMP and GIP changes for Wagga Wagga Tamworth | NSW/ACT RMP and GIP changes for Wagga Wagga Tamworth | AEMO | 2015-01-22 | NARGP | NSW/ACT | Yes | Implementation Phase | Apr 2016 update - NARGP going live on 2 May 2016 On Track July 2015 Update - Notice of AEMO decision published on 11 June.
Retail Gas | IN018/15 | NSW/ACT B2B As Built changes | As Built' NSW/ACT Retail Market Procedure and Gas Interface Protocol changes (if required) | AEMO | 2015-04-14 | NARGP | NSW/ACT | Yes | Implementation Phase | Apr 2016 update - NARGP going live on 2 May 2016 On Track Feb 2016 Update - IIR issued 22nd Jan. Workshops were held on 5th Feb and 10th Feb (for WWT) to discuss this proposal. Response to IIR due 19th Feb Dec 2015 Update - PPC issued 19 Nov. PPC workshop on 4 Dec, WWT PPC workshop on 16 Dec. PPC responses due 5 Jan.
Retail Gas | IN032/15 | NSW/ACT Transition arrangements to new RMPs | NSW/ACT Retail Market Procedure (RMP) changes to support the transition to the new gas market arrangements | NARGP | 2015-12-17 | NARGP | NSW/ACT | Yes | Implementation Phase | Apr 2016 update - NARGP going live on 2 May 2016.Transition period starts 22 Apr 2016. On Track Feb 2016 Update - IIR issued 29th Jan. A workshop was held on 4th Feb to discuss this proposal. Also Production Verification Test (PVT) relief was discussed. Response to IIR due 25th Feb
Retail Gas | IN007/16 | Standardised retail gas schema adoption | During NARGP project it was raised by APA that whether the gas participants would be amenable to adoption of a standard version of aseXML schema across all retail gas markets. GRCF to review the merits of such an approach. | To be determined | 2016-02-18 | GRCF | All | TBC | Withdrawn | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this can be withdrawn. Apr 2016 Update - Updates to be made at prioritisation session. Feb 2016 Update - Yet to be prioritised.
Retail Gas | IN003/16* | Proposal to remove the yearly review of co-efficient values | AUDIT ITEM. Remove the AEMO obligation to undertake a 12 month review of the co-efficient values currently set out in the SA RMPs to harmonise with other jurisdictionRMP | AEMO | 2016-02-10 | GRCF | SA | No | Discussion Only | Apr 2016 Update - This item is now bundled with IN019/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Feb 2016 Update - Yet to be prioritised.
Retail Gas | IN001/15* | Minor edits to QLD RMPs | Minor edits to the QLD RMPs that AGL has identified | AEMO | 2015-01-19 | GRCF | Qld | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. Yet to be prioritised.
Retail Gas | IN016/15* | MIRN Listings | During the NARGP consultation it was identified that the RMPs in VIC and QLD the Distributor delivers the Complete MIRN listing to Retailers. In fact he Distributor delivers the file first to AEMO. The NSW/ACT now reads - Each Network Operator must use its reasonable endeavours to update, format and deliver a new complete MIRN listing in accordance with the Gas Interface Protocol which is to be made available to AEMO by 5.00 pm on the 8th business day after the end of the calendar month or as otherwise agreed from time to time by all relevant parties. AEMO must make each complete MIRN listing available to all Retailers after it is received from the Network Operator. (See IIR consolidated Response document ref # 130) | AEMO | 2015-02-26 | GRCF | VIC and QLD and SA | TBC | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 Prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. Yet to be prioritised. Raised during the NARGP consultation
Retail Gas | IN020/15* | RMP change to publishing Heating Values | Clause 6.2.2 (f) place an obligation on the DB to tell AEMO of a changes to Heating Value changes. There needs to be a further clause add to this section that obligates AEMO to publish the change and advises RBs. | David Grove (Origin) | 2015-04-14 | GRCF | Qld | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. May 2015 Update - Yet to be prioritised.
Retail Gas | IN021/15* | Add CustomerClassificationCode and CustomerThresholdCode needs to NMIStanding Data Response | During the NARGP WWT consultation it was identified that CustomerClassificationCode and CustomerThresholdCode needs to be added to the NMIStanding Data Response transaction in the FRC B2B System Interface Definition document. This is a documentation change only. | AEMO | 2015-04-23 | GRCF | SA | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders questioned whether this change may have system impacts.R. Abbott confirming whether this requires a system change. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. Uncertain that this does not require system changes. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. May 2015 Update - Yet to be prioritised.
Retail Gas | IN022/15* | Remove reference to “business day” for alternate transfer date | In preparing the AEMO’s internal system specification for NARGP changes, it was identified that change to allow transfer to also occur on non- business that was implement in Nov 2004 occurred however it appears that VIC clause 4.6.3 (Alternative Transfer Date) makes a reference to “business day” which is inconsistent with how the system operates. It is proposed to correct this drafting anomaly in QLD. This is a documentation change only. This changes has also be flagged in the NARGP change register. | AEMO | 2015-04-24 | GRCF | VIC/QLD | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. May 2015 Update - Yet to be prioritised.
Retail Gas | IN023/15* | Documentation change to Process Flow diagram 106 | In the VIC diagram 106 the GIP number is incorrect. It should be GIP 131 Instead of GIP 134 | AEMO | 2015-05-06 | GRCF | VIC | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. May 2015 Update - Yet to be prioritised.
Retail Gas | IN025/15* |  | There is a typo in section 2.1.6 of the FRC B2M-B2B Hub System Architecture in that the document still refers to Hansen’s Network. It should be changed to MarketNet to be consistent with the Vic and Qld version of the documents. Note this wasn’t pick up in the changes for IN023/14 consultation. The equivalent issue has been raised by REMCo and is issue # I78 | AEMO | 2015-05-29 | GRCF | SA | Nil | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to only have procedural impacts. Apr 2016 Update - This item is now bundled with IN025/16 - Refer to In Progress Tab. This line item is to be moved to the completed/withdrawn tab post the April 2016 prioritisation session. Oct 2015 Update – At the GRCF Aug 2015 meeting the GRCF supported AEMO view this was one of the low priority items that can be bundled with other similar low priority items for consideration by the GRCF in Dec 2015 whether they can be progressed in 2016. June 2015 Update - Yet to be prioritised.
Retail Gas | IN019/16 | RMP 2016 Changes Package 1 | AEMO initiated changes. AEMO Priority items for audit identified items: IN019/15 (Effective Degree Day) and IN003/16 (Heating Degree Day). Expedited consultation. | AEMO | 2016-04-09 | GRCF | VIC, SA | No | Discussion Only | May 2016. On May GRCF Agenda to discuss. IIR to be released. 26 Apr 2016 GRCF Prioritisation session - AEMO updated the GRCF stakeholders that it as progressing this item as a priority. Both items are likely to be procedural and have no system impact. April 2016. This item is a priority for AEMO as it relates to two audit findings. Intention is to commence expedited consultation in July 2016.
Retail Gas | IN023/12 |  | Direct Customer Connections (NECF) | AusNet | 2012-07-19 | GRCF | VIC | TBC | Withdrawn | June Prioritisation session - GRCFed to move this to the 'completed-withdrawn' tab. Apr 2016 Update - Updates to be made at prioritisation session.Apr 2016 Update - Updates to be made at prioritisation session. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, The GRCF agreed this issue should remain on hold.
Retail Gas | IN026/14 | Special Read Request | Update the following aseXML trn - SpecialReadRequest Add contact Name and Contact phone number Note - Raised at the NARGP - PRWG | GRCF | 2014-12-18 | GRCF | All | No | Withdrawn | June 2016 Prioritisation session update - Considered to be a low priority and GRCF decided to include on the 'completed/withdrawn' tab. Apr 2016 Update - Updates to be made at prioritisation session. Mar 2015 Update - GRCF agreed that this issue can remain on hold and revisited Q4 2015.
Retail Gas | IN024/14 | Definition of Allowable period potential incorrect. | According to AEMO legal the word "notification" should be deleted. It should be "Transfer Request". In the following definition - Allowable period means either: (a) in relation to a transfer request notification lodged without a customer no-change statement, the period commencing on the 10th business day prior to the proposed transfer date and expiring on the fourth business day after the proposed transfer date; or (b) in relation to a transfer request notification lodged with a customer no-change statement, the period commencing on the fourth business day prior to the proposed transfer date and expiring on the fourth business day after the proposed transfer date. | AEMO | 2014-11-25 | GRCF | VIC/QLD | No | Discussion Only | July update - this item has been included in IN025/16 (RMP 2016 Changes Package 2) and therefore moved to 'completed-withdrawn' June 2016 Prioritisation session update - minor document changes, AEMO to consider bundling in non-controversial changes. Considered to be a low priority. Apr 2016 Update - Updates to be made at prioritisation session. Mar 2015 Update - GRCF agreed that this issue can remain on hold and revisited Q4 2015.
Retail Gas | IN004/16 | Merger of Ellengrove gate stations | Update the Mapping of heating value zone to custody transfer meter in the QLD Retail gas market table to remove HV Zone id 103 and move those Postcodes to HV Zone 104. | AEMO | 2016-02-10 | GRCF | QLD | TBC | Implementation Phase | On June 2016 Agenda for discussion. Gate station decommissioning has been separated from the heating zone changes. HVZ changes to occur 22 June 2016. The Ellengrove 1 Gatestation will be decommissioned at a later date. May 2016. On May GRCF agenda to discuss. Implemenation date 26 May 2016. Apr 2016 update - APA advised that the merger will not occur until late April at the earliest. They will advise a firm date as soon as it is available. Mar 2016 update - Moved to progress tab as work on this change is underway Feb 2016 Update - GMI included in Feb meeting pack.
Retail Gas | IN028/15** | Build Pack 3 | A review of customer classification process flows with a view to updating the flow titles and appropriateness of 99.6, 99.7, and 99.8; as for NARGP it was agreed that only 99.9 is relevant as it is fit for purpose | AEMO | 2015-08-04 | GRCF | All | No. Documentation only | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is a low priority and unlikely to need system changes for Retailers and DBs and agreed this could be bundled into the NARGP package. Apr 2016 Updates to be made at prioritisation session. Yet to be prioritised. Raised during the NARGP consultation Aug 2015 Update - Yet to be prioritised.
Retail Gas | IN029/15** |  | A potential title change in PBP3 process flows and rename diagram 4.1 as ‘Customer Details Notification’ as that is more reflective of this process flow | AEMO | 2015-08-04 | GRCF | All | No. Documentation only | Discussion Only | 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is unlikely to need system changes for Retailers and DBs and agreed this could be bundled into the NARGP package. AEMO to assess this further. Apr 2016 Update - Updates to be made at prioritisation session. Aug 2015 Update - Yet to be prioritised.
Retail Gas | IN010/16** | PBP5 clarification item - PCF in Service Orders | The NSW-ACT RMPs and PBP5/PBP6 provide the difference for Jemena/AAD and APA/AGNL for WWT, and indicate that the PCF is only relevant for GAS only in Jemena/AAD but is relevant for Gas and Hot water for APA/AGNL. PBP5 does not have wording to differentiate in section 5.13.2 (ServiceOrderResponse) and to the letter implies the field should be present. But at the same time from reading the RMP it is infeasible for Jemena/AAD to provide something for it and it would not appear meaningful for retailers to make use of it and therefore to expect it for JGN service order responses whenever a new meter is fitted. This clarification can be included in a future release of the PBP5. | AEMO | 2016-03-16 | GRCF | NSW-ACT | No. Documentation only | Discussion Only | April 16 - low priority for AEMO. Only priority if participants pushes for this item to become a priority. AEMO to remain the proponent to raise a GMI if one is requested and could be grouped with other changes in the future. To be discussed as part of the prioritisation review in April GRCF. Mar 2016 Update - Yet to be prioritised.
Retail Gas | IN011/16** | PBP5 clarification item - MeterSerial Number in Service Orders | The NSW-ACT PBP5 does not have unambiguous wording in section 5.13.2 (ServiceOrderResponse) to clarify whether the Current/ MeterSerialNumber is always required to be included in SO Response and to the letter implies the field should be present. It is noted that it would be infeasible for Jemena/AAD to provide something for it in No Access scenarios, where the NoAccess block in the transaction would be used. The wording in the Usage column should ideally say "Required whenever a current meter is referenced as part of the Service Order request (and results in a Service Order completion)". This clarification can be included in a future release of the PBP5. Discussion may be required on whether it should be optional or even required if the Service order is closed with a ‘Could not complete’ or ‘Cancellation’ as these will not be using the NoAccess block. | AEMO | 2016-03-21 | GRCF | NSW-ACT | No. Documentation only | Discussion Only | April 16 - low priority for AEMO. Only priority if participants pushes for this item to become a priority. AEMO to remain the proponent to raise a GMI if one is requested and could be grouped with other changes in the future. To be discussed as part of the prioritisation review in April GRCF. Mar 2016 Update - Yet to be prioritised.
Retail Gas | IN012/16** | NSW-ACT process clarification item - Customer own read card process | Jemena advised in late Feb 2016 that they are ceasing their customer self read card process post NARGP Go live (2 May 2016). This change potentially impacts clauses 1.2.1 (Definitions), 3.1.3 (Customer provided Meter Readings), 3.5.1 (f) (General Meter Readings), 3.5.2(c) (Meter Readings on Transfer Request) and PBP5 process flows - Diagram 2.0 – Multiple Meter MIRN Read/Validation Process (Page 1). From an RMP perspective these clauses could be changed so to make provision for processing of Customer-Own Reads if the NWO provides the facility As per discussions in the NARGP CF on 15 March no changes are required to AEMO documentation (GIP, Process flows) for NARGP go-live and Jemena would be working bilaterally with the Retailers on this issue. This item has been raised to clarify the process and to confirm whether any changes are required to AEMO documentation. | Jemena | 2016-03-24 | GRCF | NSW-ACT | No. Documentation only | Discussion Only | Apr 2016 Update - Updates to be made at prioritisation session. Mar 2016 Update - Yet to be prioritised.
Retail Gas | IN015/16** | PBP5 Upgrade / Downgrade amendment | Update section 6.10 Upgrade/Downgrade to note that AEMO should send the CSV file received from DB to the impacted Retailer(s) and later provide the email ACK to both the DB and Retailer(s). | AEMO | 2016-03-30 | GRCF | NSW-ACT | No. Documentation only | Discussion Only | Apr 2016 Update - Updates to be made at prioritisation session. Mar 2016 Update - Yet to be prioritised.
Retail Gas | IN017/16** | PBP6 clarification item: Non Daily Meter Reads from DB to RBs | The NSW-ACT PBP6 requires explicit clarification in section 5.1 (Meter Reads – Energy and Consumption (Non Daily read meters) (DB to RBs)), and should ideally say: "• Note the following CSV elements may not be provided (including placeholders) by the Distributor. Transform process to add additional header field names and data row empty fields (comma delimiters) in that case." This clarification can be included in a future release of the PBP6. | AEMO | 2016-04-07 | GRCF | NSW-ACT | No. Documentation only | Discussion Only | April 16 - low priority for AEMO. Only priority if participants pushes for this item to become a priority. AEMO to remain the proponent to raise a GMI if one is requested and could be grouped with other changes in the future. To be discussed as part of the prioritisation review in April GRCF.
Retail Gas | IN024/16** | PBP5 minor documentation change | PBP5 has a typographical error in section 6.8.1.9 ERFTEstimationResultsToNWORpt, where the delivery time is noted as 10am, which is not in compliance with the RMPs clause 8.12.2 which requires delivery by 11am. RMPs take precedence over the PBP5 so this is not a compliance matter. This minor change can be incorporated in the next NSW-ACT consultation. | AEMO | 2016-05-02 | GRCF | NSW-ACT | No | Discussion Only | May 2016 Update - Yet to be prioritised.
Retail Gas | IN027/16** | PBP5 and PBP6 minor documentation change | PBP5 and PBP6 has a typographical error in section 5.5.1 Account Creation Notification, where data element 'MeterData/ Meter /ScheduledReadingDayNumber' path is not in sync with the schema path of 'MeterData/Meter/BasicMeter/ ScheduledReadingDayNumber'. PBP5 and PBP6 wording needs to be updated to match the schema implementation. | AEMO | 2016-05-24 | GRCF | NSW-ACT | No | Discussion Only | May 2016 Update - Yet to be prioritised.
Retail Gas | IN003/16 | Heating Degree Day | AUDIT ITEM. Section177(2) of the SA RMP requires AEMO to recalculate the value for each coefficient in the Heating Degree Day (HDD) calculation and publish these, at least annually. Operationally this has not been the case. Remove the requirement on AEMO to recalculate and publish these coefficients at least annually. | AEMO | 2016-04-09 | GRCF | SA | No | Implementation Phase
Retail Gas | IN019/15 | Calculation of Effective Degree Day (EDD) | AUDIT ITEM.'Attachment 6 of the Vic RMPs makes mention that the sunshine hours is the Bureau of Meteorology weather station Laverton. Operationally this is not the case. Bureau of Meteorology weather station at Melbourne Airport is used. The RMPs should be updated to reflect this. Expedited consultation. | AEMO | 2015-04-14 | GRCF | Vic | No | Implementation Phase
Retail Gas | IN028/16 | FRC Hub T&C minor documentation change | REMCo and AEMO have agreed that REMCo and the WA gas retail market are to be transitioned into AEMO. This transition to be targeted to be completed in October 2016. The proposed changes are minor documentation type changes to replace terminology such as to REMCo to AEMO, Rules to Procedures etc.. | AEMO | 2016-06-07 | GRCF | All | No | Implementation Phase
Retail Gas | IN029/16 | Spec Pack minor documentation changes | REMCo and AEMO have agreed that REMCo and the WA gas retail market are to be transitioned into AEMO. This transition to be targeted to be completed in October 2016. The proposed changes are minor documentation type changes to replace terminology such as to REMCo to AEMO, Rules to Procedures etc.. | AEMO | 2016-06-07 | GRCF | SA | No | Implementation Phase
Retail Gas | IN031/16 | High-Low tolerance | Changing meter read validation tolerances in the NSW/ACT market | Jemena | 2016-09-08 | GRCF | NSW/ACT | TBC | Implementation Phase
Retail Gas | IN035/16 | Gate Station | Decommission the Brightview gate station. Updates to Heating Value Zone to Custody Transfer Meter Mapping (was IN032/16 but number was duplicated) | APA | 2016-09-08 | GRCF | Qld | TBC | Implementation Phase
Retail Gas | IN036/16 | Info Pack minor documentation changes | REMCo and AEMO have agreed that REMCo and the WA gas retail market are to be transitioned into AEMO. This transition to be targeted to be completed in October 2016. The proposed changes are minor documentation type changes to replace terminology such as to REMCo to AEMO, Rules to Procedures etc.. | AEMO | 2016-10-11 | GRCF | SA | No | Implementation Phase
Retail Gas | IN032/12 | Duplicate Address Attributes | Duplicate Address Attribute Codes | AEMO | 2012-08-28 | GRCF | VIC, QLD, SA | TBC | Implementation Phase
Retail Gas | IN031/11 | Duplicate Address Attributes | Fast Track Process for release of address enumerations | AGL | 2011-12-22 | GRCF | VIC, QLD, SA | Likely system impacts for RBs and DBs | Implementation Phase
Retail Gas | IN020/16 | NSW-ACT WWT clarification item: Service Orders | APA reject Special Reads raised inside of 3 business days of the date submitted. This is not in accordance with the NSW-ACT RMPs clause 3.1.4(a) and SA RMPs clause 147, which allow 2 business days. | Energy Australia | 2016-04-21 | GRCF | NSW-ACT, SA | Yes. Potentially DB system change | Withdrawn
Retail Gas | IN037/10 |  | Changes to the Retail Market Procedures (Vic) in light of National Energy Customer Framework | AEMO | 2010-11-08 | GRCF | VIC |  | Withdrawn
Retail Gas | IN024/12 | RoLR Process Review | First-tier and non-DTS RoLR (system automation) | AEMO | 2012-07-25 | GRCF | VIC | TBC | Withdrawn
Retail Gas | IN020/10 | Balancing Arrangements in ACT | Market Design issues related to reconciliation account balances in no OBA network sections | TBA | 2010-08-24 | GRCF | NSW/ACT | TBC | Withdrawn
Retail Gas | IN007/12 |  | PIA/ URAA data issues related to information trail in participant systems | TBA | 2012-02-24 | GRCF | NSW/ACT | TBC | Withdrawn
Retail Gas | IN002/09 | Global Settlements Initiative | Global Settlements (indicative analysis) | AEMO | 2008-11-14 | GRCF | VIC | Major system impacts for AEMO and DBs. Moderate system impact for RBs | Withdrawn | Jan 2017 Prioritisation session update - GRCF considered this initiative was no longer worth pursuing therefore agreed it should be withdrawn. June 2016 Prioritisation session - GRCF requested AEMO provide an update on the progress of this initiative. Apr 2016 Update - Updates to be made at prioritisation session. Jan 2015 Update At the GRCF Prioritisation Session held 20th Jan, the GRCF agreed this issue should remain on hold.
Retail Gas | IN022/12 |  | Updates to deregistered MIRN status | APA | 2012-06-20 | GRCF | SA | TBC | Withdrawn
Retail Gas | IN015/14 | SA-RoLR | The SA RMP doesn’t make mention that Mildura MIRNs are to be treated differently. AEMO and Participants system are in sync with AER register of RoLR as it stipulates that AGL has been appointed by the AER as the default RoLR for all customers in South Australia connected to the gas distribution system of Envestra Ltd (ACN 078 551 685). In AEMOs opinion, there are questions around whether this is correct. NECF doesn’t apply in VIC so it is problematic to solve whilst the default RoLR are unknown. The outcome to avoid system changes is that when NECF arrives in VIC, AEMO needs to advocate that AGL is also the default RoLR for Mildura. | AEMO | 2014-07-22 | GRCF | SA & VIC | Yes | Withdrawn
Retail Gas | IN014/14 | SA-QLD UAFG Treatment | AGN proposal to adopt VIC UAFG methodology in SA and QLD | AGN | 2014-06-19 | GRCF | SA & QLD | Yes | Withdrawn
Retail Gas | IN022/13 | 5.Roadmap Business Process Reviews (Transfers) | Road Map - BP reviews (Customer Transfers) | GRCF | 2012-12-04 | GRCF | VIC, QLD, SA, NSW/ACT | TBC | Withdrawn
Retail Gas | IN038/12 | 3.Roadmap Business Process Reviews (MIRN Discovery) | Road Map - BP reviews (MIRN Discovery) | GRCF | 2012-12-04 | GRCF | VIC, QLD, SA, NSW/ACT | TBC | Withdrawn
Retail Gas | IN030/16 | Meter Disconnection Notification at street (MDN) | Clarify service order for street disconnections, where there is no customer with the existing FRO | Lumo/Red and AGL | 2016-07-28 | GRCF | TBC | TBC | Withdrawn
Retail Gas | IN042/16 |  | Change the MIRN Status allowable values in T94 AEMO Meter Fix Notification | Jemena | 2016-11-08 | GRCF | NSW/ACT | No | Implemented
Retail Gas | IN001/16 | Shoalhaven contestability | NSW Minister has advised AEMO to introduce retail contestability in the NSW Shoalhaven network. This needs to be completed in FY 2016-17. | AEMO | 2015-08-04 | GRCF | NSW/ACT | Yes | Implementation Phase
Retail Gas | IN033/16 | Removal of a RMP provision to provide a report to users | Proposal to remove a AEMO provision in the RMPs (Clause 9.1 (c ) to provide Used a overall outcome report from the forecasting algorithm. | AEMO | 2016-09-23 | GRCF | NSW/ACT | TBC | Implementation Phase
Retail Gas | IN034/16 | Certification | FRC Self-Service Certification enhancement | AEMO | 2016-09-23 | GRCF | SA | TBC | Implementation Phase
Retail Gas | IN038/16 |  | Align the requirements in clause of 8.12.1 of the AEMO NSW Retail Market Procedures with the delivery of market reports generated by the NSW RMO system (GRMBS) | AEMO | 2016-10-13 | GRCF | NSW/ACT | No | Implementation Phase
Retail Gas | IN040/16 | FRC Hub T&C | Add further clarity in relation to the timing noted in table 4 of section 4.1.3. | AEMO | 2016-10-31 | GRCF | All | No | Implementation Phase
Retail Gas | IN024/15 | RoLR | During the QLD RoLR consultation, it was identified that the timing provision aren't mentioned in QLD clause 10.1.3, SA clause 412, VIC clause 6.1.4A and new NSW RMP clause 7.2.5. This clauses relate to when the DB needs to update their database following a RoLR event. AGL proposes that timing provisions should be added with AEMO also supports. | to be determined | 2015-05-20 | GRCF | All | Nil | Withdrawn
Retail Gas | IN021/16 | NSW-ACT Complete MIRN Listing data quality | Jemena to rectify Complete MIRN Listing data quality issues as per defect #195 identified in the NARGP Market Trial #3. | Origin | 2016-04-21 | GRCF | NSW-ACT | No | Withdrawn
Retail Gas | IN022/16 | NSW-ACT WWT Complete MIRN Listing data quality | APA to rectify Complete MIRN Listing data quality issues as per defect #206 identified in the NARGP Market Trial. | Origin | 2016-04-21 | GRCF | NSW-ACT | No | Withdrawn
Retail Gas | IN027/14 | Possible VIC, QLD and SA RMP changes to Harmonise with new NSW/ACT RMPS | The following is a list of possible RMP changes to apply to other states result for from NARGP consultation Project. The ref # refer to a PPC consolidated Response document for IN006/14. Ref # 5 Definition for Certification to be deleted as it is only referenced in the one clause in the body of the RMPs. Ref # 2 and 32 - Remove ref to "Index Read" and replace with actual meter reading in body of RMPs Ref # 24 - Use NERL definition Energise/Connect and De-Energise/disconnect to replace commissioned and Decommissioned. Ref #36 - Replace definition of Customer with NERL version and remove subject customer Ref #38 Replace EIC definition with NERL EIC definition Ref # 26 - Replace the existing FRC Hub definition with "FRC HUB means the information system provided by AEMO for the transmission of aseXML messages under these Procedures" Ref #10 Use the NERL definition for EIC Ref # 22 - Update the definition special read request to reference the GIP Ref # 56 - Update the Interpretation sections to include ref to the NERL Ref # 138 and 51 - Define the term Reading Period Ref #173 - Review Disconnecting of Basic Meter clause and reword so it uses the terms De-energising and Disconnect. Also delete clause tiled Decommissioning of delivery points Add clause about Additional FRC Hub Outages | AEMO | 2014-12-18 | GRCF | Vic and Qld | No | Impemented
Retail Gas | IN025/16 | RMP document changes Packdage 1 | RMP documentation changes (Package 1) VIC, QLD, SA. AEMO initiated changes. Bundled RMP changes into one non-contentious package. GMI's are: IN001/15, IN008/15, IN016/15, IN020/15, IN021/15, IN022/15, IN023/15, IN025/15 and IN024/14 | AEMO | 2016-04-09 | GRCF | VIC, QLD, SA | TBC | Implemented
Retail Gas | IN041/16 | Outage plan | When NARGP was implement in May 2016, Jemeice raised concerns that they didn’t what to adopt the same Service Order outage plan used in other states. They plan to put forward some modification to the existing plan in the future | Jemena | 2016-11-02 | GRCF | NSW/ACT | No | Implemented
Retail Gas | IN037/16 |  | Remove JCC 3 from AML completion response transaction | APA | 2016-08-17 | GRCF | All | No | GMI
Retail Gas | IN039/16 |  | Harmonise the approach to apply password protection on the T900 (Customer Details) file that Retailers send AEMO | M2 | 2016-10-13 | GRCF | All | Yes | AEMO decision published
Retail Gas | IN026/16** | RMP document changes Packdage 2 | RMP documentation changes (Package 2) NSW/ACT. AEMO initiated changes. Bundled RMP changes into one non-contentious package. GMI's are: IN28/15, IN29/15, IN10/16, IN11/16, IN12/16, IN15/16, IN17/16, IN24/16, IN27/16 | AEMO* | 2016-05-02 | GRCF | NSW-ACT | No | Awaiting Implementation
Retail Gas | IN005/17 | Error with Sample | An error in the “PARTICIPANT BUILD PACK 5: NSW-ACT SPECIFIC BUILD PACK”, in particular in page 188, the XML Sample section of 6.7.8 IAITImbalanceTradeRequest. As there are missing elements in the given XML Sample, GRMBS would reject such transaction when processing it. | AEMO | 2017-04-20 | GRCF | NSW/ACT | No | Awaiting Implementation
Retail Gas | IN010/17 | Error in Spec Pack | The changes applied to the SA FRC B2B System Interface definition for IN039/16 (Harmonisation of T900 Password Protection) iniative overlooked that a chapter 4 specifying the compressed CSV format doesn’t exist in this document. This document needs amending to say "as described in Specification Pack document titled FRC CSV File Format Specifications" rather than the words "in this document". | AEMO | 2017-08-18 | GRCF | SA | No | Awaiting Implementation
Retail Gas | IN003/17 | VIC Pressure Factors | New Metering Pressures – Victoria AGN network | APA | 2017-03-09 | GRCF | VIC |  | Withdrawn
Retail Gas | IN007/13 |  | Develop one MIRN structure document for all jurisdictions and include Multinet Update. | AEMO | 41395 | GRCF | VIC, QLD, SA, NSW/ACT | Nil | Implement
Retail Gas | IN024/16 | Customer Transfer Rule Change Requests | Customer Transfer Rule Change requests (AEMC consultation) may be extended to the gas market. | GRCF | 2016-06-30 | GRCF | All (except Vic) | TBC | Withdrawn
Retail Gas | IN014/16 | 6 monthly Base load refresh for NSW-ACT | Evaluate adoption of a 6 monthly Base Load refresh process for NSW-ACT, similar to the process prescribed in the VIC RMPs clause 2.8.1 | AGL | 2016-03-30 | GRCF | NSW-ACT | Yes. Potentially AEMO-DB system change | Withdrawn
Retail Gas | IN013/16 | PBP5 clarification item - Jemena/AAD network bills | During the last stages of the NARGP Market Trial 3 in March 2016, Origin identified potential issues with Jemena/AAD network bills, that create issues with reconciliation of network bills by Retailers. Specific issues are: - Charge components in DUOS A and DUOS B file do not have the correct quantity as quantity multiplied by rate does not equal dollars - Previous Read Date does not align between the reading file and the charge file for DUOS B An interim solution is being implemented till such a time a consultation takes place to incorporate a permanent fix to the issue in the PBP5. This issue is being raised to ensure a permanent fix is incorporated in the PBP5 in a future consultation. This may require addition of new fields (such as number of days) in the CSV elements for Tariff A and B. | Origin | 2016-03-24 | GRCF | NSW-ACT | Yes | Withdrawn
Retail Gas | IN021/14 | NSW/ACT Energy Value Validation ranges | Review of NSW/ACT Energy Value Validation ranges described in 3.6.10. by NARGP PRWG | to be determined | 2014-10-13 | GRCF | NSW/ACT | No | Discussion Only
Retail Gas | IN011/17 | Reports | Removal of Intra Day reports as described in clause 215 has they are not used | AEMO | 2017-08-30 | GRCF | SA | Yes | Implementation Phase
Retail Gas - WA | IN001/16W | Move-In Transfer when ECN has been raised | Alinta Energy is proposing to give clarity in the Rules regarding the timeframe concerning when a customer “commences occupation of premises”, to assist Users in circumstances when they are permitted to raise a transfer as a move-in following an ECN. | Alinta | 2016-08-29 | Clause 78 | Nil | Decision | 2017-02-17
Retail Gas - WA | IN002/16W | Clause 255 Revised Timing and Notification of Special Circumstances | It may be possible to improve the effectiveness of notifications of special circumstances under clause 255(1), and there is some ambiguity in timing for notices in clause 255(2) that needs to be clarified | AEMO | 2016-10-17 | Clause 255 | Info Pack - Non-IT RMP Communications | Decision | 2017-02-17
Retail Gas - WA | IN034/16W | Certification | FRC Self-Service Certification enhancement | AEMO | 2016-09-23 | N/A | Connectivity Testing and Technical Certification | Decision | 2017-02-17
Retail Gas - WA | IN040/16W | FRC Hub T&C | Add further clarity in relation to the timing noted in table 4 of section 4.1.3. Proposed changes to FRC Hub T&C | AEMO | 2016-10-31 | N/A | FRC Hub T&Cs | Decision | 2017-02-17
Retail Gas - WA | IN002/17W | Procedure Change Process Review | Review procedure change process described in chapter 9 | AEMO | 2017-06-07 | PCC | TBA | Implementation | 2018-04-30
Retail Gas - WA | IN003/17W | Identify previous retailer | Amendments to identify previous retailer of transfer request | Kleenheat | 2017-06-14 | PCC | TBA | Implementation | 2018-04-30
Retail Gas - WA | IN005/17W | Transition Deed | AEMO proposed to remove clause 8.6 from the REMCo/AEMO transition deed | AEMO | 2017-12-01 | PCC |  | No
Retail Gas - WA | IN004/17W | New RMP clause for Regulator Fee | Introduce a mechanism for the Economic Regulation Authority (ERA) to recover the costs of its gas retail market-related administration functions from gas retail market participants via a ‘Regulator Fee’. | PUO | 2017-12-01 | PCC | WA | No | Implementation Phase
Retail Gas - WA | IN027/15 | Life Support | The issue was initially raised in NARGP and WWT and refers to whether gas should support Life Support. The GRCF discussed how a specific gas equipment can be considered as Life Support equipment. GRCF participants agreed to shadow mapping processes currently taking place in the BMRG noting that the outcomes could potentially lead to schema and process changes. | AGL | 2015-07-02 | GRCF | All | TBC - likely | Withdrawn
Retail Gas - WA | IN007/17 | Kent town Weather station change | Changes to SA weather observation station | AEMO | 2017-06-23 | GRCF | SA | No | Implementation Phase
Retail Gas - WA | IN013/17 | Include UAFG in QLD RMPS | QLD Retail Market Procedures to be updatexd to include UAFG process | APA | 2017-09-19 | GRCF | QLD | TBC | Implement
Retail Gas - WA | IN001/18 |  | Change to transfer timeframes affecting RMP/PBP5 | Jemena/AEMO | 2018-01-08 | GRCF | VIC, QLD, SA and NSW/ACT | TBC | IIR
Retail Gas - WA | IN003/18 | Fix to definition of FRC Hub T&C | Currently the VIC and QLD RMP definition for FRC HUB Operational Terms and Conditions isn’t in sync with operational practice. The definition current includes Self Contracting Uses. This needs to be removed. | AEMO | 2018-05-03 | GRCF | VIC and QLD |  | IIR
Retail Gas - WA | IN007/18 |  | Proposal to amend the Hot Water Estimation and Substitution Methodology as described in the Retail Market Procedure. | Jemena | 2018-06-18 | GRCF | NSW/ACT |  | NoD
Retail Gas - WA | IN013/14 | SA RoLR | The SA RoLR testing revealed that currently there is insufficient clarity in the RMP and/or the Specification Pack pertaining to the T1060 (AEMO Meter Fixes). AEMO sends the T1060 file the designated RoLR in a RoLR event. The lack of clarity has meant the T1060 file is generating incorrect information. The purpose of this file is to signify that the Network Operator completed a Meter Fix on a date prior to the RoLR event that was generated by the losing FRO and that AEMO has processed the meter fix post the RoRL event potential registering the losing FRO as the FRO. The report is to prompt the designated RoLR that the parties (designated RoLR, AEMO and Network Operator) need to get together to remedy the situation. The list of known RoLR consequences needs to be updated to capture this situation. | AEMO | 2014-06-02 | GRCF | SA | Yes | Discussion Only
Retail Gas - WA | IN002/17 | Plumber Licence Number and CoC | Potential Schema Change resulting from NSW Plumber Licence Number length and CoC Number Length | AGL | 2017-01-27 | GRCF | NSW/ACT | TBC - likely | GMI
Retail Gas - WA | IN016/14 | CBA Review | The Retail market (both gas & electricity) groups and AEMO are developing a ‘Cost Benefit Analysis’ process that seeks to establish the costs and benefits (tangible & intangible) across the industry when undertaking Retail Market changes. | AEMO | 2014-02-22 | GRCF | All | No | Discussion Only
Retail Gas - WA | IN005/18W | Notification of Error or Inaccuracy by Previous User | Amend the procedures to include a formal process in the event a previous user notifies a current user that there may be a transfer error | Alinta | 2018-06-21 | PCC | WA | No | Approved by ERA
Retail Gas - WA | IN002/18W | Clause 323A (1) | Minor RMP change. The complaince panel supported the idea to remove provision 323A(1)(a) for the compliance panel to meet annually. | AEMO | 2018-04-13 | PCC | WA | No | Approved by ERA
Retail Gas - WA | IN003/18W | Spec Pack needs updating to accommodate additional Flat or Unit type | Proposed changes to resolve a minor inconsistency with the FRC B2B System Interface Definition documentation and AEMO and some participant IT systems | AEMO | 2018-05-09 | PCC | WA | Yes | Approved by ERA
Retail Gas - WA | IN005/19W |  | Retrospective EIC |  |  | GRCF | WA | Procedure-only | Withdrawn
Retail Gas | IN001/19 | High-Low tolerance | Changing meter read validation tolerances in the NSW/ACT market | Jemena | 2019-01-29 | GRCF | NSW/ACT | Procedure-only | Implementation | April 2019 update - Feedback closed 1 March. Awaiting advice from Jemena on effective date. Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019.
Retail Gas | IN004/18 | HDD | Changes to the SA RMP clause 177(5) (Calculation of heating degree day) to accommodate Forecast hour of sunshine | AEMO | 2018-05-21 | GRCF | SA | Procedure and system impacts | Implementation | April 2019 update - IIR issued on 1 April. Feedback due 2 May Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. GMI circulated for feedback which claosed 15th Feb Nov 2018 update - Because of other priorities, the preparation of consultation paper has been postpone whihc was due in October. AEMO proposed that the consultation for this initiative will commence by Q2 2019. There was no objection to this revised proposed commencement date. May 2018 update - Yet to be prioritised
Retail Gas - WA | IN001/19W | Transition Deed | Review remaining clause 8 of the provisions within the REMCo/AEMO transition deed related to continuing obligations on AEMO and determine whether they are still required. | AEMO | 2019-02-19 | GRCF | WA | Procedure-only | Implementation | April 2019 update - Seek acceptance by GRCF particip[ants Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. New issue raised
Retail Gas | IN012/17 |  | Updates to deregistered MIRN status. This was IN022/12 | APA | 2017-09-11 | GRCF | SA | TBA | Implementation | Jul 2019 update- NoD published 3 Jul 2019. Changes take effect 8 Aug 2019. April 2019 update - Consultation due to commence 15 Apr 2019 Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Feb 2018 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2018 therefore agreed to move this item to the in progress tab. Sept 2017 Update - Yet to be prioritised.
Retail Gas | IN002/16 | Gas day commencement time | NGR rule change proposal - change of gas day start time in SA, Qld & NSW to align to Vic (6:00) | AEMO | 2016-02-10 | GRCF | NSW/ACT, SA and QLD | Procedure and system impacts | Implementation | Jul 2019 update - Awaiting implemation on 1 Oct Apr 2019 update- NoD published 1 March. Changes take effect 1 October 2019. Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. IIR now closed. Awaiting AEMO decsion Jan 2019 update - IIR issued 11 Jan. Feedback due 11 Feb Nov 18 update – A PPC is due to be issued in the week commencing 19 Nov. July 2018 update. A presentation on this topic occurred at the June meeting. It was agreed that this program of work should commence in early November to allow the Rules and procedures to align. June 2018 update – AEMO is planning to mobilise working groups in Q3 2018 Feb 2018 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2018 therefore agreed to move this item to the in progress tab. Jan 2017 update - AEMC have issued a draft determination proposing to implement a 6am gas day start time across all facilitated markets from 1 Apr 2021 May 2016 - Minor system (GSH and STTM) changes and procedure changes. 28 Apr 2016 GRCF Prioritisation session - GRCF stakeholders noted this is likely to require procedural and system changes for Retailers and DBs and will need a transition period to allow this to occur. Agreed that all stakeholders need to keep a 'watching brief' on this as the AEMC progresses the rule change. Apr 2016 Updates to be made at prioritisation session. Yet to be prioritised. Raised during the NARGP consultationApr 2016 Update - Updates to be made at prioritisation session..Apr 2016 update - This is a Watching brief dependant on outcomes of rule change with AEMC. Submissions closed on 31 Mar 2016. Feb 2016 Update - Yet to be prioritised.
Retail Gas - WA | IN004/18W | Complete MIRN Listing | Report generated each month by the network opertor of all MIRNs and addresses to assit the Retailer complete MIRN Discovery requests | AGL | 2018-05-09 | GRCF | WA | Procedure and system impacts | ERA submission | Jul 2019 update - PCR was issued 8 Mar with submission closing 22 Mar. IIR issued 10 May with responses closing 7 June. The ERA submission was issued 28 June with feedback closing 9 Aug. April 2019 update - Awaiting internal review of feedback provided by participant Feb 2019 update - Awaiting ERA approval Dec 2018 update - PCR and IIR consultations completed. Submission made to ERA for approval. Aug 2018 update - The GMI has been file layout and proposed transfer method details. AEMO will issue the Procedure Change Request for consultation on 29 Aug 2018. June 2018 update - GMI tabled for discussion at June meeting
Retail Gas | IN009/18 |  | RMP regulatory relief transitionals for the shorter gas day on 30 Sept 2019. This is linked to IN002-16, Change proposal - change of gas day start time in SA, Qld & NSW to align to Vic (6:00) | AEMO | 2018-11-08 | GRCF | NSW/ACT, SA and QLD | TBA | Implementation | Jul 2019 update - NoD published on 27th May with changes taking effect 28 June April 2019 update - PPC feedback closed 29 March. AEMO reviewing feedback and is on track to publish IIR on 12 April Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Sept 2018 update - Yet to be prioritied
Retail Gas | IN002/19 | GDH | GDH Retail Guidelines | AEMO | 2019-02-12 | GRCF | NSW/ACT, SA and QLD | TBA | Implementation | Jul 2019 update - Awaiting Implementation April 2019 update - AEMO requested feedback on retail guides in early March. Feedback closed 29 March. Feb 2019 update - Yet to be prioritied
Retail Gas | IN010/18 | Exempt seller | AEMO has identified a mismatch between the retail gas market registration provisions in the National Gas Rules (NGR) (Part 15A) and the exempt seller regime within the National Energy Retail Law (NERL). Should the AEMC approve the rule change, the Retail Market Procedures (RMP) for SA, QLD and NSW/ACT will need to be amended. There should be no system changes | AEMO | 2018-11-16 | GRCF | NSW/ACT, SA and QLD | TBA | Implementation | Jul 2019 update - IIR feedback closed 28 Jun. NoD due to be published soon. April 2019 update - Details on when the RMP consultation will commence is due late June 2019 Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Dec 2018 update - Yet to be prioritied
Retail Gas - WA | IN004/19W | Minor amendments to the WARGMA | Minor amendment to clause 5.5 of the WA Gas Retail Market Agreement (WAGRMA) to remove the need for ERA to approve addition of a new participant. | AEMO | 2019-02-21 | GRCF | WA | Procedure-only | Implementation | Jul 2019 update - IIR issued 10 May with responses closing 7 June. The ERA submission was issued 28 June with feedback closing 9 Aug April 2019 update - PCR feedback being reviewed Mar 2019 update - New issue raised
Retail Gas | IN009/19 | Residual GDH procedure changes | Residual GDH procedure changes | AEMO | 2019-05-03 | GRCF | SA,NSW/ACT and QLD | TBA | Implementation | Yet to be prioritised
Retail Gas | IN003/19 |  | The MIRN ranges described in the MIRN Structure (section 2.5.2) document and the Identification of Victorian Contestable Transfer Points (section 3.2.2) are different. They should be that same. AEMO to investigate and advise. | Multinet | 2019-02-19 | GRCF | Vic | Procedure-only | Implementation | Nov 2019 update - The updated MIRN Structure and Identification of Victorian Contestable Points documents have been published. Sep 2019 update - Move this from pending to in progress as this initative involves a changes to a guide Mar 2019 update - Yet to be prioritied
Retail Gas | IN006/17 | Harmonise RMPs | Harmonise SA RMPs with other jurisdictions | AEMO | 2017-06-02 | GRCF | SA | Procedure-only | Implementation | Jan 2020 update - Feedback on the IIR closed on 13 Dec. None of the responses received opposed the changes set out in the IIR. AEMO published its decision to on 10th Jan 2020 to approve the changes. Changes to the RMPs, TP and guides will take effect on 10 Feb. Nov 2019 update – On 14 Oct AEMO issued PPC to GRCF. Submissions closed 1 Nov. AEMO received responses from OE and AGL. AEMO issued IIR which included feedback on the PPC comments received from participants. IIR closes on 13 Dec and AEMO is on track to publish decision on 10 Jan. Updates to the various guides will be issued soon with feedback targeted for 13th Dec Sep 2019 update - Feedback on the 4th draft SA RMP has now closed. A review of the feedback identified about 40 items needs to addressed. If AEMO’s review doesn’t unearth any material issue the formal round of consultation would commence early October 2019. Jul 2019 update - 4th draft of RMP and TPs issued 1 Jul with feedback due 9 Aug Apr 2019 update - Targeting to have 4th draft of RMP issued for feedback in late April 2019. Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Jan 2019 update - 3rd draft feedback closed 23 Nov. AEMO still reviewing feedback Nov 18 update - 3rd draft of SA harmonised RMP was issued on 18 Oct. Feedback is due 23 Nov. Aug 2018 update – With the Life Support initiative closed, a proposed revised timeline put to the GRCF for consideration July 2018 update – AEMO has received feedback on the second draft of the revised SA procedures from AGL, AGN, OE and EA. Because of the potential aseXML schema change for Life Support, the next steps for this program of work will need to be reviewed. This will be a topic of discussion at the next GRCF meeting to be held Tuesday 17th July. June 2018 update – The 2nd draft of the SA harmonised RMPs was issued on 12 June. Feedback is due 29 June May 2018 Update - Proposed revised timeline put to the GRCF for consideration Feb 2018 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2018 Feb 2018 update - Initial draft to be issued ahead on workshop planned for Mon 26 Feb 2018 July 2017 Update - Yet to be prioritised.
Retail Gas | IN014/17 |  | Remove the text "using the sum of the actual heating degree days calculated under rule 177 for each of the previous 365 gas days for the HDD zone" from clause 373B as it is AEMO view it is not reqired. | AEMO | 2017-11-06 | GRCF | SA | TBA | Implementation | Linked to IN006/17 Feb 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Feb 2018 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2018 therefore agreed to move this item to the in progress tab. Nov 2017 Update - Yet to be prioritised.
Retail Gas | IN002/20 | Report Timing Rqeuirements | Review all AEMO timings in the RMPs (all jurisdictions) (documentation changes only) | AEMO | 2019-09-17 | GRCF | All except WA | Procedure-only | Withdrawn | May 2020 update: AEMO has decided not proceed with this change based on the advice from Legal. April 2020 update - Targeting late Apr to issue a GMI with feedback due mid May Feb 2020 update - Same as Jan 2020 Jan 2020 update - Awaiting availability of resource to progress this proposal Nov 2019 update - Consultation targeted to commence early Jan 2020. Sept 2019 Prioritisation session update - GRCF considered this initiative was worth pursuing in 2020.
Retail Gas - WA | IN013/19W | Proposed amendment to Clause 32 | Clause 32 (Error Corection Notice) of the WA Retail Market Procedures be amended to make it clear that participants must resolve incorrect churns within a certain period of time. | Kleenheat | 2019-07-09 | GRCF | WA | Procedure-only | Rejected | May 2020 update: IIR closed 6 May. Several participants did not support this proposal. AEMO has published decision on 15 May stating it had rejected the change. Apr 2020 update - IIR Published on 6 April 2020 with participant feedback by 6 May 2020. Should AEMO decide to submit the proposal to ERA for approval it will be included with the IN006-18W change which is on tracket to be issued to the ERA by third week of May 2020. Feb 2020 update - Procedure Change Request issued for consultation on 10 Feb 2020. Jan 2020 update - AEMO has allocated resource to commence the formal consultation and is aiming to issue the Procedure change request by early Feb 2020 Nov 2019 update - AEMO is still working around proposed changes to clause 32. Sept 2019 - Added to "in progress" tab and GRCF 2019 work program July 2019 update - N Telford presented the GMI at the GRCF meeting. AEMO will conduct an internal review of the GMI and provide updated GMI for GRCF consideration
Retail Gas | IN015/20 |  | Create a new Withdrawal Zone for the Wide Bay gas network system | Australian Gas Networks | 2020-12-21 | GRCF | Qld | TBA | GMI | On the 18th May, AEMO circulated a GMI invited participants to provide feedback on the proposal to creating a separate withdrawal zone for Wide Bay area. This are no RMP but there is minor changes to 2 guideline. AGL and Origin Energy provided feedback supporting the proposal. It now up to AGIG to determine whether to progress this change. Given there are no RMP implication and no desenting view raised AEMO will close this initiative.
Retail Gas - WA | IN003/19W | Holistic “tidy up” of the WA RMPs | Holistic “tidy up” of the WA RMPs These are non-contentious minor changes that are typo corrections or add further clarity to the RMPs. They are documentation changes only | AEMO | 2019-02-19 | GRCF | WA | Procedure-only | Implementation | July 2020 update. ERA approved changes on 17 July. Updated RMP published 3 Aug June 2020 update: The ERA consultation on this proposal closes 30 June. A ERA decision on the proposed changes is expected by the end of July. May 2020 update: This proposal has been submitted to the ERA for approval. A decision from ERA is expected by end of July 2020. Apr 2020 update - IIR closed 31 March 2020. This proposal is now awaiting AEMO decision whether to submit the proposal to ERA for approval. If it is to proceed, it will be included with the IN006-18W change which is on tracket to be issued to the ERA by third week of May 2020. Feb 2020 update - PCR closed 4 Feb 2020. Feedback broadly supportive of AEMO's position. IIR due to be issued 3 Mar 2020. Jan 2020 update - PCR issued 6 Jan 2020. Feedback due 4th Feb Nov 2019 update - Opportunity for Category 2 and 3 change submission has now closed. AEMO will distribute the changes for industry review and then proceed to the PCR. Sep 2019 update - AEMO has issued a new version of the draft RMPs as well as a new Register of Category 2 and 3 changes. GMI V2.0 will be issued in November. Jul 2019 update - GMI issued 9 Jul alson with draft RMPs. Feedback due 12 Aug April 2019 update - AEMO internal review Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. New issue raised
Retail Gas - WA | IN007/18W | Replace the term Procedure Change Committee with Gas Retail Consultative Forum (GRCF) | With the Procedure Change Committee (PCC) agreeing to merge with the Gas Retail Consultative Committee (GRCF) the WA Retail Market Procedures (RMP) need to be amended by replacing any reference to Procedure Change Committee with the term Gas Retail Consultative Forum. | AEMO | 2018-12-10 | GRCF | WA | Procedure-only | Implementation | July 2020 update. ERA approved changes on 17 July. Updated RMP published 3 Aug Sep 2019 update - As per IN003/19W Jul 2019 update - now linked to IN003/19W April 2019 update - Develop GMI Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. Dec 2018 update - Yet to be prioritied
Retail Gas - WA | IN006/18W | Requirements around EIC | Remove the requirement to delete information around explicit informed consent (EIC) from clauses 55A (3), 72 (4) and 166A (3) of the WA Retail Market Procedures | Origin | 2018-07-29 | GRCF | WA | TBA | Implementation | July 2020 update. ERA approved changes on 17 July. Updated RMP published 3 Aug June 2020 update - The ERA consultation on this proposal closes 30 June. A ERA decision on the proposed changes is expected by the end of July. May 2020 update: This proposal has been submitted to the ERA for approval. A decision from ERA is expected by end of July 2020. Apr 2020 update - This proposal will be submitted to ERA for approval by third week of May 2020. Feb 2020 update - Same as Jan 2020 Jan 2020 update - Formal consultation concluded. AEMO issued notice of its decision to submit this proposal to ERA for approval. It will be submitted with multiple other proposals. Nov 2019 update - IIR consultation commenced and will close on 9 Dec 2019. AEMO will then publish its decision on submitting an application to ERA for approval. Sep 2019 update - GMI endorsed by GRCF and AEMO will proceed with consultation. Jul 2019 update - Updated GMI for discussion at GRCF July meeting April 2019 update - Internal review Feb 2019 WA Prioritisation session update - GRCF considered this initiative was worth pursuing in 2019. New issue raised
Retail Gas | IN010/20 |  | Add a new field (Reason code) to the Service Order Request transaction | AGL | 2019-11-29 | GRCF | VIC | Procedure and system impacts | Withdrawn | Aug 2020 update: AGL request this be withdrawl given the requirment changes made to IN026/15 Apr 2020 update - At the Feb 2020 release workshop, it was noted there was minimal distributor support for this initative, so AEMO will be parking this initiative. Jan 2020 update - Yet to be prioritied
Retail Gas - WA | IN001/15W | WA Profiles | REMCo proposed a review the suitability of the estimation/daily profiling processes in the Procedures and used in the GRMS | AEMO | 2015-10-21 | GRCF | WA | TBA | Withdrawn | Sept 2020 update - AEMO tabled a report on the WA profiling methodology and recommendation at the Aug 2020 GRCF meeting. AEMO’s recommendation included retaining the UEBW calculation methodology in its current form and reviewing the estimated annual energy consumption of new basic meters. The recommendation also proposed this initiative be closed, but explore the idea review the estimated annual energy consumption of basic meter guideline. Participants were to provide feedback by 31 Aug. No participants opposed the recommendation. AEMO has now closed this issue. . June 2018 update - As per Feb meeting minutes, AEMO is investigating options to have this work undertaken by external consultants as there are no resources available internally to complete the work. Cost estimates will be provided to the PCC. Oct 2017 Update: On 18th Oct AEMO e-mailed each Retailer spreadsheets containing the old REMCo data which closed action item 3.8.1 Aug 2017 Update: AEMO advised that the data used to prepare the REMCo report can be split into retailer specific data. This would incur a cost. AEMO can provide an estimated cost and timeframe on reassessing the data. ATCO advised that they would be keen to provide as much data as possible to assist in an assessment of UAFG assumptions. AEMO to provide cost and timeframe for this review at the next meeting. Jun 2017 Update: Ruth Guest updated on AEMO's assessment of the findings and recommendations in REMCo's report. AEMO to make an assessment of the appropriateness of the estimation process for the WA market. The PCC agreed to park the issue of meter read estimates based on actual reads from same time last year. AEMO will do a brief review on the profiling methodology. AEMO to consider providing each business with their data used in the preparation of the REMCo report. Dec 2016 Update : The Chair provided a summary of the paper prepared by AEMO on the REMCo report on the GRMS Basic Meter Profile Performance. The PCC were asked whether REMCo’s report meet the original brief. Catherine Rousch (Alinta) indicated that it did meet the brief. No other PCC member put forward any alternate thoughts. The Chair advised that replacing the Aclara software in July 2017 with a “like for like” profiling methodology used today would result in a saving within 12 months based on current cost estimates. PCC members support the idea of having savings in the near future agreed to AEMO’s approach to progress the replacement of the Aclara software in July 2017 with software which provides the current profiling methodology. The Chair also advised that AEMO does not have the full picture in terms of financial implication of the 8% over estimation finding. The PCC members agreed that each business would provide analysis by 31/01/17 to determine the financial flow on effect. It was noted that AEMO would need this information to help formulate an “industry as a whole” cost benefit assessment on changing the profiling methodology to be conducted. The PCC agreed to park any further discussion on a replacement profile methodology until the flow on impacts of an 8% overestimation is understood.
Retail Gas | IN006/19 |  | 301A (4) mentions s timing delivery of 51.5 hrs replicates the 3.5 hr delivery + 2 days. If the 3.5 hr delivery changes, the 51.5 hr may also need to be changed to align delivery times. There is some doubt whether such specific timing required for this process is warranted. This idea was raised during the GDH IIR consultation and was published in NoD (see item #24) | AGL | 2019-02-19 | GRCF | SA | TBA | Withdrawn | Sept 2020 update - The clause 301A was deleted as part of SA Harmonisation work (IN006/18) so no longer applicable Mar 2019 update - Yet to be prioritied
Retail Gas | IN017/20 |  | Update the technical protocol (TP) documents so that customer contact information can be used for planned work. At the moment TP limits customer contact information to just emergency and fault call management. | AGN | 2020-06-22 | GRCF | All except WA | TBA | Implementation | Sept 2020 Update - NoD published 4 Sept. Effective date is 30 Sept. Yet to be prioritiesed
Note on B168: Taryn Maroney: This has the same identifier as '5.Roadmap Business Process Reviews (Transfers)' in the on hold tab
Note on J231: Taryn Maroney: I assume we only note IIR when commenced
Note on E239: Taryn Maroney: Is this still AGL? AEMO is now running this.

## Drop down lists
Market | Consultative Forum | Gas Status | Electricity Status | System Impact
Electricity | ERCF | Discussion only | Discussion only | TBA
Retail Gas | ERMCF | GMI | ICF | Procedure-only
Retail Gas - WA | GRCF | PPC / PCR | In Progress | Procedure and system impacts
|  | IIR | CIP | System-only
|  | Implementation | Issues Paper
|  | ERA submission | Draft Report
|  | NoD | Implementation
|  | Approved by ERA | Complete
|  | Withdrawn | Withdrawn
|  | Rejected | Rejected
Closed

## Current Fields (hidden)
ID | Description | Required? | ID | Description | Required? | ID | Description | Required?
GM00 | AEMO Retail Gas Market Issues - Change Register |  |  | Timeline for RMP Changes |  | BM00 | BMRG - QC Extract
GM01 | sorting | No | RM01 | BLANK | No | BM01 | BLANK
GM02 | Priority for 2013 |  | RM02 | Issue Number and Brief Description |  | BM02 | Target Release
GM03 | Issue Number INnnn/yy |  | RM03 | Jurisdiction |  | BM03 | Issue ID
| Date Gas Market Issue (GMI) raised |  | RM04 | 1. Notice of PPC Published |  | BM04 | Status
GM05 | State QLD NSW SA VIC |  | RM05 | 2. PPC consultation closed |  | BM05 | Priority
GM06 | Short Description of Issue |  | RM06 | 3. Notice of IIR published |  | BM06 | Short Title
GM07 | RMP Reference |  | RM07 | 4. IIR consultation closed |  | BM07 | BMRG Notes / Discussion
GM08 | GIP/Spec Pack Reference |  | RM08 | 5. CEO Approval
GM09 | Other Reference (eg: NGR/NGL etc) |  | RM09 | 6. Decision Published
GM10 | System Implications |  | RM10 | 7. Notice of Procedure date start
GM11 | TARGET system change IT build # and release date |  | RM11 | 8. Operational / Implementation date
GM12 | Status. |  | RM12 | Signed CEO Approval
GM13 | Status Comment |  | RM13 | Notice of Decision
GM14 | Proponent
GM15 | Company
GM16 | Consultative Forum GRCF-V GRCF-S GRCF-Q GRCF-N&A GWCF
GM17 | Date PPC Raised | No
GM18 | PPC Accept/ Reject | No
GM19 | SA/CF deadline (eg 30BD from date raised) | No
GM20 | I&IR to be published on AEMO website by (eg 40BD from date raised) | No
GM21 | Actual Date Forum Consultation completed on | No
GM22 | Expedite or Ordinary | No
GM23 | Date Time Limit Notice raised on | No
GM24 | New date for I&IR | No
GM25 | Actual Date I&IR published | No
GM26 | Date Public Consultation concludes? Expedited - 15BD Ordinary - 20BD | No
GM27 | RMD resource | No
GM28 | BLANK | No
GM29 | Comments relating to Priority | No
Ref ID
Priority
Problem Statement
Title
Originator Name
Originator Company
Energy Type
Market (State)
Issue Detail
Target Build
Current Stage
Stage Date
|  |  |  | Change Type | Procedure
System
Schema
Additional Comments

## Closed (hidden)
RETAIL MARKET ISSUE/CHANGE REGISTER
Ref ID | Priority | Title | Originator Name | Originator Company | Register Date | Energy Type | Resp. Forum | Juristiction | Problem Statement | Issue Detail | Target Release | Current Stage | Stage Open Date | Stage Close Date | Change Type |  |  | Additional Comments | Magnitude
[15 empty] | Proc. Change | System Change | Schema Change
826 | 1 | Small Generator Aggregator | Tbc | Tbc | 2012-06-08 | Electricity | BMRG | NEM | Change inline with AER Rule Ammendment | There is currently a Rule Change proposal progressing with the AEMC introducing a new category of Market Participant called Small Generator Aggregator. Consequently AEMO must be able to clearly identify these 'SGA' connection points in MSATS in order to accurately settle the Market. | 2013-05-15 | Awaiting Implementation | 2013-05-15 | 2013-05-15 | Yes | Yes | No | Final Decision made. Implementation on 15 May 2013 | Tbc
700 | 2 | Identification of Incumbent Retailer | Ross McAlpine | EnergyAustralia (Former) | 2008-12-18 | Electricity | BMRG | NEM | Retail Churn Visibility | Retailers are obligated to obtain approval for retrospective transfers, CRs 1020-29 from the incumbent retailer prior to raising the CR. Retailers do not always know who to obtain approval from. The key reason being the customer does not know as either they have recently moved into the property or have lost copies of the prior bill/s. In these situations the retailer either approaches NEMMCO or the DNSP. Subject to the stance of the DNSP they may decline to provide this information or they will pass on the request to the incumbent retailer seeking approval to disclose to the requesting retailer. | 2013-05-15 | Awaiting Implementation | 2013-05-15 | 2013-05-15 | Yes | Yes | No | Final Decision made. Implementation on 15 May 2013 | Tbc
829 | 2 | Obligation to Provide Customer Letter for NSW De-en non Payment | Malcolm Hempel | Origin Energy | 2012-07-24 | Electricity | BMRG | NSW | B2B Procedures - State Based Ammendment | ICF reveived from Origin on 18/07/12 to update B2B Procedures to align with revised NSW regulations as of July 1 2012 in relation to obligation to Provide Customer Letter for NSW De-en non Payment. | 2013-05-15 | Awaiting Implementation | 2013-05-15 | 2013-05-15 | Yes | Yes | No | Final Decision made. Implementation on 15 May 2013 | Tbc
823 | 3 | Greenfield Sites and Direct Connections | Tbc | Tbc | 2012-04-12 | Electricity | BMRG | NEM | New Connections | QC 823 is an amalgamation of QC 816 - Greenfield Sites and QC 817 - Direct Connections. Background Information: Create NMI on Greenfield Sites (previously QC816) As raised by Origin & AGL: It has been brought to the attention of participants that some LNSPs are creating NMIs in MSATS for Greenfield sites prior to the receipt of a New Connection from a Retailer. The concern with this process is that the roles, which are mandatory on the CATS Create NMI Request, are being defaulted. The roles being nominated at this early stage could see incorrect participants being assigned, particularly the MDP and of specific concern is the role of FRMP being defaulted to the LR. Process for Managing Direct Customer Requests for New Connections and Alterations Service Requests (previously QC817) As raised by Origin & AGL: Division 2 – Obligation to provide customer connection services of the NERL states: 66-Obligation to provide customer connection services A distributor must, subject to and in accordance with the energy laws, provide customer connection services for the premises of a customer- Who requests those services; and Whose premises are connected, or who is seeking to have those premises connected, to the distributor’s distribution system. Note- The Rules may provide that a retailer may arrange customer connection services. The customer connection services must be provided to a customer in accordance with the relevant customer connection contract. | 2013-05-15 | Awaiting Implementation | 2013-05-15 | 2013-05-15 | Yes | Yes | No | Final Decision made. Implementation on 15 May 2013 | Tbc
780 | 5 | MDP in the Rules | Tbc | Tbc | 2011-01-13 | Electricity | BMRG | NEM | Change inline with AER Rule Ammendment | On 18 June 2009, AEMO (formerly NEMMCO) submitted a Rule Change Request that principally sought to transfer the current arrangements governing certain metering data service providers from a deeds-based framework to a framework contained in Chapter 7 of the National Electricity Rules (Rules) [AEMC website <http://www.aemc.gov.au/Electricity/Rule-changes>] The Rule change was to: · create a new category of person in the Rules called a Metering Data Provider; and · transfer the responsibility for collecting metering data from AEMO to the Responsible Person for metering installation types 1,2, 3 and 4 with the exception of transmission / complex connection points. The Rule change also included other amendments to Chapter 7 of the Rules as follows: · apply the existing dispute resolution process in clause 8.2 of the Rules to disputes between Metering Data Providers and other parties, including Registered Participants; · clarify AEMO's power to establish service level procedures for Metering Data Providers and specify the scope and purpose of the procedures AEMO can make; · vary, delete or introduce definitions to clarify the roles and obligations of service providers, improve the clarity of and reduce duplication within the Rules, and standardise terminology across all metering installation types; · restructure Chapter 7 to ensure each clause deals only with one substantive matter, correct errors and improve clarity, and take into account of the substantive changes proposed in AEMO's Rule change proposal; and · makes consequential amendments to Chapters 3, 5, 6, 8, 9 and 11 of the Rules. | 2013-05-15 | Awaiting Implementation | 2013-05-15 | 2013-05-15 | Yes | Yes | No | Final Decision made. Implementation on 15 May 2013 | Tbc
855 |  | Ads & Alts | Mara Tenis | EnergyAustralia | 2013-06-21 | Electricity | BMRG | NEM | Ads & Alts Review | A review of the B2BProcedures is required to accommodate multiple Ads & Alts service orders for situations such as Solar. | Tbc | Waiting Assessment | Not Started | N/A | Yes | Yes | No | Withdrawn based on recommendation from BMRG Meeting 140 - see action item 138.9.1 | Tbc
815 |  | B2B & MSATS Minor Manifest Updates | Tbc | Tbc | 2011-12-02 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | The Glossaries in the B2B Procedure Technical Guideline contains the following redundant terms. B2B - MDA, NEMMCO MSATS - MDA, Metering Data Agent These terms are required to be removed from the B2B Procedures in the next B2B release. The Glossaries in the MSATS Procedures contains the following redundant terms; B2B - MDA, NEMMCO MSATS - MDA, Metering Data Agent These terms are required to be removed from the MSATS Procedures in the next MSATS release. | 2013-05-15 | Waiting Assessment | N/A | N/A | Yes | No | No | Changes incorporated in MSATS and B2B | Tbc
724 |  | Consistent use of grey explaination boxes in B2B Procedures | Tbc | Tbc | 2009-10-19 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | There are a number of diagrams and clauses in the B2B Procedures that are surrounded by 'Grey Boxes'. The intent of the 'Grey Boxes' is to advise the audience that this information has been provided for information purposes only and does not form any obligation under the procedures. The use of these grey boxes is inconsistent throughout the B2B Procedures and needs to be rectified. Note: There is no ICF for this QC as it was raised as a result of earlier consultations. | 2014-05-01 | White Paper A | Not Started | N/A | Yes | No | No | Andrew Suwignjo <asuwignjo>, 24/01/2013: As per the November BMRG, this enhancement is to move from build 46.83 - May 14 to 46.84 - Nov 14 (pending IT to update QC vlaues). Closed | Tbc
834 |  | MSATS CATS Minor Manifest - CR6801 retrospective days typo | Adrian Salkeld | Ergon Energy Corporation Ltd | 2010-02-24 | Electricity | BMRG | NEM | CSDN | On 11 June 2009 the IEC noted the Consolidated CSDN Review Report & requested the BPRG to review the CSDN Procedures in light of the CSDN Review. This item should incorporate details and resolve QC's - 713, 660 and International Address Issues. | 2013-05-15 | Waiting Assessment | N/A | N/A |  |  |  | Correct retrospective days value should be 130 business days (not 20 business days) Section 39.9 Table 39-A needs to be updated accordingly. CLOSED | Tbc
835 |  | MSATS CATS Minor Manifest: CR1084 table missing heading text | Tbc | Tbc | 2013-02-26 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | MSATS CATS Procedures, Section 9.9, Table 9-A Time Frame Rules missing heading for CR1084 (see attachment). To be updated with: CR Code 1084 – Change Retailer Child NMI - Move-In – Retro | 2013-05-15 | Waiting Assessment | N/A | N/A | Yes | Yes | Yes | To be updated with: CR Code 1084 – Change Retailer Child NMI - Move-In – Retro CLOSED | Tbc
Note on P3: Craig Dickson: This section looks to identify what is impacted by the change.

## Change Register (hidden)
RETAIL ELECTRICTY MARKET ISSUE/CHANGE REGISTER | [11 empty] | Colour Code Blue = Currently Assigned Resources by AEMO No colour = no planned implementation date / still pending discussions / review
Ref ID | Priority | Title | Originator Name | Originator Company | Register Date | Energy Type | Resp. Forum | Juristiction | Problem Statement | Issue Detail | Target Release | Current Stage | Stage Open Date | Stage Close Date | Change Type |  |  | Additional Comments | Magnitude
[15 empty] | Proc. Change | System Change | Schema Change
853 | 1 | FRC Tasmania - Market Transfer Cap (Temp) | Tas Govt | Tas Govt | 2013-06-24 | Electricity | BMRG | NEM | Full Retail Contestability | Development of changes to enable the temporary control of market transfer volumes inline with Tas Govnt. Requirements. |  | Initial Consultation | Started | N/A | Yes | Yes | No | Initial Consultation released, submissions close 23 September. DD released subs close 6/11 | Small
776 | 2 | CSDN Project | IEC/RMEC | IEC/RMEC | 2010-11-16 | Electricity | BMRG | NEM | Customer Data | Improving the CSDN process for participants | 2013-11-01 | Final determination | N/A | N/A |  |  |  | AEMO has commenced UAT 14/10 AEMO has completed UAT | Tbc
756 | 2.1 | Small Generator Standing Data | IEC/RMEC | IEC/RMEC |  | Electricity | BMRG | NEM | Standing Data | Review on how NMI standing data is used and enable small genration to be captured within Standing Data fields in MSATS | Tbc | Final determination | N/A | N/A |  |  |  | AEMO has commenced UAT 14/10 AEMO has completed UAT | Tbc
839 | 2.3 | CSDN Project - Sensitive Load | BMRG | BMRG | 2013-03-25 | Electricity | BMRG | NEM | Customer Data | New issue created as per action item 134.11.7 of BMRG meeting 134 Original items 776-5-1a of CSDN project Additional fields for sensitive load - new sensitive load values Facilitate a proof of concept trial of the proposed Sensitive Load Life Support Reconciliation Process | 2014-05-01 | Initiate | N/A | N/A | Yes | Yes | Yes | Sub -group established of AGL, Energex, Endeavour and AEMO. Trial to occur in mid September 4/10: Trial completed - BMRG requested be incorporated into May 2014 release | Tbc
852 | 4 | Duplicate Address Attributes | Malcolm Hempel / Peter Ellis | Origin Energy / SP AusNet | 2013-05-03 | Electricity | BMRG | NEM | Customer Data | The new Enumerations list for Street Types introduced via the Schema 29 change in July has introduced a number of duplicate Codes for Street Types. The new list has duplicate codes e.g. Boardwalk = BWK or BWLK; Connection = CNN or CNTN; Waterway = WTWY or WWAY. Or duplicate codes for "Street Types" already in the list e.g. Avenue = AV or AVE; Crescent = CR or CRES. Others with duplicates include: Causeway, Deviation, Gateway, Heath, Island, Lane, Thoroughfare, Wood (see Note 1). Also in the Schema 29 change were additions to the other Address Attribute lists. This has introduced a number of duplicates for Flat Type Address Attribute. In the "Flat or Unit Type" list duplicate codes now exist for Unit = U (and now) UNIT; Flat = F or FLAT; Factory = FY or FCTY; Office = OFF or OFFC. (see Note 1 and Note 2). There is an Options paper to remove or keep the duplicates in the schema. The BMRG agreed to Option 3 at August meeting. | Tbc | Initiate | N/A | N/A | No | Yes | Yes | Options paper - to keep or remove duplicates from the schema. BMRG agreed to Option 3 at August meeting to correct the duplicates in MSATS, allow industry to maintain duplicates and remove the duplicates from the Schema. This is contingent on ASWG approval. 4/10: Issues paper drafted by SPAN raised issues requiring BMRG resolution; unlikely to hit May 2014 release timeframes; | Tbc
787 | 5 | NECF - Retailer Initiated De-energisation (Relating to Sub-Types) | AEMO | AEMO | 2011-07-13 | Electricity | BMRG | NEM | Re-en and De-en | Retailer initiated De-energisation This QC has been raised as part of the NECF review process to identify potential NECF related enhancements. Service order processes dated 25 November 2009 (V1.6.1) address De-Energisations under 2.12.8. The current information is not expansive as it is written to address the process from a service order perspective. It is also not consistent in its formatting. NERR 111-116 considers the reasoning for raising a service order, going into considerable depth. | 2013-05-15 | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | Awaiting assessment by the RMLF | Tbc
775 | 9 | RoLR Testing Project | Tbc | Tbc | 2010-11-16 | Electricity | BMRG | NEM | ROLR | RoLR Testing Project - AS per the IEC/RMEC based on the outcome of QC 734 RoLR Testing Paper, Industry RoLR testing to be undertaken. Also see closed QC539 There is no ICF or supporting documentation for this QC other than the IEC and RMEC meeting outcomes. NOTE: This is an AEMO action item at this stage and listed here for tracking and noting purposes only. | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | Awaiting RMLF assessment | Tbc
832 |  | CBA Review | Tbc | Tbc | 2012-12-06 | Electricity | BMRG | NEM | Review of AEMO Change Management | BMRG raised the concept of a CBA ‘review’ in their September 2012 meeting. As a result a workshop was held at the BMRG meeting in October to identify matters for consideration and resolve as part of the review, prior to consideration of inclusion in the NEM Change Management Process. (Refer item 5 of the BMRG minutes from October BMRG meeting minutes). This work will continue into 2013. | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc |  | Tbc
854 |  | Market Size Reporting | Mara Tenis | EnergyAustralia | 2013-05-27 | Electricity | BMRG | NEM | Market Reporting | Align the AEMO market size reporting in line with the current gas requirements. | Tbc | Waiting Assessment | Not Started | N/A | Yes | Yes | No | Continuous improvement - prioritised at 16 July BMRG meeting | Tbc
810 |  | Jurisdictional Documents - Stage 1 - Network Billing | Tbc | Tbc | 2011-09-08 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | BDPIP Project - Network Billing only ICF - to be prepared (See QC 651 for Stage 2) The BPRG have undertaken significant work in cleaning up and requesting closure of jurisdictional B2B Documents that are no longer in use. The next phase for this project is to review each of the documents in the list and detemine the best method to consolidate these active Jurisdictional documents into a B2B Procedure to shift governance from multilple individual bodies to a National framework & governance. | Tbc | White Paper - A | Not Started | N/A | Yes | No | No | Andrew Suwignjo <asuwignjo>, 16/08/2012: As per July/August BMRG, item is still with IEC/RMEC. Removed from build until outcome from IEC/RMEC known. | Tbc
833 |  | Schema Versioning Consistency | Tbc | Tbc | 2013-02-26 | Electricity | BMRG | NEM | AseXML | The initial development of the aseXML schema required version attributes on elements to be supplied in instance documents. It was later found that this lead to un necessary complexity when migrating from one schema to another. There was a gas retail market paper raised (CR 72) that dealt to this issue and proposed the introduction of optional / default versioning. In brief this meant that when migrating between schema versions, where no changes in an instance document occurs to a user, i.e. the change may have introduced an optional element that is not relevant to them they will not have to change their code base. The receiver of the document can populate the version attributes if they need to since they are stored in the schema as default values. When introduced the change was applied only to elements which were being touched as part of any schema change or to any new ones being added that required versioning. With all the changes in schema that have occurred since, it is time to consider if applying the same versioning throughout the schema to provide consistency is an appropriate change to make. Note: this has been presented to the Gas forums with the ref: IN037-12 | Tbc | CBA - Stage 1 | 2013-02-26 | N/A | No | Yes | Yes | The specific proposal by the ASWG is to update the remaining version attributes in the schema which are still designated as mandatory or are not completely designated to an optional / default to be designated as optional and with a default value related to the version where they were last modified. | Tbc
851 |  | Customer Preferred Date and Time | Lyn McBryde | Energex | 2013-05-02 | Electricity | BMRG | QLD | B2B Procedures - State Based Ammendment | Queensland Electricity Safety Regulation 2002 S152 places an obligation on Queensland distributors to perform a visual inspection of customers’ premises prior to reconnection (an exemption exists for reconnection after disconnection for non-payment where the site has been disconnected for less than 1 month and the customer has not changed). A 5 or 4 hour appointment window is required as per legislation. Retailers set this appointment window when talking to the customer. Special read/Check reads often require a 5 hour appointment window to gain access to the metering installation due to ongoing estimated reads. Retailers have been asked to set this appointment window when talking to the customer. Minimal volumes of other service order types also require a 5 hour appointment window. One other Distributor has confirmed that if an appointment is not set in the CustomerPreferredDateAndTime field, any appointment details in the Special Instructions are ignored. Other Distributors (not all) generally agree that the appointment window (for access) required in QLD constitutes an ‘appointment’. | Tbc | Waiting Assessment | N/A | N/A | Yes | Yes | No | TBC | Tbc
721 |  | B2B VMD/PMD processes related to meter data churn (MDP Issue) | AEMO | AEMO | 2009-10-01 | Electricity | BMRG | NEM | AseXML | Raised by Meter Data Provider Working Group (MDPWG) The MDPWG have raised an ICF to review the use of the Verify Meter Data and Provide Meter Data B2B Transactions for use by MDP's in a churn situation. See ICF for further details. This is also related to QC325 and must be addressed as a whole solution. | 2013-05-15 |  | N/A | N/A | Yes | Yes | No | This project has been transferred to the metering group as at July 2013. 14/10: Workshop proposed for Nov with participants | Tbc
812 |  | Customer Threshold Code - Ongoing Maintenance and Calculation | AEMO | AEMO | 2011-11-04 | Electricity | BMRG | NEM | NECF | Customer Threshold Code - Ongoing Maintenance and Calculation - Currently being calculated based on the ADL by some distributors whilst others target the calculation based on actual consumption data. | 2013-05-15 | On Hold | N/A | N/A | Tbc | Tbc | Tbc | Awaiting review of ADL papers from WG for presentation to the BMRG. | Tbc
849 |  | Changes Required For DRMASLWG | Tbc | BMRG | 2013-05-02 | Electricity | BMRG | NEM | Demand Response | Overview: This QC item looks to recognise that significant procedure and system changes may be required as a result of the initiated Power Of Choice review/project currently managed through the DRMASLWG. Impacts to BMRG: A programme of work may arise that will require the BMRG to review and make procedural changes to B2B and MSATS. Reason for QC Item: To allocate priority and ensure we track resource requirements accordingly | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | As yet, requirements of the BMRG are undefined and appropriate solutions will be identified and implemented as required. | Tbc
830 |  | Placeholder – New Conn Direct Connect BDPIP flows for NECF | Tbc | Tbc | 2012-08-16 | Electricity | BMRG | NEM | NECF | As agreed in August BMRG, placeholder item created to track work completed by BMRG to date regarding process flow for New Connections - Direct Connect, that needs to be considered as part of NECF. | Tbc | Waiting Assessment | Not Started | N/A | Yes | Yes | No | TBC | Tbc
831 |  | Service Order Requests raised on Non-Business Day | Trent Smith | AGL | 2012-09-12 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | Interpretation of B2B procedure Service Order Process 3.3.2 Notice Period Timing Requirements for submission of next day re-energisations has been interpreted differently by various DNSP’s. This results in: 1. Inconsistency between DNSP processes causes increased handling costs for Retailers as well as a degraded customer experience 2. Unnecessary rejects for Retailers: if retailer raises the same service order on next business day, this service order would be accepted | Tbc | CBA - Stage 1 | 2012-10-02 | N/A | Yes | No | No | TBC | Tbc
836 |  | CSDN Project - Changes to Telephone Definition to ensue only numeric values can be provided | Tbc | CSDNWG | 2013-03-18 | Electricity | BMRG | NEM | CSDN | New issue created as a result of action item 134.11.2 from BMRG meeting 134. Original item 776-1-N1 of CSDN project To handle the changes to telephone definition to ensure only numeric values can be provided | Tbc | Waiting Assessment | N/A | N/A | Yes | Yes | Yes | Make the field numeric | Tbc
837 |  | CSDN Project - Clarification for the use of Business Name & Customer Name and obligations in respect of Site Vacant | Tbc | CSDNWG | 2013-03-18 | Electricity | BMRG | NEM | CSDN | New Issue created as per action item 134.11.3 of BMRG meeting 134 Original item 776-1-N1 of CSDN project The procedures for customer name / business name are ambiguous as a result of differences in systems built by participants There are differences between retailer processes for unknown customers and vacant sites | Tbc | Waiting Assessment | N/A | N/A | Yes | Yes | No | Further investigation needed on what distributors and retailers are doing with customer name / business name From a distributors perspective consistent retailer processes are required in respect of unknown customer or vacant site | Tbc
838 |  | CSDN Project - Clarification of Peson Name | Tbc | CSDNWG | 2013-03-25 | Electricity | BMRG | NEM | CSDN | New issue created as per action item 134.11.4 of BMRG meeting 134 Original item 776-1-N3 of CSDN project Resolve issue of mandatory fields Title, First and Last Name where customer do not wish to provide title or only have single name | Tbc | Waiting Assessment | N/A | N/A | Yes | No | No | TBA | Tbc
840 |  |  | Tbc | CSDNWG | 2013-03-25 | Electricity | BMRG | NEM | CSDN | New issue created as per action item 134.11.8 of BMRG meeting 134 Original item 776-1-G1 of CSDN project The CSDN item proposed adding an email address for the customer. This relates to various issues raised by the BMRG. | Tbc | Waiting Assessment | N/A | N/A | Yes | Yes | Yes | TBA | Tbc
841 |  | CSDN Project - Timing Obligations / Clause Changes | Tbc | CSDNWG | 2013-03-25 | Electricity | BMRG | NEM | CSDN | New issue created as per action item 134.11.9 of BMRG meeting 134 Original item 776-1-G1 of CSDN project To review the process of Retailer sending CDN to the Distributor | Tbc | Waiting Assessment | N/A | N/A |  |  |  | TBA | Tbc
842 |  | CSDN Project - Adopt the Gas Process in Electricity for RoLR | Tbc | CSDNWG | 2013-03-25 | Electricity | BMRG | NEM | CSDN | New issue created as per action item 134.11.10 of BMRG meeting 134 Original items 776-8-3 and 776-8-N1 of CSDN project Discuss the best process for storing customer information for a RoLR event | Tbc | Waiting Assessment | N/A | N/A | Yes | No | No | TBA | Tbc
843 |  | CSDN Project - Life Support | Tbc | CSDNWG | 2013-03-27 | Electricity | BMRG | NEM | CSDN | New issue created as per action item 134.11.7 of BMRG meeting 134 Original items 776-5-1b&c of CSDN project Additional fields for sensitive load - new sensitive load values | Tbc | Waiting Assessment | N/A | N/A | Yes | Yes | No | TBC | Tbc
844 |  | SGSD - Small Generation via standing data fields | Tbc | CSDNWG | 2013-04-16 | Electricity | BMRG | NEM | SGSD | New issue created as a result of action item 135.7.1 from BMRG meeting 135 Original item 1A of SGSD project | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
845 |  | SGSD - Update MP Obligations and CRs for Tariff Applications | Tbc | CSDNWG | 2013-04-16 | Electricity | BMRG | NEM | SGSD | New issue created as a result of action item 135.7.2 from BMRG meeting 135 Original item 2H of SGSD project Clarify MPB and LNSP obligations to ensure consistent application of Network Tariff Codes and associated metering information in MSATS | Tbc | Waiting Assessment | N/A | N/A | Yes | No | No | TBA | Tbc
846 |  | SGSD - Notification of old MDP/MPB during churn | Tbc | CSDNWG | 2013-04-16 | Electricity | BMRG | NEM | SGSD | New issue created as a result of action item 135.7.3 from BMRG meeting 135 Original item 4J of SGSD project Provision of the current MDP/MPB participant ID for related change role CRs | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
847 |  | SGSD - Standing data validation via MSATS | Tbc | CSDNWG | 2013-04-16 | Electricity | BMRG | NEM | SGSD | New issue created as a result of action item 135.7.5 from BMRG meeting 135 Original item 7E of CSDN project Creation of a new MSATS transaction in order to query the validity of standing data in MSATS with the data owner | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
848 |  | SGSD - Clarification of NMI Suffix and Meter Register | Tbc | CSDNWG | 2013-04-16 | Electricity | BMRG | NEM | SGSD | New issue created as a result of action item 135.7.6 from BMRG meeting 135 Original item 1E & 1F of SGSD project NMI suffix & meter register fields to have consistent definitions and be mandatory across CATS, MDM and MDFF as determined necessary and the values should match in all locations | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
792 |  | NECF - Protected period | AEMO | AEMO | 2011-07-13 | Electricity | BMRG | NEM | NECF | NECF - Protected period This QC has been raised as part of the NECF Review process to identify potential NECF related enhancements. The introduction of NECF in the NEM introduces changes with regard to Requirements: NERR 108 and 120 DB must not de-energise a customer for non-payment during protected periods. Industry will need a common understanding of this term to enable systems and processes to be developed that allow for enhanced validation of service order requests eliminating/reducing disputes as to why de-energisations were not performed. It should be noted that there are currently differences in timeframes to perform this work across jurisidictions. | 2013-05-15 | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
806 |  | Process for Re-Classification of NT, CCT, CCC etc | AEMO | AEMO | 2011-07-14 | Electricity | BMRG | NEM | NECF | An automated solution for reclassification requests above must be considered as soon as possible post urgent NECF deliverables. The automated solution should also cover issues such as NMI Reclassification requests, Network Tariff Code change requests etc | 2013-05-15 | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
773 |  | CSDN Audit - Ongoing Review | AEMO | CSDNWG | 2010-11-16 | Electricity | BMRG | NEM | CSDN | CSDN Audit - as per the IEC/RMEC an audit is required to review the CSDN procedures. AEMO and Deloitte are responsible for providing a strategy for managing the CSDN procedural audit/review. Refer to the IEC Meeting minutes for further information on details relating to this QC. NOTE: This is an AEMO action item and listed here for tracking and noting purposes only. | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBC | Tbc
782 |  | B2B Contacts List Project | Tbc | BMRG | 2011-04-08 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | B2B Contacts List Project: Primarily the BMRG are looking for a spreadsheet liting of B2B Contacts to provide consistency and sufficent infrormation that is easy to locate. The BMRG are also looking for a doucment that; 1. Details the change management. This includes change management of the spreadsheet template, roll out to participants as well as how participants make changes; and 2.Details an explanation of each of the fields/contracts on the spreadsheet to remove the current confusion. | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | TBA | Tbc
541 |  | Placement of Business Continuity Process | AEMO | BMRG | 2008-02-25 | Electricity | BMRG | NEM | B2B Procedures - Inconsistency | Placement of Business Continuity Process within the B2B Procedures. As part of the 'Quick Wins' project undertaken under the IEC, a 'Business Continuity Process' was developed by the a Contingency Working Group. The BPRG suggested that this Business Continuity Process be permanently added to the B2B Procedures. | Tbc | Waiting Assessment | N/A | N/A | Tbc | Tbc | Tbc | Continuous Improvement - Prioritised at 1/2 August Meeting BMRG comments: Go through process to publish as Guideline & open issue in QC to later determine if this should be a procedure (per options above). Guideline publication should be issued for review/consultation with the IEC/RMEC Nominated Representatives. | Tbc
Note on P3: Craig Dickson: This section looks to identify what is impacted by the change.